## Delivery
KAFD00330 — RO Plant: Material Delivery Master (edit here; sync to the report)
SL | Project | Div. Ref | Material list | PO No. | Sub-PO No. | PO Status | PO Planned Issue | PO Actual Issue | QTY | PQD No. | Status | MAR No. | Status | Lead Time | Supplier | FAT | Spare Part | Country of Origin | Marine Cargo Insurance | Baseline ETA | ETA | Fabrication / Material Readiness | Shipping | Delivery | MIR | Activity ID | Activity Name
1 | RO | Div No 27-COMMUNICATIONS | ACTIVE (SCADA,RTU,PLC) | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00016 | Approved with Comments | LLI | SIEMENS | N | Y | Germany | Y | 2026-10-11 | #N/A | Started | Not Started | Not Started |  | PR.RO.D40.MTD.1265 | RO l MT Delivery for Process scada system and intrumentation
2 | RO | Div No 28-ELECTRONIC SAFETY AND SECURITY | Access Control | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-STY-MAR-00002 | Rejected | LLI |  | N | Y |  |  | 2026-12-11 |  | Not Started | Not Started | Not Started |  | PR.RO.D28.MTD.1140 | RO l MT Delivery for Access control components
3 | IPS | Div No 28-ELECTRONIC SAFETY AND SECURITY | Access Control | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-STY-MAR-00002 | Rejected | LLI |  | N | Y |  |  | 2026-12-11 |  | Not Started | Not Started | Not Started |  | PR.PS.D28.MTD.1055 | IPS l MT Delivery for Access control components
4 | IPS | Div No 27-COMMUNICATIONS | ACTIVE (SCADA,RTU,PLC) | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00016 | Approved with Comments | LLI | SIEMENS | N | Y | Germany | Y | 2026-10-11 | #N/A | Started | Not Started | Not Started |  | PR.PS.D40.MTD.1110 | IPS l MT Delivery for SCADA
5 | COS | Div No 33-UTILITIES | ACTIVE (SCADA,RTU,PLC) | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00016 | Approved with Comments | LLI | SIEMENS | N | Y | Germany | Y | 2026-10-11 | #N/A | Started | Not Started | Not Started |  | PR.CL.D33.MTD.1025 | CLS l MT Delivery for Remote terminal unit (RTU)
6 | COS | Div No 33-UTILITIES | Fiber Optic Cables | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00004 | Approved with Comments | LLI | Commscope | N | Y | Germany | Y | 2026-10-11 | #N/A | Started | Shipped | Partially Delivered | KAFD-636-SBC-ICT-MIR-00003 | PR.CL.D33.MTD.1030 | CLS l MT Delivery for Fiber Optic Cables
7 | COS | Div No 33-UTILITIES | Fiber Optic Conduits | P01549 | RF(3203)-EQ (8559) - 12-25-Project V02 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00001 KAFD-636-SBC-ELE-MAR-00006 | Approved with Comments | LLI | ITCC | N | Y | Germany | Y | 2026-10-11 | #N/A | Started | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00001 KAFD-636-SBC-ELE-MIR-00012 KAFD-636-SBC-ELE-MIR-00014 KAFD-636-SBC-ELE-MIR-00030 | PR.CL.D33.MTD.1035 | CLS l MT Delivery for Fiber optic conduits
8 | RO | Div No 27-COMMUNICATIONS | ICT Passive | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  | Approved with Comments | GEN | KAFD-636-SBC-ICT-MAR-00004 | Approved with Comments | LLI | Commscope | N | Y | UK | Y | 2026-10-21 | 2026-10-26 | Started | Not Started | Not Started |  | PR.RO.D27.MTD.1130 | RO l MT Delivery for Data communication components
9 | IPS | Div No 27-COMMUNICATIONS | ICT Passive | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  | Approved with Comments | GEN | KAFD-636-SBC-ICT-MAR-00004 | Approved with Comments | LLI | Commscope | N | Y | UK | Y | 2026-10-21 | 2026-10-26 | Started | Not Started | Not Started |  | PR.PS.D27.MTD.1050 | IPS l MT Delivery for Communication System
10 | IPS | Div No 27-COMMUNICATIONS | ICT & Non-ICT Rack Cabinets | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  |  |  | KAFD-636-SBC-ICT-MAR-00005 | Approved with Comments | LLI | GAMMA | N | Y |  | Y | 2026-10-21 | 2026-10-26 | Not Started | Not Started | Not Started |  | PR.PS.D27.MTD.1050 | IPS l MT Delivery for Communication System
11 | RO | Div No 27-COMMUNICATIONS | ICT & Non-ICT Rack Cabinets | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  |  |  | KAFD-636-SBC-ICT-MAR-00005 | Approved with Comments | LLI | GAMMA | N | Y |  | Y | 2026-10-21 | 2026-10-26 | Not Started | Not Started | Not Started |  | PR.RO.D27.MTD.1120 | RO l MT Delivery for Communication equipment fitting
12 | RO | Div No 27-COMMUNICATIONS | ICT ACTIVE | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  |  |  | KAFD-636-SBC-ICT-MAR-00002 | Approved with Comments | GEN | Cisco | N | Y | UK | Y | 2026-11-04 | 2026-11-15 | Started | Not Started | Not Started |  | PR.RO.D27.MTD.1130 | RO l MT Delivery for Data communication components
13 | IPS | Div No 27-COMMUNICATIONS | ICT ACTIVE | P01549 | KAFD-RO-0001 | Issued | 2026-09-15 | TBA |  |  |  | KAFD-636-SBC-ICT-MAR-00002 | Approved with Comments | GEN | Cisco | N | Y | UK | Y | 2026-11-04 | 2026-11-15 | Started | Not Started | Not Started |  | PR.PS.D27.MTD.1050 | IPS l MT Delivery for Communication System
14 | RO | Div No 28-ELECTRONIC SAFETY AND SECURITY | IP CCTV | P01549 | CCTV-V05-26 | Issued | 2026-10-28 | TBA |  |  |  | KAFD-636-SBC-STY-MAR-00001 | Rejected | GEN | DAHUA | N | Y |  | Y | 2026-12-13 |  | Not Started | Not Started | Not Started |  | PR.RO.D28.MTD.1145 | RO l MT Delivery for CCTV system components
15 | IPS | Div No 28-ELECTRONIC SAFETY AND SECURITY | IP CCTV | P01549 | CCTV-V05-26 | Issued | 2026-10-28 | TBA |  |  |  | KAFD-636-SBC-STY-MAR-00001 | Rejected | GEN | DAHUA | N | Y |  | Y | 2026-12-13 |  | Not Started | Not Started | Not Started |  | PR.PS.D28.MTD.1060 | IPS l MT Delivery for CCTV system components
16 | RO | Div No 27-COMMUNICATIONS | IP Telephone | P01549 | IPT-V02-06 | Issued | 2026-09-15 | TBA |  |  |  | KAFD-636-SBC-ICT-MAR-00003 | Approved with Comments | GEN | ALCATEL | N | Y |  | Y | 2026-10-31 | 2026-07-30 | Ready | Shipped | Delivered | KAFD-636-SBC-ICT-MIR-00004 | PR.RO.D27.MTD.1135 | RO l MT Delivery for Telecommunication components
17 | RO | Div No 27-COMMUNICATIONS | Fire Alarm System | P01549 | QuotRO&CO01062025 | Issued | 2026-10-28 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00026 | ,. | GEN | SEMINS | N | Y |  | Y | 2026-12-11 | 2026-08-27 | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00036 | PR.RO.D28.MTD.1150 | RO l MT Delivery for Fire alarm components
18 | IPS | Div No 27-COMMUNICATIONS | Fire Alarm System | P01549 | QuotRO&CO01062025 | Issued | 2026-10-28 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00026 | Approved with Comments | GEN | SEMINS | N | Y |  | Y | 2026-12-11 | 2026-08-27 | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00036 | PR.PS.D28.MTD.1065 | IPS l MT Delivery for Fire alarm system
19 | RO | Div No 26-ELECTRICAL | Lighting Control System | P01549 | KNXX-V02-26 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00025 | Approved with Comments | LLI | SEMINS | N | Y |  | Y | 2026-11-06 | 2026-07-27 | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00037 | PR.RO.D26.MTD.1255 | RO l MT Delivery for Lighting system
20 | RO | Div No 26-ELECTRICAL | UPS | P01549 | PASSIVE-V02-26 | Issued | 2026-09-28 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00024 | Approved with Comments | GEN | RIELLO | N | Y | Italy | Y | 2026-11-06 | 2026-10-15 | Ready | Shipped | Not Started |  | PR.RO.D26.MTD.1105 | RO l MT Delivery for Uninterruptible Power Supply (UPS)
21 | RO | Div No 26-ELECTRICAL | LIGHTING FIXTURE | P01549 | ALAM-260012 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00017 | Approved with Comments | LLI | Aalam Al Inara | N | Y |  | Y | 2026-11-06 | 2026-09-27 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1255 | RO l MT Delivery for Lighting system
22 | IPS | Div No 26-ELECTRICAL | LIGHTING FIXTURE | P01549 | ALAM-260012 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00017 | Approved with Comments | LLI | Aalam Al Inara | N | Y |  | Y | 2026-11-06 | 2026-09-27 | Not Started | Not Started | Not Started |  | PR.PS.D26.MTD.1105 | IPS l MT Delivery for Lighting fixtures
23 | IPS | Div No 26-ELECTRICAL | PANELS | P01549 | Not Assigned | Not Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00048 | Rejected | GEN | ALFANAR | N | Y | KSA | - | 2026-10-24 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.PS.D26.MTD.1095 | IPS l MT Delivery for Panel boards
24 | RO | Div No 26-ELECTRICAL | PANELS | P01549 | Not Assigned | Not Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00048 | Rejected | GEN | ALFANAR | N | Y | KSA | - | 2026-10-24 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board
25 | RO | Div No 26-ELECTRICAL | MCC PANELS | P01549 | Not Assigned | Not Issued | 2026-09-12 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00032 | Rejected | LLI | ALFANAR | N | Y | KSA | - | 2026-11-18 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board
26 | RO | Div No 26-ELECTRICAL | ATS | P01549 | Not Assigned | Not Issued | 2026-09-12 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00048 | Rejected | LLI | ALFANAR | N | N | KSA | - | 2026-11-18 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board
27 | RO | Div No 26-ELECTRICAL | P.F CORRECTION | P01549 | Not Assigned | Not Issued | 2026-09-12 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00048 | Rejected | LLI | ALFANAR | N | Y | KSA | - | 2026-11-18 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board
28 | RO | Div No 26-ELECTRICAL | Synchronization switchboard | P01549 | Not Assigned | Not Issued | 2026-09-12 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00048 | Rejected | LLI | ALFANAR | N | Y | KSA | - | 2026-11-04 | 2027-01-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1240 | RO l MT Delivery for Main distribution board (MDB)
29 | RO | Div No 26-ELECTRICAL | Generators | P01549 | PO-KAFD00330-ELE-004-26 | Issued | 2026-07-09 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00028 | Approved with Comments | LLI | Cummins | N | Y | UK | Y | 2026-11-04 | 2026-12-27 | Started | Not Started | Not Started |  | PR.RO.D26.MTD.1235 | RO l MT Delivery for Diesel Generators
30 | RO | Div No 26-ELECTRICAL | Transformer | P01549 | PO-00330-ELE-002-26 | Issued | 2026-08-06 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00027 | Approved with Comments | LLI | AL-FANAR | N | Y | KSA | - | 2026-12-06 | 2027-01-25 | Started | Not Started | Not Started |  | PR.RO.D26.MTD.1230 | RO l MT Delivery for Meduim-Voltage Transformers
31 | RO | Div No 26-ELECTRICAL | MV - Switchgear | P01549 | PO-00330-ELE-001-26 | Issued | 2026-08-06 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00038 | Rejected | LLI | ALFANAR | N | Y | KSA | - | 2026-11-27 | 2026-12-22 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1225 | RO l MT Delivery for Meduim-Voltage switchgear
32 | RO | Div No 26-ELECTRICAL | BUSWAY | P01549 | PO-KAFD00330-ELE-003-26 | Issued | 2026-09-12 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00041 | Approved with Comments | GEN | BAHRA | N | Y | KSA | - | 2026-09-20 | 2026-11-30 | Not Started | Not Started | Not Started |  | N/a | N/a
33 | RO | Div No 26-ELECTRICAL | Cable Tray, Ladders, & Trunking | P01549 | - | Not Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00012 | Approved with Comments | GEN | Al Fareed / PILLARS INDUSTRy | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Shipped | Partially Delivered | KAFD-636-SBC-ELE-MIR-00031 | PR.RO.D26.MTD.1110 | RO l MT Delivery for Cable routing matrial
34 | RO | Div No 26-ELECTRICAL | Electrical Boxes | P01549 | SIS2605900 INV/2026/07102 | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00003 | Approved with Comments | GEN | ALFANAR STEEL CITY ITCC | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00013 KAFD-636-SBC-ELE-MIR-00017 KAFD-636-SBC-ELE-MIR-00004 KAFD-636-SBC-ELE-MIR-00006 KAFD-636-SBC-ELE-MIR-00010 | PR.RO.D26.MTD.1115 | RO l MT Delivery for Sochets & switches matrial
35 | RO | Div No 26-ELECTRICAL | EMT Conduits, Rigid Conduits & Fittings | P01549 | INV/2025/22996 INV/2026/07102 INV/2026/07228 | Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00001 | Approved with Comments | GEN | ITCC | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00018 KAFD-636-SBC-ELE-MIR-00020 KAFD-636-SBC-ELE-MIR-00022 KAFD-636-SBC-ELE-MIR-00027 KAFD-636-SBC-ELE-MIR-00028 KAFD-636-SBC-ELE-MIR-00029 KAFD-636-SBC-ELE-MIR-00033 KAFD-636-SBC-ELE-MIR-00034 KAFD-636-SBC-ELE-MIR-00001 KAFD-636-SBC-ELE-MIR-00002 KAFD-636-SBC-ELE-MIR-00003 KAFD-636-SBC-ELE-MIR-00007 KAFD-636-SBC-ELE-MIR-00009 KAFD-636-SBC-ELE-MIR-00011 | N/a | N/a
36 | RO | Div No 26-ELECTRICAL | PVC and UPVC Pipes & Fittings | P01549 | INV0007788 | Issued | 2026-10-10 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00008 | Approved with Comments | GEN | Decoduct /EGA | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Shipped | Partially Delivered | KAFD-636-SBC-ELE-MIR-00032 KAFD-636-SBC-ELE-MIR-00008 | N/a | N/a
37 | RO | Div No 26-ELECTRICAL | Safety Switches | P01549 | KAFD-RO-186082-Y3P4 | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00037 | Approved with Comments | GEN | Schneider/GE | N | N | Italy | - | 2026-10-11 | 2026-09-15 | Not Started | Shipped | Partially Delivered | KAFD-636-SBC-ELE-MIR-00035 | PR.RO.D26.MTD.1115 | RO l MT Delivery for Sochets & switches matrial
38 | RO | Div No 26-ELECTRICAL | Wiring Devices | P01549 | Not Assigned | Not Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00036 | Approved with Comments | GEN | ALFANAR | N | Y | KSA | - | 2026-10-11 | 2026-08-26 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1115 | RO l MT Delivery for Sochets & switches matrial
39 | RO | Div No 26-ELECTRICAL | Earthing & Lightning Protection | P01549 | INV/2026/08421 | Issued | 2026-09-01 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00010 | Approved with Comments | LLI | FURSE | N | Y |  | - | 2026-10-31 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00025 | PR.RO.D26.MTD.1245 | RO l MT Delivery for Lightning & Earthing
40 | RO | Div No 26-ELECTRICAL | Cable and Wires | P01549 | Not Assigned | Not Issued | TBA | TBA | [5 empty] | GEN | RYAHD BAHRA ALFANAR | N | Y | KSA | - | 2026-11-27 | 2027-01-16 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1250 | RO l MT Delivery for Low voltage electrical cables
41 | RO | Div No 26-ELECTRICAL | Manhole Covers | P01549 | - | Not Issued | 2026-03-07 | TBA | [5 empty] | GEN | SaudiCast | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Not Started | Partially Delivered |  | N/a | N/a
42 | RO | Div No 26-ELECTRICAL | ELE Manholes | P01549 | 3091 | Issued | 2026-03-07 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00083 | Approved with Comments | GEN | Al-Bilad | N | N | KSA | - | 2026-09-20 | Delivered | Ready | Not Started | Delivered | KAFD-636-SBC-CIV-MIR-00008 KAFD-636-SBC-CIV-MIR-00011 KAFD-636-SBC-CIV-MIR-00012 KAFD-636-SBC-CIV-MIR-00048 KAFD-636-SBC-MEC-MIR-00008 | PR.RO.D27.MTD.1125 | RO l MT Delivery for Communication Cables
43 | COS | Div No 33-UTILITIES | Pre-cast Manholes | P01547 | 3091 | Issued | [19 empty] | PR.CL.D33.MTD.1000 | CLS l MT Delivery for Precast Manholes
44 | RO | Div No 26-ELECTRICAL | Control / Fire Cables | P01549 | Not Assigned | Not Issued | 2026-10-28 | TBA | [5 empty] | GEN | BRIGHT WIRE ELECTRIC HOUSE | N | N |  | - | 2026-12-11 | 2026-09-15 | Not Started | Not Started | Not Started |  | PR.RO.D27.MTD.1125 | RO l MT Delivery for Communication Cables
45 | IPS | Div No 26-ELECTRICAL | Low&Medium Voltage Accessories | P01549 | Not Assigned | Not Issued | TBA | TBA |  | KAFD-636-SBC-ELE-PQD-00011 KAFD-636-SBC-ELE-PQD-00024 | Approved with Comments |  |  | GEN | ELECTRIC HOUSE SESCO | N | N | KSA | - | 2026-11-27 | 2026-08-30 | Not Started | Not Started | Not Started |  | PR.PS.D26.MTD.1100 | IPS l MT Delivery for Low voltage electrical cables
46 | RO | Div No 26-ELECTRICAL | Low&Medium Voltage Accessories | P01549 | Not Assigned | Not Issued | TBA | TBA |  | KAFD-636-SBC-ELE-PQD-00011 KAFD-636-SBC-ELE-PQD-00024 | Approved with Comments |  |  | GEN | ELECTRIC HOUSE SESCO | N | N | KSA | - | 2026-11-27 | 2026-08-30 | Not Started | Not Started | Not Started |  | PR.RO.D26.MTD.1250 | RO l MT Delivery for Low voltage electrical cables
47 | IPS | Div No 22-PLUMBING | UPVC Pipe | P01547 | Done | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00003 | Approved with Comments | GEN | Al Munif | N | N | KSA | - | 2026-05-30 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00001 KAFD-636-SBC-MEC-MIR-00003 KAFD-636-SBC-MEC-MIR-00004 KAFD-636-SBC-MEC-MIR-00005 KAFD-636-SBC-MEC-MIR-00007 KAFD-636-SBC-MEC-MIR-00009 KAFD-636-SBC-MEC-MIR-00011 KAFD-636-SBC-MEC-MIR-00012 KAFD-636-SBC-MEC-MIR-00028 KAFD-636-SBC-MEC-MIR-00048 KAFD-636-SBC-MEC-MIR-00049 | N/a | N/a
48 | COS | Div No 22-PLUMBING | GRP Pipe Gravity | P01547 | SQ006735 | Issued | 2026-04-25 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00008 KAFD-636-SBC-MEC-MAR-00041 | Approved with Comments | LLI | Al Munif | N | N | KSA | - | 2026-05-30 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00014 KAFD-636-SBC-MEC-MIR-00015 KAFD-636-SBC-MEC-MIR-00018 KAFD-636-SBC-MEC-MIR-00021 KAFD-636-SBC-MEC-MIR-00024 KAFD-636-SBC-MEC-MIR-00038 | PR.CL.D33.MTD.1010 | CLS l MT Delivery for GRP pipes
49 | COS | Div No 22-PLUMBING | HDPE Pipe | P01547 | SQ-0488875-9 | Issued | 2026-04-02 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00002 KAFD-636-SBC-MEC-MAR-00056 | Approved with Comments | LLI | Al wasael | N | N | KSA | - | 2026-05-30 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00017 KAFD-636-SBC-MEC-MIR-00019 KAFD-636-SBC-MEC-MIR-00022 KAFD-636-SBC-MEC-MIR-00023 KAFD-636-SBC-MEC-MIR-00025 KAFD-636-SBC-MEC-MIR-00026 KAFD-636-SBC-MEC-MIR-00027 KAFD-636-SBC-MEC-MIR-00029 KAFD-636-SBC-MEC-MIR-00030 | PR.CL.D33.MTD.1015 | CLS l MT Delivery for HDPE pipes
50 | IPS | Div No 22-PLUMBING | Covers | P01547 | QO-045251-1 QO-045252-2 | Issued | 46088 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00015 | Approved with Comments | GEN | SaudiCast | N | N | KSA | - | 2026-09-25 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-ELE-MIR-00016 KAFD-636-SBC-ELE-MIR-00024 KAFD-636-SBC-ELE-MIR-00026 | N/a | N/a
51 | COS | Div No 33-UTILITIES | General duty valves | P01547 | DV245757 | Issued | 2026-04-25 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00005 KAFD-636-SBC-MEC-MAR-00011 KAFD-636-SBC-MEC-MAR-00013 KAFD-636-SBC-MEC-MAR-00014 KAFD-636-SBC-MEC-MAR-00019 KAFD-636-SBC-MEC-MAR-00044 KAFD-636-SBC-MEC-MAR-00057 | Approved with Comments | LLI | TECOFI | Y | Y | France | Y | 2026-06-26 | 2026-10-25 | Ready | Shipped | Not Started |  | PR.CL.D33.MTD.1020 | CLS l MT Delivery for General Duty valves
52 | IPS | Div No 22-PLUMBING | Valves | P01547 | DV245757 | Issued | 2026-04-25 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00005 KAFD-636-SBC-MEC-MAR-00011 KAFD-636-SBC-MEC-MAR-00013 KAFD-636-SBC-MEC-MAR-00014 KAFD-636-SBC-MEC-MAR-00019 KAFD-636-SBC-MEC-MAR-00044 KAFD-636-SBC-MEC-MAR-00057 | Approved with Comments | LLI | TECOFI | Y | Y | France | Y | 2026-06-26 | 2026-10-25 | Ready | Shipped | Not Started |  | PR.PS.D22.MTD.1040 | IPS l MT Delivery for Plumbing valves
53 | IPS | Div No 21-FIRE SUPPRESSION | Firefighting | P01547 | 939 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00002 KAFD-636-SBC-FFI-MAR-00003 KAFD-636-SBC-FFI-MAR-00004 KAFD-636-SBC-FFI-MAR-00005 KAFD-636-SBC-FFI-MAR-00006 KAFD-636-SBC-FFI-MAR-00007 KAFD-636-SBC-FFI-MAR-00008 | Approved with Comments | LLI | ELITE | N | N |  | - | 2026-09-10 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00050 | PR.PS.D21.MTD.1080 | IPS l MT Delivery for Clean Agent FK-5.1.12 cylinders
54 | IPS | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | EXHAUST FANSFANS | P01547 | QN - QUO-4367545-X7G2K4 Rev. 0 | Issued | 2026-04-22 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00080 | Approved with Comments | GEN | AIR SYSTEM | N | Y |  | Y | 2026-10-07 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00032 KAFD-636-SBC-MEC-MIR-00033 | PR.PS.D23.MTD.1090 | IPS l MT Delivery for HVAC System
55 | IPS | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | SRAC-01H/SRCU-01H (Split AC) | P01547 | Done | Issued | 2026-04-22 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00091 | Approved with Comments | GEN | LG | N | Y | China | - | 2026-10-07 | Delivered | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00051 | PR.PS.D23.MTD.1090 | IPS l MT Delivery for HVAC System
56 | RO | Div No 10-SPECIALTIES | TOILET, BATH, AND LAUNDRY ACCESSORIES (Soap dispenser, Paper Towel, paper holder, Robe Hook, Grab Bar, Swing up grap bar, Tilted Mirror, Mirror, Waste bin | P01497 | Not Assigned | Not Issued | 2026-08-18 | TBA | [5 empty] | GEN | Saudi Ceramic | N | N |  | - | 2027-01-24 |  | Not Started | Not Started | Not Started |  | PR.RO.D22.MTD.1080 | RO l MT Delivery for Plumbing Fixtures
57 | RO | Div No 10-SPECIALTIES | TOILET COMPARTMENTS | P01497 | Not Assigned | Not Issued | 2026-08-18 | TBA | [5 empty] | GEN | Maica Laminates Sdn Bhd | N | Y |  | - | 2027-01-24 |  | Not Started | Not Started | Not Started |  | PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting
58 | RO | Div No 10-SPECIALTIES | Fire Extinguishers (Dry Chemical, Carbon Dioxide CO2, Wet Chemical, Pressurized Water/F.F.F.P. Foam type | P01497 | PO-00225 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00008 | Approved with Comments | GEN | NATIONAL FIRE FIGHTING MANUFACTURING FZCO | N | N | UAE | - | 2026-10-17 | 2026-09-15 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1190 | RO l MT Delivery for Foam Water system
59 | RO | Div No 12-FURNISHINGS | SOLID SURFACING COUNTERTOPS | P01497 | Not Assigned | Not Issued | TBA | TBA | [5 empty] | GEN | future Idea company (fikra ) /Al Jawad AlHUR industrials factorLong Lead | N | N |  | - | 2027-01-24 |  | Not Started | Not Started | Not Started |  | N/a | N/a
60 | RO | Div No 22-PLUMBING | Oil interceptors | P01497 | PO-00213 | Issued | 2026-06-16 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00053 | Approved with Comments | LLI | MIFAB,INC. | Y | N | USA | Y | 2026-10-18 | 2026-10-22 | Ready | Shipped | Delivered |  | PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting
61 | RO | Div No 21-FIRE SUPPRESSION | fire Department connection | P01497 | PO-00235 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00053 | Approved with Comments | LLI | Reliable | N | N | China and USA | Y | 2026-10-04 | 2026-10-20 | Ready | Shipped | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
62 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 119 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
63 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1.1/4" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 25 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
64 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1.1/2" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 50 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
65 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 2" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 17 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
66 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 2.1/2" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 15 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
67 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 3" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 21 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
68 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 4" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 36 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
69 | RO | Div No 21-FIRE SUPPRESSION | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 6" | P01497 | PO-00233 | Issued | 2026-08-18 | TBA | 20 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-04 | 2026-02-01 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
70 | RO | Div No 21-FIRE SUPPRESSION | fire suppression valves | P01497 | PO-00235 | Issued | 2026-08-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00003 | Approved with Comments | GEN | Reliable | N | N |  | - | 2026-10-04 | 2026-11-05 | Ready | Shipped | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
71 | RO | Div No 21-FIRE SUPPRESSION | sprinklers | P01497 | PO-00235 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00003 | Approved with Comments | LLI | Reliable | N | Y | USA | Y | 2026-10-04 | 2026-09-20 | Ready | Shipped | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
72 | RO | Div No 21-FIRE SUPPRESSION | Fire Hose Cabinet | P01497 | PO-00224 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00007 | Approved with Comments | LLI | NATIONAL FIRE FIGHTING MANUFACTURING FZCO | N | N | UAE | - | 2026-10-17 | 2026-10-15 | Ready | Shipped | Delivered | KAFD-636-SBC-FFI-MIR-00001 | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
73 | RO | Div No 21-FIRE SUPPRESSION | Foam System | P01497 | PO-00224 | Issued | 2026-08-20 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00004 | Approved with Comments | LLI | NATIONAL FIRE FIGHTING MANUFACTURING FZCO | N | Y | UAE | - | 2026-11-18 | 2026-10-25 | Ready | Shipped | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
74 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving LV Room (004) on ground floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
75 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving Transformer and MV-SWGR (006) on ground floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
76 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving Admin and PLC Scada Room (011) on first floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
77 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving Telecom Room (018) on first floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
78 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving UPS Room (005) on first floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
79 | RO | Div No 21-FIRE SUPPRESSION | Clean agent FK-5.1.12 cylinders serving Electrical Room (002) on second floor | P01497 | PO-00222 | Issued | 2026-09-22 | TBA | 1 |  |  | KAFD-636-SBC-FFI-MAR-00006 | Approved with Comments | LLI | Avenger System | N | Y | Usa/singapore | Y | 2026-12-24 | 2026-11-26 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System
80 | RO | Div No 21-FIRE SUPPRESSION | Fire Pump Set | P01497 | PO-00223 | Issued | 2026-07-18 | TBA |  |  |  | KAFD-636-SBC-FFI-MAR-00005 | Approved with Comments | LLI | NATIONAL FIRE FIGHTING MANUFACTURING FZCO | N | Y | UAE | - | 2026-10-17 | 2026-11-15 | Started | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
81 | RO | Div No 22-PLUMBING | General duty valves | P01497 | PO-00215 | Issued | 2026-04-25 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00044 | Approved with Comments | LLI | Tecofi France | Y | Y | France | Y | 2026-09-06 | 2026-12-25 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
82 | RO | Div No 22-PLUMBING | Valves (Ball valves, Gate valves, Globe valves, Check Valve, ButterflLong Lead Valve, Motorized Butterfly Valve | P01497 | PO-00218 | Issued | 2026-07-28 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00019 | Approved with Comments | GEN | WATTS INDUSTRIES MIDDLE EAST FZE | N | Y |  | - | 2026-09-06 | 2026-11-11 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
83 | RO | Div No 22-PLUMBING | Water Meters | P01497 | Not Assigned | Not Issued | 2026-07-28 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00075 | Approved with Comments | GEN | Modern Arab Enterprises Co. Ltd. | N | Y |  | - | 2026-09-06 |  | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
84 | RO | Div No 22-PLUMBING | Water Hammer Arrestor | P01497 | PO-00218 | Issued | 2026-07-28 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00019 | Approved with Comments | GEN | WATTS INDUSTRIES MIDDLE EAST FZE | N | N |  | - | 2026-09-06 | 2026-11-11 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
85 | RO | Div No 22-PLUMBING | Hose Bibs | P01497 | PO-00218 | Issued | 2026-08-18 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00019 | Approved with Comments | GEN | WATTS INDUSTRIES MIDDLE EAST FZE | N | N |  | - | 2026-09-06 | 2026-11-11 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
86 | RO | Div No 22-PLUMBING | Water Softener | P01497 | PO-00221 | Issued | 2026-06-29 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00046 | Approved with Comments | LLI | Veolia Water Tech | Y | Y | BELGIUM - USA - ITALY - INDIA | Y | 2026-10-18 | 2026-10-27 | Started | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00058 | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
87 | RO | Div No 22-PLUMBING | Chemical Dosing Unit | P01497 | 46159 | Issued | 2026-06-29 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00050 | Approved with Comments | LLI | PROMINENT GMBH | Y | Y | Germany - Arab United of Emarites | Y | 2026-10-18 | 2026-10-30 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
88 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | HVAC Controller and Field insrumatations | P01497 | 46188 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-ELE-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | N | KSA | Y | 2026-10-20 | 2026-12-15 | Started | Not Started | Not Started |  | N/a | N/a
89 | RO | Div No 22-PLUMBING | sanitry waste Drains (Roof Drains, Cleanouts, Floor Cleanouts, Floor Drains, Trench Drains) | P01497 | Not Assigned | Not Issued | 2026-07-23 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00086 | Approved with Comments | GEN | ZURN INDUSTRIES, LLC | N | N |  | - | 2026-09-01 |  | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00041 | PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting
90 | RO | Div No 22-PLUMBING | Supporting System and Siamese Connection - Fire | P01497 | 46218 | Issued | 2026-07-18 | TBA | [5 empty] | LLI | Easy / Star Enterprizes | N | N | KSA | - | 2026-10-04 |  | Not Started | Not Started | Not Started |  | PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting
91 | RO | Div No 22-PLUMBING | Sanitary and plumbing Fixtures | P01497 | Not Assigned | Not Issued | 2026-08-18 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00042 | Approved with Comments | GEN | Saudi Ceramic | N | Y |  | - | 2026-09-29 |  | Not Started | Not Started | Not Started |  | PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting
92 | RO | Div No 22-PLUMBING | drainge inpection chamber | P01497 | Not Assigned | Not Issued | 2026-03-07 | TBA | [5 empty] | GEN |  | N | N |  | - | 2026-09-01 |  | Not Started | Not Started | Not Started |  | PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting
93 | RO | Div No 21-FIRE SUPPRESSION | Recirculing pumps for fire suppression system | P01497 | PO-00208 | Issued | 2026-07-18 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00031 | Approved with Comments | LLI | KSB PUMPS ARABIA LTD | Y | Y | KSA | - | 2026-10-18 | 2026-10-31 | Ready | Not Started | Not Started |  | PR.RO.D21.MTD.1185 | RO l MT Delivery for Fire Suppression equipment
94 | RO | Div No 22-PLUMBING | GRP Pipes & Fittings RO Building | P01497 | Not Assigned | Not Issued | 2026-04-22 | TBA | [5 empty] | GEN | Munir Abdullah Al Munif Factory | N | N |  | - | 2026-09-06 |  | Not Started | Not Started | Not Started |  | PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves
95 | RO | Div No 22-PLUMBING | Electric Water Heater | P01497 | PO-00216 | Issued | 2026-06-16 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00020 | Approved with Comments | LLI | A.O. SMITH MIDDLE EAST & AFRICA | Y | N | USA | Y | 2026-10-18 | 2026-10-22 | Started | Shipped | Delivered |  | PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment
96 | RO | Div No 22-PLUMBING | Booster Pumps | P01497 | PO-00208 | Issued | 2026-06-16 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00031 | Approved with Comments | LLI | KSB PUMPS ARABIA LTD | Y | Y | KSA | - | 2026-10-18 | 2026-10-31 | Ready | Not Started | Not Started |  | PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment
97 | RO | Div No 22-PLUMBING | Circulation pumps | P01497 | PO-00208 | Issued | 2026-06-16 | TBA | 3 |  |  | KAFD-636-SBC-MEC-MAR-00031 | Approved with Comments | LLI | KSB PUMPS ARABIA LTD | Y | Y | KSA | - | 2026-10-18 | 2026-10-31 | Ready | Not Started | Not Started |  | PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment
98 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Supporting System - Duct | P01497 | PO-00232 | Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Easyfix / Star Enterprizes | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
99 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 3/4" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 44 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
100 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 14 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
101 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1.1/4" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 20 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
102 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 1.1/2" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 7 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
103 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 2" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 23 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
104 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.B 6MTRS. Jazeera Oman BPW40O 2.1/2" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 26 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
105 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 3" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 13 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
106 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 4" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 9 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
107 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Black Pipe ERW SCH40 A53 GR.A 6MTRS. Jazeera Oman BPW40O 6" | P01497 | PO-00232 | Issued | 2026-08-13 | TBA | 26 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | Ideal Caliber Company | N | N |  | - | 2026-10-20 |  | Not Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
108 | RO | Div No 22-PLUMBING | Potable water storage tanks ( GRP Tanks ) | P01497 | PO-00206 | Issued | 2026-06-16 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00041 | Approved with Comments | LLI | Pipeco Water Tanks Co | Y | N | KSA | - | 2026-11-02 | 2026-10-20 | Ready | Not Started | Not Started |  | PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment
109 | RO | Div No 22-PLUMBING | Filters | P01497 | PO-00221 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00046 | Approved with Comments | LLI | Veolia Water Tech | Y | Y |  | - | 2026-10-18 | 2026-10-25 | Started | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00058 | PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment
110 | RO | Div No 22-PLUMBING | Dismantling Joints | P01497 | PO-00215 | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00055 | Approved with Comments | LLI | Tecofi France | Y | N | France | Y | 2026-09-06 | 2026-12-25 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves
111 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Hydronic pipes with fitting | P01497 | PO-00232 | issued | 2026-08-15 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | KSB PUMPS ARABIA LTD | N | Y |  | - | 2026-10-01 | 2026-02-01 | Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
112 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | PVC condensate Draine | P01497 | PO-00232 | issued | 2026-08-15 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00003 | Approved with Comments | GEN | Munir Abdullah Al Munif Factory | N | N |  | - | 2026-10-01 | 2026-02-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00001 KAFD-636-SBC-MEC-MIR-00003 KAFD-636-SBC-MEC-MIR-00004 KAFD-636-SBC-MEC-MIR-00005 KAFD-636-SBC-MEC-MIR-00007 KAFD-636-SBC-MEC-MIR-00009 KAFD-636-SBC-MEC-MIR-00011 KAFD-636-SBC-MEC-MIR-00012 KAFD-636-SBC-MEC-MIR-00028 KAFD-636-SBC-MEC-MIR-00048 KAFD-636-SBC-MEC-MIR-00049 | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
113 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Condensate Pipes & Fittings | P01497 | PO-00232 | issued | 2026-08-15 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | GEN | JAZEERA OMAN PIPE | N | N |  | - | 2026-10-01 | 2026-02-01 | Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
114 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | meter and Gauge for HVAC | P01497 | PO-00219 | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00071 | Approved with Comments | LLI | WATTS INDUSTRIES MIDDLE EAST FZE | N | Y |  | - | 2026-10-20 | 2026-11-13 | Started | Not Started | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
115 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | HVAC valves | P01497 | PO-00219 | Issued | 2026-08-15 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00071 | Approved with Comments | GEN | WATTS INDUSTRIES MIDDLE EAST FZE | N | Y |  | - | 2026-10-01 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves
116 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Single Skin Rectangular ducts and fittings | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 2,527.08 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
117 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Fire Rated Non Coated Rectangular ducts and fittings - APPLUS Approved BS476 | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 208.76 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
118 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Corner | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 820 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
119 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Mate Flange Galvanized 35mm | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 61.20 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
120 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Galvanized Rectangular Angle bar 30x30x3mm | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 24.80 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
121 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Single Skin Rectangular ducts and fittings | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 5,524.62 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
122 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Fire Rated Non Coated Rectangular ducts and fittings - APPLUS Approved BS476 | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 191.60 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
123 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Aluminum Rectangular ducts and fittings - 3.0mm thick | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 351.74 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
124 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Corner | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 532 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
125 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Mate Flange Galvanized 35mm | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 51 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
126 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Galvanized Rectangular Angle bar 30x30x3mm | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 17.70 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
127 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Wiremesh | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 0.36 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
128 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Single Skin Rectangular ducts and fittings | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 5,146.01 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
129 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Corner | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 1,432 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
130 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Wiremesh | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 0.45 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
131 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Duct Corner | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 104 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
132 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | GI Wiremesh | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 0.72 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
133 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | SS 304 Round ducts and fittings - 1.2mm thick, Fully welded | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 166.99 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
134 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | SS 304 Round Angle bar 30x30x3mm | P01497 | PO-00239 | Issued | 2026-08-13 | TBA | 43.40 |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
135 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Flexible duct | P01497 | PO-00240 | Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | N |  | - | 2026-09-25 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts
136 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Dampers (Volume dampers, Fire dampers, Motorized Fire Smoke Dampers , Motorized Dampers) | P01497 | PO-00236 | Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00049 | Approved with Comments | GEN | CUBE-METAL INDUSTRIES | N | Y |  | - | 2026-10-20 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1095 | RO l MT Delivery for HVAC Accessories
137 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Air Outlets (Supply Return Slot Linear Diffusers, Supply/Return Registers, Supply/Return Square diffusers, Exhaust Registers, Sand Trap Fresh Air Louvers, Door Grilles) | P01497 | PO-00237 | Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00023 | Approved with Comments | GEN | GULF GRILLS CO | N | N |  | - | 2026-10-20 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1095 | RO l MT Delivery for HVAC Accessories
138 | RO | Div No 22-PLUMBING | Submersible sump Pumps RO Building | P01497 | PO-00208 | Issued | 2026-06-16 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00031 | Approved with Comments | LLI | GRANDFOS | Y | Y | Germany | Y | 2026-10-18 | 2026-10-31 | Ready | Not Started | Not Started |  | PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves
139 | RO | Div No 22-PLUMBING | Filteration Equipment (Backwash screen filters ) | P01497 | PO-00221 | Issued | 2026-06-29 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00046 | Approved with Comments | LLI | Veolia Water Tech | Y | N | BELGIUM - USA - ITALY - INDIA | Y | 2026-10-18 | 2027-02-13 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves
140 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-FF-01 (1710x2040) 5600 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
141 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-SF-02 (910x1250) 1290 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
142 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-SF-03 (1580x1910) 4710 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
143 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-SF-04 (1460x1520) 3200 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
144 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-SF-05 (1580x1780) 4320 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
145 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | AHU-SF-01 (1290x2000) 3720 - Modular Indoor Central-Station Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 3 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
146 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FAHU-SF-01 (660x870) 450 - Fresh Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
147 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FAHU-SF-02 (900x1110) 1090 - Fresh Air Handling Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-11-18 | 2026-10-01 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00053 | PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units
148 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-01E (FWW400VA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
149 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-01H (FWW400VA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 7 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
150 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-02H (FWW700VA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 6 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
151 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-03H (FWW1000VA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
152 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-04 (FWW1400VA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
153 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-05 (FWW1600TA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
154 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-05H (FWW1600TA-EC) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 3 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
155 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-03E (FWW800BA) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
156 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | FCU-BOH-05E (FWW1400BA) - Fan Coil Unit | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
157 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | SRAC-01H/SRCU-01H Airfel Split On-Off R410 - Split-System Air Conditioner | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1220 | RO l MT Delivery for Split & Fan coil Units & Exhaust Fans
158 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | SRAC-03/SRCU-03 Airfel Split On-Off R410 - Split-System Air Conditioner | P01497 | PO-00211 | Issued | 2026-08-06 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00030 | Approved with Comments | LLI | Daikin Air Conditioning Saudi Arabia LLC | Y | Y | KSA | - | 2026-10-23 | 2026-11-01 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
159 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Exhaust Fans | P01497 | PO-00207 | Issued | 2026-08-06 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00029 | Approved with Comments | LLI | Rosenberg Ventilatoren GmbH | Y | Y | Germany | Y | 2026-10-23 | 2026-10-25 | Ready | Shipped | Delivered |  | PR.RO.D23.MTD.1220 | RO l MT Delivery for Split & Fan coil Units & Exhaust Fans
160 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Expansion tanks | P01497 | PO-00209 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00018 | Approved with Comments | LLI | TACO | Y | N | USA | - | 2026-11-22 | 2026-12-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
161 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Air Separator | P01497 | PO-00209 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00017 | Approved with Comments | LLI | TACO | Y | N | USA | - | 2026-11-22 | 2026-12-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
162 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | HYDRONIC PUMPS | P01497 | PO-00208 | Issued | 2026-09-03 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00035 | Approved with Comments | LLI | KSB PUMPS ARABIA LTD | Y | Y | Germany - Arab United of Emarites | Y | 2026-11-22 | 2026-10-31 | Ready | Not Started | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
163 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | PLATE HEAT EXCHANGER | P01497 | PO-00210 | Issued | 2026-09-03 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00016 | Approved with Comments | LLI | HEXONIC | Y | N | KSA | - | 2026-11-22 | 2026-11-15 | Ready | Shipped | Not Started |  | PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment
164 | RO | Div No 23-HEATING, VENTILATING AND AIR CONDITIONING | Centrifugal HVAC FANS | P01497 | PO-00207 | Issued | 2026-08-06 | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00029 | Approved with Comments | LLI | Rosenberg Ventilatoren GmbH | Y | Y | Germany | Y | 2026-10-23 | 2026-11-01 | Started | Not Started | Not Started |  | PR.RO.D23.MTD.1220 | RO l MT Delivery for Split & Fan coil Units & Exhaust Fans
165 | RO | Div No 31-EARTHWORK | Backfilling behind basement walls from foundation level up to basement slab level using red sand, compacted as per standard and code | P01720 | - | Issued | TBA | TBA | 3800 |  |  |  |  | GEN | Desert Shine | N | N | KSA | - |  |  | Ready | Not Started | Not Started |  | N/a | N/a
166 | RO | Div No 22-PLUMBING | KSB Vertical Turbines | P01694 | - | Issued | 2026-06-16 | 2026-04-16 | 8 |  |  | KAFD-636-SBC-ELE-MAR-00031 | Approved with Comments | LLI | KSB | Y | Y | KSA | - |  | 2026-09-19 | Started | Not Started | Not Started |  | PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves
167 | RO | Div No 33-UTILITIES | GRP Tank for back wash process 8 x 6.5 x 3.5m | P01690 | - | Issued | TBA | TBA | 1 |  |  | KAFD-636-SBC-MEC-MAR-00058 | Approved with Comments | LLI | Pipeco Water Tanks Co | N | N | KSA | - | 2026-11-02 |  | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
168 | RO | Div No 31-EARTHWORK | Supply & Installation uPVC Perforated Pipes DN200 mm for Under Ground Water Control System | P01690 | - | Not Issued | TBA | TBA | 187 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | GEN | CLC | N | N | KSA | - | 2026-09-06 |  | Started | Not Started | Not Started |  | N/a | N/a
169 | RO | Div No 31-EARTHWORK | Supply & Installation Sump Well, uPVC Pipe DN400 mm for Under Ground Water Control System | P01690 | - | Not Issued | TBA | TBA | 10 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | GEN | CLC | N | N | KSA | - | 2026-09-06 |  | Started | Not Started | Not Started |  | N/a | N/a
170 | RO | Div No 31-EARTHWORK | Supply & Installation of Submersible Pump (GR-SP-1) | P01690 | PO-00208 | Issued | TBA | TBA | 1 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | CLC | N | Y | KSA | - | 2026-10-18 | 2026-09-19 | Started | Not Started | Not Started |  | N/a | N/a
171 | COS | Div No 22-PLUMBING | Pump SP-P4.11.1 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 12 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Ready | Shipped | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
172 | COS | Div No 22-PLUMBING | Pump SP-P4.11.2 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 3 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Ready | Shipped | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
173 | COS | Div No 22-PLUMBING | Pump SP-P2.15 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 4 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Started | Not Started | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
174 | COS | Div No 22-PLUMBING | Pump SP-P2.09 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 3 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Ready | Shipped | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
175 | COS | Div No 22-PLUMBING | Pump SP-P1.11 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 6 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Started | Not Started | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
176 | COS | Div No 22-PLUMBING | Pump SP-P5.06 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 6 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Started | Not Started | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
177 | COS | Div No 22-PLUMBING | Pump SP-P3.10 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 6 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Ready | Shipped | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
178 | COS | Div No 22-PLUMBING | Pump SP-P5.03 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 6 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Started | Not Started | Not Started |  | PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps
179 | IPS | Div No 22-PLUMBING | Pump SP-01 | P01650 | - | Issued | 2026-06-16 | 2026-04-06 | 4 |  |  | KAFD-636-SBC-ELE-MAR-00021 | Approved with Comments | LLI | KSB | Y | Y | KSA | - | 2026-08-23 | 2026-09-19 | Started | Not Started | Not Started |  | PR.PS.D22.MTD.1085 | IPS l MT Delivery for Submersible pumps
180 | RO | Div No 08-OPENINGS | Hollow Metal Doors and Frames | P01285 | - | Not Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00038 | Rejected | LLI | Rollec | N | N | KSA | - | 2026-09-14 |  | Not Started | Not Started | Not Started |  | PR.RO.D08.MTD.1175 | RO l MT Delivery for Acoustic & Fire rated doors
181 | RO | Div No 08-OPENINGS | Hollow Metal Doors and Frames | P01285 | - | Not Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00038 | Rejected | LLI | Rollec | N | N | KSA | - | 2026-09-14 |  | Not Started | Not Started | Not Started |  | PR.RO.D08.MTD.1050 | RO l MT Delivery for Steel doors
182 | RO | Div No 08-OPENINGS | ROLLING SHUTTER DOOR, | P01966 | - | Issued | 2026-08-13 | TBA | 8 |  |  | KAFD-636-SBC-ARC-MAR-00036 | Rejected | LLI | Crawford | N | N | KSA | - | 2026-09-14 |  | Not Started | Not Started | Not Started |  | PR.RO.D08.MTD.1050 | RO l MT Delivery for Steel doors
183 | RO | Div No 08-OPENINGS | Hardware | P01285 | - | Not Issued | 2026-08-13 | TBA | List |  |  | KAFD-636-SBC-ARC-MAR-00038 | Rejected | LLI | Rollec | N | N | KSA | - | 2026-09-14 |  | Not Started | Not Started | Not Started |  | PR.RO.D08.MTD.1050 | RO l MT Delivery for Steel doors
184 | IPS | Div No 08-OPENINGS | Hollow Metal Doors and Frames | P01285 | - | Not Issued | 2026-08-13 | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00038 | Rejected | LLI | Rollec | N | N | KSA | - | 2026-11-01 |  | Not Started | Not Started | Not Started |  | N/a | N/a
185 | IPS | Div No 08-OPENINGS | Hardware | P01285 | - | Not Issued | 2026-08-13 | TBA | List |  |  | KAFD-636-SBC-ARC-MAR-00038 | Rejected | LLI | Rollec | N | N | KSA | - | 2026-11-01 |  | Not Started | Not Started | Not Started |  | N/a | N/a
186 | RO | Div No 32-EXTERIOR IMPROVEMENTS | Asphalt Works | Not Assigned | Not Assigned | Not Issued | 2026-09-12 | TBA | [5 empty] | GEN |  | N | N | KSA | - | 2027-01-11 |  | Not Started | Not Started | Not Started |  | N/a | N/a
187 | RO | Div No 32-EXTERIOR IMPROVEMENTS | Fence | P01868 | - | Issued | 2026-08-08 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00117 | Under Review | GEN | NAJD | N | N | KSA | - |  |  | Not Started | Not Started | Not Started |  | PR.RO.D32.MTD.1160 | RO l MT Delivery for Precast concrete wall
188 | IPS | Div No 32-EXTERIOR IMPROVEMENTS | Fence | P01868 | - | Issued | 2026-08-08 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00117 | Under Review | GEN | NAJD | N | N | KSA | - |  |  | Not Started | Not Started | Not Started |  | N/a | N/a
189 | RO | Div No 32-EXTERIOR IMPROVEMENTS | Gate | P01868 | - | Issued | 2026-08-08 | TBA | [5 empty] | GEN | NAJD | N | N | KSA | - | 2027-01-11 |  | Not Started | Not Started | Not Started |  | N/a | N/a
190 | IPS | Div No 32-EXTERIOR IMPROVEMENTS | Gate | P01868 | - | Issued | 2026-08-08 | TBA | [5 empty] | GEN | NAJD | N | N | KSA | - | 2026-12-08 |  | Not Started | Not Started | Not Started |  | N/a | N/a
191 | IPS | Div No 32-EXTERIOR IMPROVEMENTS | Softscape | P01576 | - | Issued | 2026-09-05 | TBA |  |  |  | KAFD-636-SBC-LAN-MAR-00004 | Under Review | GEN | NAHDA | N | N |  | - | 2026-10-12 |  | Not Started | Not Started | Not Started |  | PR.PS.D32.MTD.1075 | IPS l MT Delivery for Planting
192 |  |  | Building Finishes - Furniture | Not Assigned | Not Assigned | Not Issued | 2026-07-04 | TBA | [5 empty] | GEN |  | N | N |  | - |  |  | Not Started | Not Started | Not Started |  | PR.RO.D09.MTD.1060 | RO l MT Delivery for Floor
193 |  |  | Building Finishes - Furniture | [22 empty] | PR.RO.D09.MTD.1055 | RO l MT Delivery for Gypsum board
194 | RO | Div No 05-METALS | Trench Covers | P02045 | - | Issued | 2026-08-22 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00122 | Approved with Comments | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | N/a | N/a
195 | RO | Div No 05-METALS | Handrail | P02045 | - | Issued | 2026-07-09 | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00005 | Rejected | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | N/a | N/a
196 | RO | Div No 05-METALS | Hatch Cover | P02045 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00064 | Rejected | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | N/a | N/a
197 | RO | Div No 05-METALS | Ladders | P02045 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00062 | Rejected | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | N/a | N/a
198 | IPS | Div No 05-METALS | Trench Covers | P02045 | - | Issued | 2026-08-22 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00122 | Approved with Comments | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | PR.PS.D05.MTD.1015 | IPS l MT Delivery for Trench covers
199 | IPS | Div No 05-METALS | Hatch Cover | P02045 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00064 | Rejected | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | N/a | N/a
200 | RO | Div No 32-EXTERIOR IMPROVEMENTS | Car parking shade | P01868 | - | Issued | 2026-07-09 | TBA | [5 empty] | GEN | NAJD | N | N | KSA | - | 2027-01-24 |  | Not Started | Not Started | Not Started |  | N/a | N/a
201 | RO | N/a | Over head crane | P01888 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-MEC-MAR-00083 | Approved with Comments | LLI | Crane and Steel | N | N | Italy | Y | 2027-01-26 |  | Not Started | Not Started | Not Started |  | N/a | N/a
202 | RO | N/a | Penstock | P01890 | - | Issued | 2026-07-21 | TBA |  |  |  | KAFD-636-SBC-MEP-MAR-00001 | Approved with Comments | LLI | Tawajer | N | N | Germany | Y | - | 2026-12-25 | Not Started | Not Started | Not Started |  | N/a | N/a
203 | RO | Div No 33-UTILITIES | R.O skids | P01039 | - | Issued | 2026-06-29 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00012 | Approved with Comments | LLI | Veolia | Y | N | Germany | Y | 2026-11-30 | 2026-09-21 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00052 | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
204 | RO | Div No 33-UTILITIES | R.O Cartridge filters | P01039 | - | Issued | 2026-06-29 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00006 | Approved with Comments | LLI | Veolia | Y | N | Spain | Y | 2026-11-30 | 2026-09-21 | Ready | Shipped | Delivered | KAFD-636-SBC-MEC-MIR-00054 | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
205 | RO | Div No 33-UTILITIES | CIP Cartridge filters | P01039 | - | Issued | 2026-06-29 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00006 | Approved with Comments | LLI | Veolia | Y | Y | Hungary | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started | KAFD-636-SBC-MEC-MIR-00054 | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
206 | RO | Div No 33-UTILITIES | Dosing skids | P01039 | - | Issued | 2026-06-29 | TBA | 8 |  |  | KAFD-636-SBC-MEC-MAR-00009 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
207 | RO | Div No 33-UTILITIES | Static Mixers | P01039 | - | Issued | 2026-06-29 | TBA | 3 |  |  | KAFD-636-SBC-MEC-MAR-00025 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started | KAFD-636-SBC-MEC-MIR-00055 | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
208 | RO | Div No 33-UTILITIES | Media for filters | P01039 | - | Issued | 2026-06-29 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00034 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
209 | RO | Div No 33-UTILITIES | High pressure pumps | P01039 | - | Issued | 2026-06-29 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00007 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
210 | RO | Div No 33-UTILITIES | Backwash pumps | P01039 | - | Issued | 2026-06-29 | TBA | 3 |  |  | KAFD-636-SBC-MEC-MAR-00007 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
211 | RO | Div No 33-UTILITIES | CIP pumps | P01039 | - | Issued | 2026-06-29 | TBA | 4 |  |  | KAFD-636-SBC-MEC-MAR-00007 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
212 | RO | Div No 33-UTILITIES | Air blowers | P01039 | - | Issued | 2026-06-29 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00047 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
213 | RO | Div No 33-UTILITIES | CIP Heaters | P01039 | - | Issued | 2026-06-29 | TBA | 2 |  |  | KAFD-636-SBC-MEC-MAR-00074 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
214 | RO | Div No 33-UTILITIES | Dosing tanks | P01039 | - | Issued | 2026-06-29 | TBA | 8 |  |  | KAFD-636-SBC-MEC-MAR-00067 | Approved with Comments | LLI | Veolia | Y | Y | Italy | Y | 2026-11-30 | 2026-09-21 | Started | Not Started | Not Started |  | PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant
215 | RO | Div No 03-CONCRETE | C32 MPA Concrete | P01550 | List | Issued | TBA | 2026-03-04 |  |  |  | KAFD-636-SBC-CIV-MAR-00089 | Approved with Comments | GEN | Green Concrete | N | N | KSA | - | 2026-05-04 |  | Started | Shipped | Partially Delivered |  | N/a | N/a
216 | RO | Div No 04-MASONRY | Solid Block | P01550 | List | Issued | TBA | 2026-03-04 |  |  |  | KAFD-636-SBC-CIV-MAR-00028 | Approved with Comments | GEN | Falwa | N | N | KSA | - | 2026-08-15 |  | Started | Shipped | Partially Delivered |  | PR.RO.D04.MTD.1040 | RO l MT Delivery for Masonary
217 | RO | Div No 04-MASONRY | Cladding & Skirting | Not Assigned | Not Assigned | Not Issued | TBA | TBA | [5 empty] | GEN | Fedras | N | N |  | - | 2026-10-16 |  | Not Started | Not Started | Not Started |  | PR.RO.D04.MTD.1040 | RO l MT Delivery for Masonary
218 | RO | Div No 05-METALS | Steel Structure | P01626 | - | Issued | 2026-07-09 | TBA |  |  |  | KAFD-636-SBC-CIV-MAR-00065 | Approved with Comments | LLI | LITCO | Y | N | UAE | - | 2026-10-10 | 2027-01-15 | Started | Not Started | Not Started |  | PR.RO.D05.MTD.1165 | RO l MT Delivery for Structural steel
219 | RO | Div No 05-METALS | Safety cage | P02045 | - | Issued | TBA | TBA | [5 empty] | GEN | LITCO | N | N | KSA | - | 2026-10-10 |  | Not Started | Not Started | Not Started |  | n/a | n/a
220 | RO | Div No 06-WOOD AND PLASTICS | Base cabinet L-shape | Not Assigned | Not Assigned | Not Issued | TBA | TBA | [5 empty] | GEN |  | N | N | KSA | - | 2027-01-24 |  | Not Started | Not Started | Not Started |  | N/a | N/a
221 | RO | Div No 07-THERMAL AND MOISTURE PROTECTION | Dalcobond ACP cladding | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00041 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1170 | RO l MT Delivery for Aluminium cladding
222 | RO | Div No 07-THERMAL AND MOISTURE PROTECTION | alumnium Perforated sheet - Anping | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00013 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | China | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
223 | RO | Div No 07-THERMAL AND MOISTURE PROTECTION | Waterproof | P01005 | - | Issued | 2026-04-06 | 2026-04-26 |  |  |  | KAFD-636-SBC-ARC-MAR-00018 KAFD-636-SBC-ARC-MAR-00019 KAFD-636-SBC-ARC-MAR-00020 KAFD-636-SBC-CIV-MAR-00025 KAFD-636-SBC-CIV-MAR-00033 KAFD-636-SBC-CIV-MAR-00092 KAFD-636-SBC-CIV-MAR-00101 | Approved with Comments | GEN | BMC | N | N | KSA | - | 2026-05-05 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
224 | RO | Div No 07-THERMAL AND MOISTURE PROTECTION | Roof Insulation | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00019 | Approved with Comments | GEN | BMC | N | N | KSA | - | 2026-05-05 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
225 | RO | Div No 08-OPENINGS | 085113 - Glass Internal WINDOWS | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00034 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | N/a | N/a
226 | RO | Div No 08-OPENINGS | 085113 - Glass External WINDOWS | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00042 | Under Review | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | N/a | N/a
227 | RO | Div No 08-OPENINGS | 085113 - ALUMINUM External WINDOWS | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00027 | Rejected | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | N/a | N/a
228 | RO | Div No 08-OPENINGS | 085113 - ALUMINUM Internal WINDOWS | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00030 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-11-25 |  | Not Started | Not Started | Not Started |  | N/a | N/a
229 | RO | Div No 13-SPECIAL CONSTRUCTION | Control Booth | P01868 | - | Issued | TBA | TBA | [5 empty] | GEN | NAJD | N | N | KSA | - | 2026-08-19 |  | Not Started | Not Started | Not Started |  | N/a | N/a
230 | RO | Div No 14-CONVEYING EQUIPMENT | Elevator | P01234 | - | Issued | 2026-09-02 | 46095 | 1 |  |  | KAFD-636-SBC-MEC-MAR-00024 | Approved with Comments | LLI | KONE | Y | N | China | Y | 2026-12-04 | 2027-01-27 | Started | Not Started | Not Started |  | PR.RO.D14.MTD.1180 | RO l MT Delivery for Elevators
231 | RO | Div No 31-EARTHWORK | Piling & Shoring Works | P00811 | - | Issued | 2025-12-23 | 2026-02-08 | [5 empty] | GEN | IKK | N | N | KSA | - | 2026-01-17 |  | Ready | Shipped | Delivered | - | N/a | N/a
232 | IPS | Div No 31-EARTHWORK | Piling & Shoring Works | P00811 | - | Issued | 2025-12-23 | 2026-02-08 | [5 empty] | GEN | IKK | N | N | KSA | - | 2026-01-17 |  | Not Started | Not Started | Not Started | - | PR.PS.D31.MTD.1005 | IPS l MT Delivery for Reinforced piles
233 | RO | Div No 32-EXTERIOR IMPROVEMENTS | Hardscape | P02195 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-LAN-MAR-00002 | Approved with Comments | GEN | Al Sraif | N | N | KSA | - | 2026-11-15 | 2026-11-01 | Started | Not Started | Not Started |  | PR.RO.D32.MTD.1155 | RO l MT Delivery for Precast concrete paving
234 | IPS | Div No 32-EXTERIOR IMPROVEMENTS | Hardscape | P02195 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-LAN-MAR-00002 | Approved with Comments | GEN | Al Sraif | N | N | KSA | - | 2026-11-15 | 2026-11-01 | Started | Not Started | Not Started |  | PR.PS.D32.MTD.1070 | IPS l MT Delivery for concrete paving
235 | RO | Div No 07-THERMAL AND MOISTURE PROTECTION | Roof Tiles | P02195 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-LAN-MAR-00002 | Approved with Comments | GEN | Al Sraif | N | N | KSA | - | 2026-11-15 | 2026-11-01 | Ready | Shipped | Delivered |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
236 | IPS | Div No 07-THERMAL AND MOISTURE PROTECTION | Roof Tiles | P02195 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-LAN-MAR-00002 | Approved with Comments | GEN | Al Sraif | N | N | KSA | - | 2026-11-15 | 2026-11-01 | Ready | Shipped | Delivered |  | PR.PS.D07.MTD.1025 | IPS l MT Delivery for Terrazzo Tiles
237 | IPS | Div No 03-CONCRETE | C32 MPA Concrete | P01550 | List | Issued | TBA | 2026-03-04 |  | Approved with Comments |  | KAFD-636-SBC-CIV-MAR-00089 | Approved with Comments | GEN | Green Concrete | N | N | KSA | - | 2026-06-03 |  | Not Started | Not Started | Not Started |  | N/a | N/a
238 | IPS | Div No 04-MASONRY | Solid Block | P01550 | List | Issued | TBA | 2026-03-04 |  | Approved with Comments |  | KAFD-636-SBC-CIV-MAR-00028 | Approved with Comments | GEN | Falwa | N | N | KSA | - | 2026-07-13 |  | Not Started | Not Started | Not Started |  | PR.PS.D04.MTD.1010 | IPS l MT Delivery for Masonry
239 | RO | Div No 08-OPENINGS | Support System for ACP and Louvers | P01679 | - | Issued | TBA | TBA | [5 empty] | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-08-30 |  | Not Started | Not Started | Not Started |  | N/a | N/a
240 | RO | Div No 08-OPENINGS | SAFID - Fixed Louver | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00039 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-08-30 |  | Not Started | Not Started | Not Started |  | N/a | N/a
241 | RO | Div No 08-OPENINGS | SAFID - Sand Trap Louver | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00040 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-08-30 |  | Not Started | Not Started | Not Started |  | N/a | N/a
242 | RO | Div No 08-OPENINGS | Skylight | P01679 | - | Issued | TBA | TBA | [5 empty] | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - |  |  | Not Started | Not Started | Not Started |  | N/a | N/a
243 | IPS | Div No 07-THERMAL AND MOISTURE PROTECTION | Support System for Aluminum tubes | P01679 | - | Issued | TBA | TBA | [5 empty] | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-08-07 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
244 | IPS | Div No 07-THERMAL AND MOISTURE PROTECTION | Aluminum tubes | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00047 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | - | 2026-08-07 |  | Not Started | Not Started | Not Started |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
245 | IPS | Div No 07-THERMAL AND MOISTURE PROTECTION | Waterproof | P01005 | - | Issued | 2026-04-06 | 2026-04-26 |  |  |  | KAFD-636-SBC-ARC-MAR-00018 KAFD-636-SBC-ARC-MAR-00019 KAFD-636-SBC-ARC-MAR-00020 KAFD-636-SBC-CIV-MAR-00025 KAFD-636-SBC-CIV-MAR-00033 KAFD-636-SBC-CIV-MAR-00092 KAFD-636-SBC-CIV-MAR-00101 | Approved with Comments | GEN | BMC | N | N | KSA | - | 2026-05-06 |  | Ready | Shipped | Partially Delivered |  | PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation
246 | IPS | Div No 07-THERMAL AND MOISTURE PROTECTION | Roof Insulation | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00019 | Approved with Comments | GEN | BMC | N | N | KSA | - | 2026-05-06 |  | Not Started | Not Started | Not Started |  | PR.PS.D07.MTD.1000 | IPS l MT Delivery for Thermal & Moisture insulation
247 | IPS | Div No 08-OPENINGS | 089119 - FIXED LOUVERS | P01679 | - | Issued | TBA | TBA |  |  |  | KAFD-636-SBC-ARC-MAR-00028 | Approved with Comments | GEN | SEDRA INDUSTRY FACTORY | N | N | KSA | Y | 2026-08-30 |  | Not Started | Not Started | Not Started |  | PR.PS.D08.MTD.1030 | IPS l MT Delivery for Aluminium louvers
248 | IPS | Div No 13-SPECIAL CONSTRUCTION | Control Booth | P01868 | - | Issued | TBA | TBA | [5 empty] | GEN | NAJD | N | N | KSA | - | 2026-08-19 |  | Not Started | Not Started | Not Started |  | PR.PS.D13.MTD.1035 | IPS l MT Delivery for Aluminium Control booths
249 | IPS | Div No 31-EARTHWORK | Piling & Shoring Works | P00811 | - | Issued | 2025-12-23 | 2026-02-08 | [5 empty] | GEN | IKK | N | N | KSA | - | 2026-04-21 | - | Ready | Not Started | - | - | PR.RO.D31.MTD.1035 | RO l MT Delivery for Concrete Piles & prestressed anchors
250 | RO | Div No 04-MASONRY | Exterior Stone Cladding | Not Assigned | - | Not Issued | [7 empty] | GEN | Tile to Tile | N |  | KSA |  |  |  | Not Started | Not Started | Not Started |  | PR.RO.D04.MTD.1045 | RO l MT Delivery for Stone cladding
251 | IPS | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Ready | Shipped | Delivered | - | PR.PS.D07.MTD.1020 | IPS l MT Delivery for Aluminum cladding
252 | IPS | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Ready | Shipped | Delivered | - | PR.PS.D22.MTD.1045 | IPS l MT Delivery for Domestic Water Piping GRP

## Sheet2
SR | Pump No. | FAT Status
1 | SP- 4.11.1 | Approved
2 | SP-4.11.2 | Approved
3 | SP-2.15
4 | SP-2.09 | Approved
5 | SP-1.11 | Approved
6 | SP-5.06
7 | SP-3.1 | Approved
8 | SP-5.03
9 | SP-01
10 | Vertical Turbine

## Sheet1 (hidden)
PO Issuance | Fabrication / Material Readiness | Shipping | Delivery
Issued | Started | Shipped | Delivered
Not Issued | Ready | Not Started | Partially Delivered
| Not Started |  | Not Started