## Sheet1
Activity ID | Activity Name | Original Duration | Weightage | BL Start | BL Finish | Plan % DD | SBCM Prev Actual | Weekly % | SBCM Actual Progress | Saudi consultant Progress | Justification from SBCM | Comment from the Consultant
100
KAFD00330 ¦ 6.36 ¦ SBC ¦ Revised Baseline-R00 |  | 547 |  | 2025-10-01 | 2027-03-31 | 23.42% | 45.97% | 0.939% | 46.91%
Project Milestones |  | 547 |  | 2025-10-01 | 2027-03-31
Key Milestone |  | 547 |  | 2025-10-01 | 2027-03-31
MS.COM.GEN.1000 | Commencement date | 0 |  | 2025-10-01
MS.COM.GEN.1005 | Project Completion | 0 |  |  | 2027-03-31
Control Milestone |  | 229 |  | 2026-07-28 | 2027-03-14
MS.COM.GEN.1015 | Completion of Shop Drawings | 0 |  |  | 2026-07-28
MS.COM.GEN.1045 | Completion of Material Delivery | 0 |  |  | 2026-12-24
MS.COM.GEN.1030 | Completion of Intermediate Pump Station Construction Works | 0 |  |  | 2026-12-26
MS.COM.GEN.1035 | Completion of Collection system Construction Works | 0 |  |  | 2027-01-19
MS.COM.GEN.1025 | Completion of Mobilization Works | 0 |  |  | 2027-02-11
MS.COM.GEN.1040 | Completion of RO Plaint Construction Works | 0 |  |  | 2027-03-14
General (Preliminaries and Mobilization) |  | 547 |  | 2025-10-01 | 2027-03-31 | 13.37% | 55.14% | 0.7434% | 55.88%
Mobilization Works |  | 89 |  | 2026-11-01 | 2027-02-11
MO.GEN.D01.1015 | Site Offices Furnitures | 12 | 1.2252 | 2026-11-01 | 2026-11-14 | 0% | 14.01% | 0% | 14.01%
MO.GEN.D01.1005 | Site Access, Routes & Directive Signage | 10 | 0.032128 | 2026-11-15 | 2026-11-25 | 0% | 41.64% | 0% | 41.64%
MO.GEN.D01.1030 | Temporary Facilities and Devices for Offices | 20 | 1.2772 | 2026-11-15 | 2026-12-07 | 0% | 6.97% | 0% | 6.97%
MO.GEN.D01.1006 | Waste Disposal & Enviremental Protection | 15 | 0.58045 | 2026-11-26 | 2026-12-13 | 0% | 46.02% | 0% | 46.02%
MO.GEN.D01.1011 | Temporary Utilities Installation | 25 | 0.32663 | 2026-12-08 | 2027-01-05 | 0% | 12% | 0% | 12%
MO.GEN.D01.1007 | Administrative Site Offices and Facilities | 30 | 1.0597 | 2026-12-14 | 2027-01-17 | 0% | 12% | 0% | 12%
MO.GEN.D01.1008 | Site Laboratory | 12 | 0.23293 | 2027-01-18 | 2027-01-31 | 0% | 15% | 0% | 15%
MO.GEN.D01.1009 | Temporary roads and Signs | 10 | 0.3427 | 2027-02-01 | 2027-02-11 | 0% | 46.02% | 0% | 46.02%
General Requirements |  | 547 |  | 2025-10-01 | 2027-03-31
GN.GEN.D01.1020 | Performance Security | 15 | 0.6024 | 2026-02-09 | 2026-02-23 | 0% | 100% | 0% | 100%
GN.GEN.D01.1025 | Advance Payment Security | 20 | 0.6024 | 2026-02-24 | 2026-03-15 | 0% | 100% | 0% | 100%
GN.GEN.D01.1010 | Preliminaries for contractors and administrative works | 547 | 8.7013 | 2025-10-01 | 2027-03-31 | 23.03% | 70.75% | 1.28% | 72.03%
Engineering |  | 301 |  | 2025-10-01 | 2026-07-28 | 45.05% | 95.54% | 0.1624% | 95.71%
RO Plant |  | 294 |  | 2025-10-01 | 2026-07-21
RO Plant Shop Drawing Submittal |  | 228 |  | 2025-10-01 | 2026-07-01
Earthworks Shop Drawing Submittal |  | 60 |  | 2025-10-01 | 2025-12-09
EN.RO.D31.SDS.1215 | RO l Submission of Excavation Works shop drawing | 20 | 0.042352 | 2025-10-01 | 2025-10-23 | 100% | 100% | 0% | 100%
EN.RO.D31.SDS.1220 | RO l Submission of Concrete Piles shop drawing | 20 | 0.10857 | 2025-10-25 | 2025-11-16 | 100% | 100% | 0% | 100%
EN.RO.D31.SDS.1225 | RO l Submission of Prestressed anchors shop drawing | 20 | 0.012393 | 2025-11-17 | 2025-12-09 | 100% | 100% | 0% | 100%
Concrete Shop Drawing Submittal |  | 122 |  | 2025-12-10 | 2026-05-05
EN.RO.D03.SDS.1000 | RO l Submission of Raft Foundation shop drawing | 12 | 0.11607 | 2025-12-10 | 2025-12-23 | 100% | 100% | 0% | 100%
EN.RO.D03.SDS.1005 | RO l Submission of Tank walls shop drawing | 18 | 0.41079 | 2025-12-24 | 2026-01-13 | 100% | 100% | 0% | 100%
EN.RO.D03.SDS.1050 | RO l Submission of Tank slab shop drawing | 8 | 0.061766 | 2026-01-14 | 2026-01-22 | 100% | 100% | 0% | 100%
EN.RO.D03.SDS.1010 | RO l Submission of Columns shop drawing Gf | 6 | 0.0041985 | 2026-01-24 | 2026-01-29 | 100% | 100% | 0% | 100%
EN.RO.D03.SDS.1030 | RO l Submission of Concrete Slab shop drawing GF | 8 | 0.022795 | 2026-01-31 | 2026-02-08 | 37.5% | 100% | 0% | 100%
EN.RO.D03.SDS.1015 | RO l Submission of Columns shop drawing 1st | 6 | 0.0020992 | 2026-02-09 | 2026-02-15 | 0% | 100% | 0% | 100%
EN.RO.D03.SDS.1035 | RO l Submission of Concrete Slab shop drawing 1st | 8 | 0.011398 | 2026-02-16 | 2026-02-25 | 0% | 100% | 0% | 100%
EN.RO.D03.SDS.1025 | RO l Submission of Slab on grade shop drawing | 10 | 0.010465 | 2026-02-16 | 2026-02-28 | 0% | 100% | 0% | 100%
EN.RO.D03.SDS.1020 | RO l Submission of Columns shop drawing 2nd | 6 | 0.0020992 | 2026-02-26 | 2026-03-04 | 0% | 100% | 0% | 100%
EN.RO.D03.SDS.1040 | RO l Submission of Concrete Slab shop drawing 2nd | 18 | 0.011398 | 2026-03-05 | 2026-03-29 | 0% | 100% | 0% | 100%
EN.RO.D03.SDS.1045 | RO l Submission of Floor & Roof screed shop drawing | 18 | 0.005146 | 2026-04-15 | 2026-05-05 | 0% | 100% | 0% | 100%
Masonry Shop Drawing Submittal |  | 21 |  | 2026-02-09 | 2026-03-05
EN.RO.D04.SDS.1055 | RO l Submission of Masonary works shop drawing | 14 | 0.0086286 | 2026-02-09 | 2026-02-25 | 0% | 100% | 0% | 100%
EN.RO.D04.SDS.1060 | RO l Submission of Stone cladding shop drawing | 7 | 0.0097312 | 2026-02-26 | 2026-03-05 | 0% | 100% | 0% | 100%
Metal Shop Drawing Submittal |  | 14 |  | 2026-03-30 | 2026-04-14
EN.RO.D05.SDS.1065 | RO l Submission of Structural steel works | 14 | 0.019281 | 2026-03-30 | 2026-04-14 | 0% | 100% | 0% | 100%
Thermal Protection Shop Drawing Submittal |  | 38 |  | 2026-03-17 | 2026-05-03
EN.RO.D07.SDS.1080 | RO l Submission of Concrete tiles shop drawing | 16 | 0.0036254 | 2026-03-17 | 2026-04-07 | 0% | 100% | 0% | 100%
EN.RO.D07.SDS.1070 | RO l Submission of Aluminium panels cladding shop drawing | 12 | 0.017122 | 2026-04-15 | 2026-04-28 | 0% | 100% | 0% | 100%
EN.RO.D07.SDS.1075 | RO l Submission of Canopy aluminium cladding shop drawing | 16 | 0.0164 | 2026-04-15 | 2026-05-03 | 0% | 100% | 0% | 100%
Openings Shop Drawing Submittal |  | 12 |  | 2026-03-17 | 2026-04-02
EN.RO.D08.SDS.1085 | RO l Submission of Steel doors shop drawing | 12 | 0.011338 | 2026-03-17 | 2026-04-02 | 0% | 100% | 0% | 100%
EN.RO.D08.SDS.1090 | RO l Submission of Aluminum windows & Louvers shop drawing | 12 | 0.0021772 | 2026-03-17 | 2026-04-02 | 0% | 100% | 0% | 100%
Finishes Shop Drawing Submittal |  | 30 |  | 2026-02-09 | 2026-03-16
EN.RO.D09.SDS.1095 | RO l Submission of Gypsum board Works shop drawing | 16 | 0.0086832 | 2026-02-09 | 2026-02-28 | 0% | 100% | 0% | 100%
EN.RO.D09.SDS.1100 | RO l Submission of Floor Works shop drawing | 16 | 0.0050601 | 2026-02-26 | 2026-03-16 | 0% | 100% | 0% | 100%
Elevator Shop Drawing Submittal |  | 10 |  | 2026-04-21 | 2026-05-02
EN.RO.D14.SDS.1105 | RO l Submission of Elevators shop drawing | 10 | 0.0038902 | 2026-04-21 | 2026-05-02 | 0% | 100% | 0% | 100%
Fire Supperssion Shop Drawing Submittal |  | 64 |  | 2026-03-01 | 2026-05-17
EN.RO.D21.SDS.1115 | RO l Submission of Fire Suppression shop drawing GF | 10 | 0.021659 | 2026-03-01 | 2026-03-11 | 0% | 100% | 0% | 100%
EN.RO.D21.SDS.1120 | RO l Submission of Fire Suppression shop drawing 1st | 10 | 0.010829 | 2026-03-12 | 2026-03-26 | 0% | 100% | 0% | 100%
EN.RO.D21.SDS.1125 | RO l Submission of Fire Suppression shop drawing 2nd | 10 | 0.010829 | 2026-03-28 | 2026-04-07 | 0% | 100% | 0% | 100%
EN.RO.D21.SDS.1110 | RO l Submission of Fire Suppression for Pump room shop drawing | 10 | 0.026081 | 2026-05-06 | 2026-05-17 | 0% | 100% | 0% | 100%
Plumbing Shop Drawing Submittal |  | 39 |  | 2026-03-01 | 2026-04-18
EN.RO.D22.SDS.1145 | RO l Submission of Sanitary Pipes shop drawing | 12 | 0.0022254 | 2026-03-01 | 2026-03-14 | 0% | 100% | 0% | 100%
EN.RO.D22.SDS.1135 | RO l Submission of Domestic water piping shop drawing | 10 | 0.0045461 | 2026-03-15 | 2026-03-29 | 0% | 100% | 0% | 100%
EN.RO.D22.SDS.1140 | RO l Submission of Plumbing Valves shop drawing | 7 | 0.0098345 | 2026-03-30 | 2026-04-06 | 0% | 100% | 0% | 100%
EN.RO.D22.SDS.1130 | RO l Submission of Vibration & Seismic controls For Plumbingshop drawing | 10 | 0.02599 | 2026-04-07 | 2026-04-18 | 0% | 100% | 0% | 100%
HVAC System Shop Drawing Submittal |  | 36 |  | 2026-02-26 | 2026-04-12
EN.RO.D23.SDS.1150 | RO l Submission of HVAC System shop drawing GF | 12 | 0.042627 | 2026-02-26 | 2026-03-11 | 0% | 100% | 0% | 100%
EN.RO.D23.SDS.1155 | RO l Submission of HVAC System shop drawing 1st | 12 | 0.021313 | 2026-03-12 | 2026-03-29 | 0% | 100% | 0% | 100%
EN.RO.D23.SDS.1160 | RO l Submission of HVAC System shop drawing 2nd | 12 | 0.021313 | 2026-03-30 | 2026-04-12 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Submittal |  | 43 |  | 2026-02-26 | 2026-04-20
EN.RO.D26.SDS.1190 | RO l Submission of lighting system shop drawing | 9 | 0.017399 | 2026-02-26 | 2026-03-08 | 0% | 100% | 0% | 100%
EN.RO.D26.SDS.1175 | RO l Submission of Lightning & Earthing shop drawing | 6 | 0.0052247 | 2026-03-09 | 2026-03-15 | 0% | 100% | 0% | 100%
EN.RO.D26.SDS.1180 | RO l Submission of Power system shop drawing | 6 | 0.0016278 | 2026-03-16 | 2026-03-25 | 0% | 100% | 0% | 100%
EN.RO.D26.SDS.1185 | RO l Submission of Cable routing shop drawing | 12 | 0.056985 | 2026-03-26 | 2026-04-08 | 0% | 100% | 0% | 100%
EN.RO.D26.SDS.1165 | RO l Submission of Panel board shop drawing | 10 | 0.014973 | 2026-04-09 | 2026-04-20 | 0% | 100% | 0% | 100%
EN.RO.D26.SDS.1170 | RO l Submission of UPS System shop drawing | 10 | 0.0081067 | 2026-04-09 | 2026-04-20 | 0% | 100% | 0% | 100%
Low Current Shop Drawing Submittal |  | 12 |  | 2026-04-09 | 2026-04-22
EN.RO.D27.SDS.1195 | RO l Submission of Communication System shop drawing | 12 | 0.025573 | 2026-04-09 | 2026-04-22 | 0% | 100% | 0% | 100%
Security Shop Drawing Submittal |  | 42 |  | 2026-04-23 | 2026-06-14
EN.RO.D28.SDS.1205 | RO l Submission of CCTV system shop drawing | 14 | 0.0071121 | 2026-04-23 | 2026-05-09 | 0% | 100% | 0% | 100%
EN.RO.D28.SDS.1210 | RO l Submission of Fire alarm system shop drawing | 14 | 0.0040878 | 2026-05-10 | 2026-05-25 | 0% | 100% | 0% | 100%
EN.RO.D28.SDS.1200 | RO l Submission of Access control shop drawing | 14 | 0.0043308 | 2026-05-30 | 2026-06-14 | 0% | 100% | 0% | 100%
Exterior Improvement Shop Drawing Submittal |  | 18 |  | 2026-03-30 | 2026-04-19
EN.RO.D32.SDS.1230 | RO l Submission of Precast concrete shop drawing | 18 | 0.014154 | 2026-03-30 | 2026-04-19 | 0% | 50% | 0% | 50% |  | subject to approval of calculations from KAFD
Special System Shop Drawing Submittal |  | 50 |  | 2026-03-26 | 2026-05-23
EN.RO.D33.SDS.1235 | RO l Submission of (BWRO) Plant shop drawing | 50 | 0.25771 | 2026-03-26 | 2026-05-23 | 0% | 100% | 0% | 100%
SCADA Shop Drawing Submittal |  | 15 |  | 2026-06-15 | 2026-07-01
EN.RO.D40.SDS.1240 | RO l Submission of SCDA system shop drawing | 15 | 0.025122 | 2026-06-15 | 2026-07-01 | 100% | 50% | 0% | 50% |  | Submitted
RO Plant Shop Drawing Approval |  | 186 |  | 2025-10-26 | 2026-07-21
Concrete Shop Drawing Approval |  | 105 |  | 2025-12-24 | 2026-05-25
EN.RO.D03.SDA.1000 | RO l Approval of Raft Foundation shop drawing | 14 | 0.11607 | 2025-12-24 | 2026-01-12 | 100% | 100% | 0% | 100%
EN.RO.D03.SDA.1005 | RO l Approval of Tank walls shop drawing | 14 | 0.41079 | 2026-01-14 | 2026-02-02 | 100% | 100% | 0% | 100%
EN.RO.D03.SDA.1050 | RO l Approval of Tank slab shop drawing | 14 | 0.061766 | 2026-01-25 | 2026-02-11 | 57.14% | 100% | 0% | 100%
EN.RO.D03.SDA.1010 | RO l Approval of Columns shop drawing Gf | 14 | 0.0041985 | 2026-02-09 | 2026-03-01 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1030 | RO l Approval of Concrete Slab shop drawing GF | 14 | 0.022795 | 2026-02-09 | 2026-03-01 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1015 | RO l Approval of Columns shop drawing 1st | 14 | 0.0020992 | 2026-02-16 | 2026-03-08 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1035 | RO l Approval of Concrete Slab shop drawing 1st | 14 | 0.011398 | 2026-02-26 | 2026-03-17 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1025 | RO l Approval of Slab on grade shop drawing | 14 | 0.010465 | 2026-03-01 | 2026-03-18 | 100% | 80% | 0% | 80% |  | Drawings rejected, Veolia P&ID approval is pre-requisite
EN.RO.D03.SDA.1020 | RO l Approval of Columns shop drawing 2nd | 14 | 0.0020992 | 2026-03-05 | 2026-03-29 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1040 | RO l Approval of Concrete Slab shop drawing 2nd | 14 | 0.011398 | 2026-03-30 | 2026-04-16 | 0% | 100% | 0% | 100%
EN.RO.D03.SDA.1045 | RO l Approval of Floor & Roof screed shop drawing | 14 | 0.005146 | 2026-05-06 | 2026-05-25 | 0% | 100% | 0% | 100% |  | Approved
Masonry Shop Drawing Approval |  | 20 |  | 2026-02-26 | 2026-03-30
EN.RO.D04.SDA.1055 | RO l Approval of Masonary works shop drawing | 14 | 0.0086286 | 2026-02-26 | 2026-03-17 | 0% | 100% | 0% | 100%
EN.RO.D04.SDA.1060 | RO l Approval of Stone cladding shop drawing | 14 | 0.0097312 | 2026-03-08 | 2026-03-30 | 0% | 50% | 0% | 50% |  | Drawings rejected, pending MAR approval for cladding tiles and fixing system
Metal Shop Drawing Approval |  | 14 |  | 2026-04-15 | 2026-05-04
EN.RO.D05.SDA.1065 | RO l Approval of Structural steel works | 14 | 0.019281 | 2026-04-15 | 2026-05-04 | 0% | 100% | 0% | 100% |  | Approved
Thermal Protection Shop Drawing Submittal |  | 32 |  | 2026-04-08 | 2026-05-21
EN.RO.D07.SDA.1080 | RO l Approval of Concrete tiles shop drawing | 14 | 0.0036254 | 2026-04-08 | 2026-04-27 | 0% | 100% | 0% | 100%
EN.RO.D07.SDA.1070 | RO l Approval of Aluminium panels cladding shop drawing | 14 | 0.017122 | 2026-04-29 | 2026-05-18 | 100% | 80% | 0% | 80% |  | subject to approval of calculations from KAFD
EN.RO.D07.SDA.1075 | RO l Approval of Canopy aluminium cladding shop drawing | 14 | 0.0164 | 2026-05-04 | 2026-05-21 | 100% | 50% | 30% | 80% |  | Drawings rejected, subject to approval of calculations from KAFD
Openings Shop Drawing Approval |  | 14 |  | 2026-04-05 | 2026-04-22
EN.RO.D08.SDA.1085 | RO l Approval of Steel doors shop drawing | 14 | 0.011338 | 2026-04-05 | 2026-04-22 | 0% | 100% | 0% | 100%
EN.RO.D08.SDA.1090 | RO l Approval of Aluminum windows & Louvers shop drawing | 14 | 0.0021772 | 2026-04-05 | 2026-04-22 | 35.71% | 0% | 50% | 50% |  | Drawings rejected, MAR Approval is pre-requisite
Finishes Shop Drawing Approval |  | 26 |  | 2026-03-01 | 2026-04-08
EN.RO.D09.SDA.1095 | RO l Approval of Gypsum board Works shop drawing | 14 | 0.0086832 | 2026-03-01 | 2026-03-18 | 100% | 80% | 0% | 80% |  | Approved | Remaining frame Shop DWG
EN.RO.D09.SDA.1100 | RO l Approval of Floor Works shop drawing | 14 | 0.0050601 | 2026-03-17 | 2026-04-08 | 0% | 100% | 0% | 100%
Elevator Shop Drawing Approval |  | 14 |  | 2026-05-03 | 2026-05-20
EN.RO.D14.SDA.1105 | RO l Approval of Elevators shop drawing | 14 | 0.0038902 | 2026-05-03 | 2026-05-20 | 0% | 100% | 0% | 100%
Fire Supperssion Shop Drawing Approval |  | 58 |  | 2026-03-12 | 2026-06-09
EN.RO.D21.SDA.1115 | RO l Approval of Fire Suppression shop drawing GF | 14 | 0.010829 | 2026-03-12 | 2026-04-05 | 0% | 100% | 0% | 100%
EN.RO.D21.SDA.1120 | RO l Approval of Fire Suppression shop drawing 1st | 14 | 0.010829 | 2026-03-29 | 2026-04-15 | 0% | 100% | 0% | 100%
EN.RO.D21.SDA.1125 | RO l Approval of Fire Suppression shop drawing 2nd | 14 | 0.021659 | 2026-04-08 | 2026-04-27 | 0% | 100% | 0% | 100%
EN.RO.D21.SDA.1110 | RO l Approval of Fire Suppression for Pump room shop drawing | 14 | 0.026081 | 2026-05-18 | 2026-06-09 | 0% | 100% | 0% | 100%
Plumbing Shop Drawing Approval |  | 36 |  | 2026-03-15 | 2026-05-06
EN.RO.D22.SDA.1145 | RO l Approval of Sanitary Pipes shop drawing | 14 | 0.0022254 | 2026-03-15 | 2026-04-06 | 0% | 100% | 0% | 100%
EN.RO.D22.SDA.1135 | RO l Approval of Domestic water piping shop drawing | 14 | 0.0045461 | 2026-03-30 | 2026-04-16 | 0% | 100% | 0% | 100%
EN.RO.D22.SDA.1140 | RO l Approval of Plumbing Valves shop drawing | 14 | 0.0098345 | 2026-04-07 | 2026-04-26 | 0% | 100% | 0% | 100%
EN.RO.D22.SDA.1130 | RO l Approval of Vibration & Seismic controls For Plumbingshop drawing | 14 | 0.02599 | 2026-04-19 | 2026-05-06 | 0% | 100% | 0% | 100%
HVAC System Shop Drawing Approval |  | 33 |  | 2026-03-12 | 2026-04-30
EN.RO.D23.SDA.1150 | RO l Approval of HVAC System shop drawing GF | 14 | 0.042627 | 2026-03-12 | 2026-04-05 | 0% | 100% | 0% | 100%
EN.RO.D23.SDA.1155 | RO l Approval of HVAC System shop drawing 1st | 14 | 0.021313 | 2026-03-30 | 2026-04-16 | 0% | 100% | 0% | 100%
EN.RO.D23.SDA.1160 | RO l Approval of HVAC System shop drawing 2nd | 14 | 0.021313 | 2026-04-13 | 2026-04-30 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Approval |  | 42 |  | 2026-03-09 | 2026-05-10
EN.RO.D26.SDA.1190 | RO l Approval of lighting system shop drawing | 14 | 0.017399 | 2026-03-09 | 2026-03-31 | 0% | 100% | 0% | 100%
EN.RO.D26.SDA.1175 | RO l Approval of Lightning & Earthing shop drawing | 14 | 0.0052247 | 2026-03-16 | 2026-04-07 | 0% | 100% | 0% | 100%
EN.RO.D26.SDA.1180 | RO l Approval of Power system shop drawing | 14 | 0.0016278 | 2026-03-26 | 2026-04-14 | 0% | 100% | 0% | 100%
EN.RO.D26.SDA.1185 | RO l Approval of Cable routing shop drawing | 14 | 0.056985 | 2026-04-09 | 2026-04-28 | 0% | 100% | 0% | 100%
EN.RO.D26.SDA.1165 | RO l Approval of Panel board shop drawing | 14 | 0.014973 | 2026-04-21 | 2026-05-10 | 100% | 80% | 0% | 80% |  | remaining SLD only, rejected, the submission after input from supplier
EN.RO.D26.SDA.1170 | RO l Approval of UPS System shop drawing | 14 | 0.0081067 | 2026-04-21 | 2026-05-10 | 0% | 100% | 0% | 100%
Low Current Shop Drawing Approval |  | 14 |  | 2026-04-23 | 2026-05-12
EN.RO.D27.SDA.1195 | RO l Approval of Communication System shop drawing | 14 | 0.025573 | 2026-04-23 | 2026-05-12 | 100% | 70% | 0% | 70% |  | Under Review
Security Shop Drawing Approval |  | 37 |  | 2026-05-10 | 2026-07-02
EN.RO.D28.SDA.1205 | RO l Approval of CCTV system shop drawing | 14 | 0.0071121 | 2026-05-10 | 2026-06-01 | 0% | 0% | 0% | 0% |  | pending confirmation from KAFD
EN.RO.D28.SDA.1210 | RO l Approval of Fire alarm system shop drawing | 14 | 0.0040878 | 2026-05-31 | 2026-06-17 | 0% | 100% | 0% | 100%
EN.RO.D28.SDA.1200 | RO l Approval of Access control shop drawing | 14 | 0.0043308 | 2026-06-15 | 2026-07-02 | 0% | 0% | 0% | 0% |  | pending confirmation from KAFD
Earthworks Shop Drawing Approval |  | 47 |  | 2025-10-26 | 2025-12-29
EN.RO.D31.SDA.1215 | RO l Approval of Excavation Works shop drawing | 14 | 0.042352 | 2025-10-26 | 2025-11-12 | 100% | 100% | 0% | 100%
EN.RO.D31.SDA.1220 | RO l Approval of Concrete Piles shop drawing | 14 | 0.10857 | 2025-11-17 | 2025-12-04 | 100% | 100% | 0% | 100%
EN.RO.D31.SDA.1225 | RO l Approval of Prestressed anchors shop drawing | 14 | 0.012393 | 2025-12-10 | 2025-12-29 | 100% | 100% | 0% | 100%
Exterior Improvement Shop Drawing Approval |  | 14 |  | 2026-04-20 | 2026-05-07
EN.RO.D32.SDA.1230 | RO l Approval of Precast concrete shop drawing | 14 | 0.014154 | 2026-04-20 | 2026-05-07 | 0% | 50% | 0% | 50% |  | subject to approval of calculations from KAFD
Special System Shop Drawing Approval |  | 14 |  | 2026-05-24 | 2026-06-15
EN.RO.D33.SDA.1235 | RO l Approval of (BWRO) Plant shop drawing | 14 | 0.25771 | 2026-05-24 | 2026-06-15 | 0% | 80% | 0% | 80%
SCADA Shop Drawing Approval |  | 14 |  | 2026-07-02 | 2026-07-21
EN.RO.D40.SDA.1240 | RO l Approval of SCDA system shop drawing | 14 | 0.025122 | 2026-07-02 | 2026-07-21 | 100% | 20% | 0% | 20% |  | Drawings rejected,Veolia P&ID approval is pre-requisite
Pump-Station |  | 257 |  | 2025-10-25 | 2026-07-08
Pump-Station Technical Submittal |  | 40 |  | 2025-10-25 | 2025-12-03
Pump-Station Technical Submittal |  | 18 |  | 2025-10-25 | 2025-11-13
EN.PS.D02.SDS.1000 | IPS l Submission of Soil Investigations Technical Report | 18 | 0.00026424 | 2025-10-25 | 2025-11-13 | 100% | 100% | 0% | 100%
Pump-Station Technical Approval |  | 14 |  | 2025-11-16 | 2025-12-03
EN.PS.D02.SDA.1000 | IPS l Approval of Soil Investigations Technical Report | 14 | 0.00026424 | 2025-11-16 | 2025-12-03 | 100% | 100% | 0% | 100%
Pump-Station Shop Drawing |  | 217 |  | 2025-12-04 | 2026-07-08
Pump-Station Shop Drawing Submittal |  | 162 |  | 2025-12-04 | 2026-06-18
Concrete Shop Drawing Submittal |  | 16 |  | 2025-12-28 | 2026-01-14
EN.PS.D03.SDS.1010 | IPS l Submission of Concrete Works Shop drawing | 16 | 0.0052672 | 2025-12-28 | 2026-01-14 | 100% | 100% | 0% | 100%
Masonry Shop Drawing Submittal |  | 15 |  | 2026-01-15 | 2026-02-01
EN.PS.D04.SDS.1015 | IPS l Submission of Masonry works Shop drawing | 15 | 0.00036389 | 2026-01-15 | 2026-02-01 | 100% | 100% | 0% | 100%
Metal Shop Drawing Submittal |  | 12 |  | 2026-03-03 | 2026-03-16
EN.PS.D05.SDS.1020 | IPS l Submission of Trench covers Shop drawing | 12 | 0.0010526 | 2026-03-03 | 2026-03-16 | 100% | 100% | 0% | 100%
Thermal Protection Shop Drawing Submittal |  | 12 |  | 2026-02-16 | 2026-03-02
EN.PS.D07.SDS.1025 | IPS l Submission of Aluminum cladding Shop drawing | 12 | 0.0014132 | 2026-02-16 | 2026-03-02 | 0% | 100% | 0% | 100% |  | Under Review
Openings Shop Drawing Submittal |  | 12 |  | 2026-02-02 | 2026-02-15
EN.PS.D08.SDS.1030 | IPS l Submission of Steel doors Shop drawing | 12 | 0.00027686 | 2026-02-02 | 2026-02-15 | 16.67% | 100% | 0% | 100%
EN.PS.D08.SDS.1035 | IPS l Submission of Aluminium louvers Shop drawing | 12 | 0.00023857 | 2026-02-02 | 2026-02-15 | 16.67% | 100% | 0% | 100%
Special construction Shop Drawing Submittal |  | 10 |  | 2026-03-03 | 2026-03-14
EN.PS.D13.SDS.1040 | IPS l Submission of Aluminium Control booths Shop drawing | 10 | 0.00034204 | 2026-03-03 | 2026-03-14 | 100% | 100% | 0% | 100%
Fire Supperssion Shop Drawing Submittal |  | 15 |  | 2026-03-08 | 2026-03-28
EN.PS.D21.SDS.1045 | IPS l Submission of Fire Suppression Shop drawing | 15 | 0.0030517 | 2026-03-08 | 2026-03-28 | 0% | 100% | 0% | 100%
Plumbing Shop Drawing Submittal |  | 46 |  | 2026-02-02 | 2026-03-31
EN.PS.D22.SDS.1050 | IPS l Submission of Electrical room plumbing Shop drawing | 10 | 0.00016589 | 2026-02-02 | 2026-02-12 | 20% | 100% | 0% | 100%
EN.PS.D22.SDS.1060 | IPS l Submission of Submersible sump pumps Shop drawing | 18 | 0.0012795 | 2026-02-14 | 2026-03-07 | 0% | 100% | 0% | 100%
EN.PS.D22.SDS.1055 | IPS l Submission of Pump room piping & fitting Shop drawing | 18 | 0.0060893 | 2026-03-08 | 2026-03-31 | 0% | 100% | 0% | 100%
HVAC System Shop Drawing Submittal |  | 20 |  | 2026-03-29 | 2026-04-20
EN.PS.D23.SDS.1065 | IPS l Submission of HVAC System shop drawing | 20 | 0.0029217 | 2026-03-29 | 2026-04-20 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Submittal |  | 66 |  | 2026-02-02 | 2026-04-23
EN.PS.D26.SDS.1075 | IPS l Submission of Power system shop drawing | 12 | 0.00092149 | 2026-02-02 | 2026-02-15 | 16.67% | 100% | 0% | 100%
EN.PS.D26.SDS.1080 | IPS l Submission of Lightning & Earthing shop drawing | 15 | 0.00059832 | 2026-02-16 | 2026-03-05 | 0% | 100% | 0% | 100%
EN.PS.D26.SDS.1085 | IPS l Submission of Cable routing shop drawing | 16 | 0.0020921 | 2026-02-16 | 2026-03-07 | 0% | 100% | 0% | 100%
EN.PS.D26.SDS.1090 | IPS l Submission of lighting system shop drawing | 18 | 0.0063751 | 2026-03-08 | 2026-03-31 | 0% | 100% | 0% | 100%
EN.PS.D26.SDS.1070 | IPS l Submission of Panel board shop drawing | 20 | 0.0032674 | 2026-04-01 | 2026-04-23 | 0% | 100% | 0% | 100%
Low Current Shop Drawing Submittal |  | 20 |  | 2026-04-01 | 2026-04-23
EN.PS.D27.SDS.1095 | IPS l Submission of Communication System shop drawing | 20 | 0.0044579 | 2026-04-01 | 2026-04-23 | 0% | 100% | 0% | 100%
Security Shop Drawing Submittal |  | 18 |  | 2026-04-25 | 2026-05-14
EN.PS.D28.SDS.1100 | IPS l Submission of Access control shop drawing | 18 | 0.0003552 | 2026-04-25 | 2026-05-14 | 0% | 100% | 0% | 100%
EN.PS.D28.SDS.1105 | IPS l Submission of CCTV system shop drawing | 18 | 0.00045124 | 2026-04-25 | 2026-05-14 | 0% | 100% | 0% | 100%
EN.PS.D28.SDS.1110 | IPS l Submission of Fire alarm system shop drawing | 18 | 0.00065739 | 2026-04-25 | 2026-05-14 | 0% | 100% | 0% | 100%
Earthworks Shop Drawing Submittal |  | 20 |  | 2025-12-04 | 2025-12-27
EN.PS.D31.SDS.1115 | IPS l Submission of Reinforced piles Shop drawing | 20 | 0.0058991 | 2025-12-04 | 2025-12-27 | 100% | 100% | 0% | 100%
External Improvement Shop Drawing Submittal |  | 48 |  | 2026-04-21 | 2026-06-18
EN.PS.D32.SDS.1130 | IPS l Submission of Precast concrete wall Shop drawing | 20 | 0.0031902 | 2026-04-21 | 2026-05-13 | 0% | 50% | 0% | 50% |  | Pending feedback from KAFD to replace pre-cast boundary walls with steel fence
EN.PS.D32.SDS.1120 | IPS l Submission of concrete paving Shop drawing | 16 | 0.00077652 | 2026-05-14 | 2026-06-04 | 0% | 100% | 0% | 100%
EN.PS.D32.SDS.1125 | IPS l Submission of Sliding gates Shop drawing | 16 | 0.0005784 | 2026-05-14 | 2026-06-04 | 0% | 100% | 0% | 100%
EN.PS.D32.SDS.1135 | IPS l Submission of Planting Shop drawing | 12 | 0.0013816 | 2026-06-06 | 2026-06-18 | 0% | 100% | 0% | 100%
Special System Shop Drawing Submittal |  | 20 |  | 2026-05-16 | 2026-06-10
EN.PS.D40.SDS.1140 | IPS l Submission of Process Control Systems Shop drawing | 20 | 0.010879 | 2026-05-16 | 2026-06-10 | 0% | 100% | 0% | 100%
Pump-Station Shop Drawing Approval |  | 132 |  | 2025-12-28 | 2026-07-08
Concrete Shop Drawing Approval |  | 14 |  | 2026-01-15 | 2026-02-03
EN.PS.D03.SDA.1010 | IPS l Approval of Concrete Works Shop drawing | 14 | 0.0052672 | 2026-01-15 | 2026-02-03 | 100% | 100% | 0% | 100%
Masonry Shop Drawing Approval |  | 14 |  | 2026-02-02 | 2026-02-19
EN.PS.D04.SDA.1015 | IPS l Approval of Masonry works Shop drawing | 14 | 0.00036389 | 2026-02-02 | 2026-02-19 | 14.29% | 100% | 0% | 100%
Metal Shop Drawing Approval |  | 14 |  | 2026-03-17 | 2026-04-08
EN.PS.D05.SDA.1020 | IPS l Approval of Trench covers Shop drawing | 14 | 0.0010526 | 2026-03-17 | 2026-04-08 | 100% | 50% | 0% | 50% |  | Approved
Thermal Protection Shop Drawing Approval |  | 14 |  | 2026-03-03 | 2026-03-25
EN.PS.D07.SDA.1025 | IPS l Approval of Aluminum cladding Shop drawing | 14 | 0.0014132 | 2026-03-03 | 2026-03-25 | 100% | 80% | 0% | 80% |  | Under Review
Openings Shop Drawing Approval |  | 14 |  | 2026-02-16 | 2026-03-08
EN.PS.D08.SDA.1030 | IPS l Approval of Steel doors Shop drawing | 14 | 0.00027686 | 2026-02-16 | 2026-03-08 | 0% | 0% | 0% | 0% |  | Pending approval of the system by KAFD meeting was held today Aug. 10th
EN.PS.D08.SDA.1035 | IPS l Approval of Aluminium louvers Shop drawing | 14 | 0.00023857 | 2026-02-16 | 2026-03-08 | 100% | 100% | 0% | 100% |  | not in IFC
Special construction Shop Drawing Approval |  | 14 |  | 2026-03-15 | 2026-04-06
EN.PS.D13.SDA.1040 | IPS l Approval of Aluminium Control booths Shop drawing | 14 | 0.00034204 | 2026-03-15 | 2026-04-06 | 100% | 100% | 0% | 100%
Fire Supperssion Shop Drawing Approval |  | 14 |  | 2026-03-29 | 2026-04-15
EN.PS.D21.SDA.1045 | IPS l Approval of Fire Suppression Shop drawing | 14 | 0.0030517 | 2026-03-29 | 2026-04-15 | 0% | 100% | 0% | 100%
Plumbing Shop Drawing Approval |  | 43 |  | 2026-02-15 | 2026-04-20
EN.PS.D22.SDA.1050 | IPS l Approval of Electrical room plumbing Shop drawing | 14 | 0.00016589 | 2026-02-15 | 2026-03-05 | 0% | 100% | 0% | 100%
EN.PS.D22.SDA.1060 | IPS l Approval of Submersible sump pumps Shop drawing | 14 | 0.0012795 | 2026-03-08 | 2026-03-30 | 0% | 100% | 0% | 100%
EN.PS.D22.SDA.1055 | IPS l Approval of Pump room piping & fitting Shop drawing | 14 | 0.0060893 | 2026-04-01 | 2026-04-20 | 0% | 100% | 0% | 100%
HVAC System Shop Drawing Approval |  | 14 |  | 2026-04-21 | 2026-05-10
EN.PS.D23.SDA.1065 | IPS l Approval of HVAC System shop drawing | 14 | 0.0029217 | 2026-04-21 | 2026-05-10 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Approvall |  | 59 |  | 2026-02-16 | 2026-05-13
EN.PS.D26.SDA.1075 | IPS l Approval of Power system shop drawing | 14 | 0.00092149 | 2026-02-16 | 2026-03-08 | 0% | 100% | 0% | 100%
EN.PS.D26.SDA.1080 | IPS l Approval of Lightning & Earthing shop drawing | 14 | 0.00059832 | 2026-03-08 | 2026-03-30 | 0% | 100% | 0% | 100%
EN.PS.D26.SDA.1085 | IPS l Approval of Cable routing shop drawing | 14 | 0.0020921 | 2026-03-08 | 2026-03-30 | 0% | 90% | 0% | 90% |  | remaining SLD only, rejected the submission after input from supplier
EN.PS.D26.SDA.1090 | IPS l Approval of lighting system shop drawing | 14 | 0.0063751 | 2026-04-01 | 2026-04-20 | 0% | 100% | 0% | 100%
EN.PS.D26.SDA.1070 | IPS l Approval of Panel board shop drawing | 14 | 0.0032674 | 2026-04-26 | 2026-05-13 | 100% | 80% | 0% | 80% |  | approved
Low Current Shop Drawing Approval |  | 14 |  | 2026-04-26 | 2026-05-13
EN.PS.D27.SDA.1095 | IPS l Approval of Communication System shop drawing | 14 | 0.0044579 | 2026-04-26 | 2026-05-13 | 0% | 90% | 0% | 90% |  | Under Review
Security Shop Drawing Approval |  | 14 |  | 2026-05-17 | 2026-06-08
EN.PS.D28.SDA.1100 | IPS l Approval of Access control shop drawing | 14 | 0.0003552 | 2026-05-17 | 2026-06-08 | 0% | 0% | 0% | 0% |  | pending confirmation from KAFD
EN.PS.D28.SDA.1105 | IPS l Approval of CCTV system shop drawing | 14 | 0.00045124 | 2026-05-17 | 2026-06-08 | 0% | 0% | 0% | 0% |  | pending confirmation from KAFD
EN.PS.D28.SDA.1110 | IPS l Approval of Fire alarm system shop drawing | 14 | 0.00065739 | 2026-05-17 | 2026-06-08 | 0% | 100% | 0% | 100%
Earthworks Shop Drawing Approval |  | 14 |  | 2025-12-28 | 2026-01-14
EN.PS.D31.SDA.1115 | IPS l Approval of Reinforced piles Shop drawing | 14 | 0.0058991 | 2025-12-28 | 2026-01-14 | 100% | 100% | 0% | 100%
External Improvement Shop Drawing Approval |  | 37 |  | 2026-05-14 | 2026-07-08
EN.PS.D32.SDA.1130 | IPS l Approval of Precast concrete wall Shop drawing | 14 | 0.0031902 | 2026-05-14 | 2026-06-07 | 0% | 50% | 0% | 50% |  | Pending feedback from KAFD to replace pre-cast boundary walls with steel fence
EN.PS.D32.SDA.1120 | IPS l Approval of concrete paving Shop drawing | 14 | 0.00077652 | 2026-06-07 | 2026-06-24 | 0% | 100% | 0% | 100%
EN.PS.D32.SDA.1125 | IPS l Approval of Sliding gates Shop drawing | 14 | 0.0005784 | 2026-06-07 | 2026-06-24 | 0% | 0% | 0% | 0% |  | Supplier not approved
EN.PS.D32.SDA.1135 | IPS l Approval of Planting Shop drawing | 14 | 0.0013816 | 2026-06-21 | 2026-07-08 | 100% | 100% | 0% | 100% |  | Approved long time ago
Special System Shop Drawing Approval |  | 14 |  | 2026-06-11 | 2026-06-30
EN.PS.D40.SDA.1140 | IPS l Approval of Process Control Systems Shop drawing | 14 | 0.010879 | 2026-06-11 | 2026-06-30 | 0% | 80% | 0% | 80% |  | approved
Collection System |  | 136 |  | 2026-03-15 | 2026-07-28
Collection System Shop Drawing Submittal |  | 94 |  | 2026-03-15 | 2026-07-08
Plumbing Shop Drawing Submittal |  | 54 |  | 2026-03-15 | 2026-05-19
EN.CL.D33.SDS.1005 | CLS l Submission of Gravity network shop drawing | 20 | 0.026573 | 2026-03-15 | 2026-04-09 | 0% | 100% | 0% | 100%
EN.CL.D22.SDS.1000 | CLS l Submission of Submersible pump room shop drawing | 20 | 0.033078 | 2026-04-11 | 2026-05-03 | 0% | 100% | 0% | 100%
EN.CL.D33.SDS.1015 | CLS l Submission of Pressured network inside the tunnel shop drawing | 20 | 0.064609 | 2026-04-11 | 2026-05-03 | 0% | 100% | 0% | 100%
EN.CL.D33.SDS.1010 | CLS l Submission of Pressured network in trenches shop drawing | 10 | 0.021789 | 2026-05-04 | 2026-05-14 | 0% | 100% | 0% | 100%
EN.CL.D33.SDS.1020 | CLS l Submission of Fabricated Channel shop drawing | 14 | 0.010276 | 2026-05-04 | 2026-05-19 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Submittal |  | 40 |  | 2026-05-20 | 2026-07-08
EN.CL.D33.SDS.1030 | CLS l Submission of Fiber Optic network drawing | 20 | 0.047623 | 2026-05-20 | 2026-06-15 | 0% | 90% | 0% | 90% |  | remaining routing inside new tunnel (Al Ajmi scope )
EN.CL.D33.SDS.1025 | CLS l Submission of Remote terminal unit (RTU) shop drawing | 20 | 0.014446 | 2026-06-16 | 2026-07-08 | 0% | 100% | 0% | 100%
Collection System Shop Drawing Approval |  | 75 |  | 2026-04-12 | 2026-07-28
Plumbing Shop Drawing Approval |  | 42 |  | 2026-04-12 | 2026-06-11
EN.CL.D33.SDA.1005 | CLS l Approval of Gravity network shop drawing | 14 | 0.026573 | 2026-04-12 | 2026-04-29 | 0% | 100% | 0% | 100%
EN.CL.D22.SDA.1000 | CLS l Approval of Submersible pump room shop drawing | 14 | 0.033078 | 2026-05-04 | 2026-05-21 | 0% | 100% | 0% | 100%
EN.CL.D33.SDA.1015 | CLS l Approval of Pressured network inside the tunnel shop drawing | 14 | 0.064609 | 2026-05-04 | 2026-05-21 | 0% | 95% | 0% | 95% |  | remaining routing inside new tunnel (Al Ajmi scope )
EN.CL.D33.SDA.1010 | CLS l Approval of Pressured network in trenches shop drawing | 14 | 0.021789 | 2026-05-17 | 2026-06-08 | 0% | 100% | 0% | 100%
EN.CL.D33.SDA.1020 | CLS l Approval of Fabricated Channel shop drawing | 14 | 0.010276 | 2026-05-20 | 2026-06-11 | 0% | 100% | 0% | 100%
Electrical System Shop Drawing Approval |  | 31 |  | 2026-06-16 | 2026-07-28
EN.CL.D33.SDA.1030 | CLS l Approval of Fiber Optic network drawing | 14 | 0.047623 | 2026-06-16 | 2026-07-05 | 0% | 90% | 0% | 90% |  | remaining routing inside new tunnel (Al Ajmi scope )
EN.CL.D33.SDA.1025 | CLS l Approval of Remote terminal unit (RTU) shop drawing | 14 | 0.014446 | 2026-07-09 | 2026-07-28 | 0% | 100% | 0% | 100%
Procurement |  | 403 |  | 2025-11-17 | 2026-12-24 | 8.576% | 67.85% | 0.4303% | 68.28%
RO Plant |  | 403 |  | 2025-11-17 | 2026-12-24
Short Lead Items |  | 392 |  | 2025-11-17 | 2026-12-13
RO Plant Material Submittal - Short Lead |  | 271 |  | 2025-11-17 | 2026-10-07
Structural Material Submittal |  | 98 |  | 2025-11-17 | 2026-03-11
PR.RO.D31.MTS.1035 | RO l MT Submission for Concrete Piles & prestressed anchors | 14 | 0.096772 | 2025-11-17 | 2025-12-02 | 100% | 100% | 0% | 100%
PR.RO.D07.MTS.1030 | RO l MT Submission for Thermal & Moisture insulation | 12 | 0.047356 | 2026-02-26 | 2026-03-11 | 0% | 100% | 0% | 100%
Finishes Material Submittal |  | 74 |  | 2026-05-30 | 2026-08-23
PR.RO.D04.MTS.1040 | RO l MT Submission for Masonary | 14 | 0.0069029 | 2026-05-30 | 2026-06-14 | 0% | 50% | 0% | 50% |  | KAFD-636-SBC-CIV-MAR-00028 Submitted | Remaining Hollow & Solid Block
PR.RO.D09.MTS.1060 | RO l MT Submission for Floor | 12 | 0.0040481 | 2026-06-15 | 2026-06-28 | 100% | 100% | 0% | 100% |  | KAFD-636-SBC-ARC-MAR-00035 KAFD-636-SBC-ARC-MAR-00033 Submitted
PR.RO.D08.MTS.1050 | RO l MT Submission for Steel doors | 12 | 0.0054775 | 2026-06-29 | 2026-07-12 | 0% | 100% | 0% | 100%
PR.RO.D09.MTS.1055 | RO l MT Submission for Gypsum board | 12 | 0.0069466 | 2026-07-27 | 2026-08-09 | 100% | 100% | 0% | 100%
PR.RO.D04.MTS.1045 | RO l MT Submission for Stone cladding | 12 | 0.007785 | 2026-08-10 | 2026-08-23 | 0% | 100% | 0% | 100%
Fire Supperssion Material Submittal |  | 18 |  | 2026-07-08 | 2026-07-28
PR.RO.D21.MTS.1065 | RO l MT Submission for Fire Suppression piping & fitting | 18 | 0.0081828 | 2026-07-08 | 2026-07-28 | 0% | 100% | 0% | 100%
Plumbing Material Submittal |  | 38 |  | 2026-06-15 | 2026-07-28
PR.RO.D22.MTS.1075 | RO l MT Submission for Sanitary pipes & fitting | 16 | 0.0025672 | 2026-06-15 | 2026-07-02 | 0% | 100% | 0% | 100%
PR.RO.D22.MTS.1070 | RO l MT Submission for Water supply pipes & Valves | 20 | 0.0040625 | 2026-06-15 | 2026-07-07 | 0% | 100% | 0% | 100%
PR.RO.D22.MTS.1080 | RO l MT Submission for Plumbing Fixtures | 18 | 0.00091235 | 2026-07-08 | 2026-07-28 | 0% | 100% | 0% | 100%
HVAC System Material Submittal |  | 38 |  | 2026-07-04 | 2026-08-16
PR.RO.D23.MTS.1090 | RO l MT Submission for HVAC Ducts | 18 | 0.011343 | 2026-07-04 | 2026-07-23 | 0% | 100% | 0% | 100%
PR.RO.D23.MTS.1085 | RO l MT Submission for HVAC piping & Valves | 20 | 0.0039035 | 2026-07-04 | 2026-07-26 | 0% | 100% | 0% | 100%
PR.RO.D23.MTS.1095 | RO l MT Submission for HVAC Accessories | 18 | 0.0031744 | 2026-07-27 | 2026-08-16 | 0% | 100% | 0% | 100%
Electrical System Material Submittal |  | 56 |  | 2026-07-04 | 2026-09-06
PR.RO.D26.MTS.1110 | RO l MT Submission for Cable routing matrial | 18 | 0.0031219 | 2026-07-04 | 2026-07-23 | 0% | 100% | 0% | 100%
PR.RO.D26.MTS.1115 | RO l MT Submission for Sochets & switches matrial | 18 | 0.0013023 | 2026-07-25 | 2026-08-13 | 100% | 100% | 0% | 100%
PR.RO.D26.MTS.1100 | RO l MT Submission for Distribution board | 20 | 0.0056377 | 2026-07-25 | 2026-08-16 | 100% | 100% | 0% | 100% |  | Waiting Al Fanar Calculation
PR.RO.D26.MTS.1105 | RO l MT Submission for Uninterruptible Power Supply (UPS) | 18 | 0.0064854 | 2026-08-17 | 2026-09-06 | 0% | 100% | 0% | 100%
Low Current Material Submittal |  | 48 |  | 2026-07-25 | 2026-09-17
PR.RO.D27.MTS.1125 | RO l MT Submission for Communication Cables | 16 | 0.0023385 | 2026-07-25 | 2026-08-11 | 0% | 100% | 0% | 100%
PR.RO.D27.MTS.1130 | RO l MT Submission for Data communication components | 12 | 0.012681 | 2026-08-12 | 2026-08-25 | 0% | 100% | 0% | 100%
PR.RO.D27.MTS.1135 | RO l MT Submission for Telecommunication components | 12 | 0.002451 | 2026-08-12 | 2026-08-25 | 0% | 100% | 0% | 100%
PR.RO.D27.MTS.1120 | RO l MT Submission for Communication equipment fitting | 20 | 0.0029882 | 2026-08-26 | 2026-09-17 | 0% | 100% | 0% | 100%
Security Material Submittal |  | 16 |  | 2026-09-19 | 2026-10-07
PR.RO.D28.MTS.1140 | RO l MT Submission for Access control components | 16 | 0.0034646 | 2026-09-19 | 2026-10-07 | 0% | 100% | 0% | 100%
PR.RO.D28.MTS.1145 | RO l MT Submission for CCTV system components | 16 | 0.0056897 | 2026-09-19 | 2026-10-07 | 0% | 100% | 0% | 100%
PR.RO.D28.MTS.1150 | RO l MT Submission for Fire alarm components | 16 | 0.0032703 | 2026-09-19 | 2026-10-07 | 0% | 100% | 0% | 100%
External Improvement Material Submittal |  | 60 |  | 2026-06-15 | 2026-08-23
PR.RO.D32.MTS.1160 | RO l MT Submission for Precast concrete wall | 30 | 0.0089505 | 2026-06-15 | 2026-07-19 | 100% | 100% | 0% | 100% |  | KAFD-636-SBC-ARC-MAR-00034
PR.RO.D32.MTS.1155 | RO l MT Submission for Precast concrete paving | 30 | 0.0023724 | 2026-07-20 | 2026-08-23 | 100% | 100% | 0% | 100% |  | Samples Provided
RO Plant Material Approval - Short Lead |  | 227 |  | 2025-12-03 | 2026-10-27
Structural Material Approval |  | 84 |  | 2025-12-03 | 2026-04-05
PR.RO.D31.MTA.1035 | RO l MT Approval for Concrete Piles & prestressed anchors | 14 | 0.096772 | 2025-12-03 | 2025-12-22 | 100% | 100% | 0% | 100%
PR.RO.D07.MTA.1030 | RO l MT Approval for Thermal & Moisture insulation | 14 | 0.047356 | 2026-03-12 | 2026-04-05 | 0% | 100% | 0% | 100% |  | KAFD-636-SBC-ARC-MAR-00019 KAFD-636-SBC-CIV-MAR-00036 KAFD-636-SBC-CIV-MAR-00099 KAFD-636-SBC-CIV-MAR-00101 KAFD-636-SBC-CIV-MAR-00103 KAFD-636-SBC-CIV-MAR-00006
Finishes Material Approval |  | 64 |  | 2026-06-15 | 2026-09-10
PR.RO.D04.MTA.1040 | RO l MT Approval for Masonary | 14 | 0.0069029 | 2026-06-15 | 2026-07-02 | 100% | 50% | 0% | 50% |  | KAFD-636-SBC-CIV-MAR-00028 Submitted | Remaining Hollow Block and Other Type: Solid Block
PR.RO.D09.MTA.1060 | RO l MT Approval for Floor | 14 | 0.0040481 | 2026-06-29 | 2026-07-16 | 35.71% | 0% | 10% | 10% |  | Rejected - Checking another supplier
PR.RO.D08.MTA.1050 | RO l MT Approval for Steel doors | 14 | 0.0054775 | 2026-07-13 | 2026-07-30 | 0% | 50% | 0% | 50% |  | Under Review
PR.RO.D09.MTA.1055 | RO l MT Approval for Gypsum board | 14 | 0.0069466 | 2026-08-10 | 2026-08-27 | 100% | 100% | 0% | 100%
PR.RO.D04.MTA.1045 | RO l MT Approval for Stone cladding | 14 | 0.007785 | 2026-08-24 | 2026-09-10 | 0% | 0% | 0% | 0%
Fire Supperssion Material Approval |  | 14 |  | 2026-07-29 | 2026-08-17
PR.RO.D21.MTA.1065 | RO l MT Approval for Fire Suppression piping & fitting | 14 | 0.0081828 | 2026-07-29 | 2026-08-17 | 0% | 100% | 0% | 100%
Plumbing Material Approval |  | 32 |  | 2026-07-05 | 2026-08-17
PR.RO.D22.MTA.1075 | RO l MT Approval for Sanitary pipes & fitting | 14 | 0.0025672 | 2026-07-05 | 2026-07-22 | 0% | 100% | 0% | 100%
PR.RO.D22.MTA.1070 | RO l MT Approval for Water supply pipes & Valves | 14 | 0.0040625 | 2026-07-08 | 2026-07-27 | 0% | 100% | 0% | 100%
PR.RO.D22.MTA.1080 | RO l MT Approval for Plumbing Fixtures | 14 | 0.00091235 | 2026-07-29 | 2026-08-17 | 0% | 100% | 0% | 100%
HVAC System Material Approvall |  | 30 |  | 2026-07-26 | 2026-09-03
PR.RO.D23.MTA.1090 | RO l MT Approval for HVAC Ducts | 14 | 0.011343 | 2026-07-26 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.RO.D23.MTA.1085 | RO l MT Approval for HVAC piping & Valves | 14 | 0.0039035 | 2026-07-27 | 2026-08-13 | 0% | 100% | 0% | 100%
PR.RO.D23.MTA.1095 | RO l MT Approval for HVAC Accessories | 14 | 0.0031744 | 2026-08-17 | 2026-09-03 | 0% | 100% | 0% | 100%
Electrical System Material Approval |  | 45 |  | 2026-07-26 | 2026-09-27
PR.RO.D26.MTA.1110 | RO l MT Approval for Cable routing matrial | 14 | 0.0031219 | 2026-07-26 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.RO.D26.MTA.1115 | RO l MT Approval for Sochets & switches matrial | 14 | 0.0013023 | 2026-08-16 | 2026-09-02 | 100% | 100% | 0% | 100% |  | outlets wiring devices still remaining
PR.RO.D26.MTA.1100 | RO l MT Approval for Distribution board | 14 | 0.0056377 | 2026-08-17 | 2026-09-03 | 100% | 20% | 0% | 20%
PR.RO.D26.MTA.1105 | RO l MT Approval for Uninterruptible Power Supply (UPS) | 14 | 0.0064854 | 2026-09-07 | 2026-09-27 | 100% | 100% | 0% | 100%
Low Current Material Approval |  | 41 |  | 2026-08-12 | 2026-10-08
PR.RO.D27.MTA.1125 | RO l MT Approval for Communication Cables | 14 | 0.0023385 | 2026-08-12 | 2026-08-31 | 0% | 100% | 0% | 100%
PR.RO.D27.MTA.1130 | RO l MT Approval for Data communication components | 14 | 0.012681 | 2026-08-26 | 2026-09-14 | 100% | 100% | 0% | 100%
PR.RO.D27.MTA.1135 | RO l MT Approval for Telecommunication components | 14 | 0.002451 | 2026-08-26 | 2026-09-14 | 0% | 100% | 0% | 100%
PR.RO.D27.MTA.1120 | RO l MT Approval for Communication equipment fitting | 14 | 0.0029882 | 2026-09-20 | 2026-10-08 | 0% | 100% | 0% | 100%
Security Material Approval |  | 14 |  | 2026-10-08 | 2026-10-27
PR.RO.D28.MTA.1140 | RO l MT Approval for Access control components | 14 | 0.0034646 | 2026-10-08 | 2026-10-27 | 0% | 0% | 0% | 0%
PR.RO.D28.MTA.1145 | RO l MT Approval for CCTV system components | 14 | 0.0056897 | 2026-10-08 | 2026-10-27 | 0% | 0% | 0% | 0%
PR.RO.D28.MTA.1150 | RO l MT Approval for Fire alarm components | 14 | 0.0032703 | 2026-10-08 | 2026-10-27 | 0% | 100% | 0% | 100%
External Improvement Material Approval |  | 39 |  | 2026-07-20 | 2026-09-10
PR.RO.D32.MTA.1160 | RO l MT Approval for Precast concrete wall | 14 | 0.0089505 | 2026-07-20 | 2026-08-06 | 0% | 0% | 0% | 0% |  | Waiting supplier
PR.RO.D32.MTA.1155 | RO l MT Approval for Precast concrete paving | 14 | 0.0023724 | 2026-08-24 | 2026-09-10 | 0% | 0% | 0% | 0%
RO Plant Material PO - Short Lead |  | 273 |  | 2025-12-23 | 2026-11-15
Structural Material PO |  | 97 |  | 2025-12-23 | 2026-04-19
PR.RO.D31.MPO.1035 | RO l PO Placement for Concrete Piles & prestressed anchors | 10 | 0.19354 | 2025-12-23 | 2026-01-03 | 100% | 100% | 0% | 100%
PR.RO.D07.MPO.1030 | RO l PO Placement for Thermal & Moisture insulation | 12 | 0.094713 | 2026-04-06 | 2026-04-19 | 0% | 100% | 0% | 100%
Finishes Material PO |  | 72 |  | 2026-07-04 | 2026-09-26
PR.RO.D04.MPO.1040 | RO l PO Placement for Masonary | 12 | 0.013806 | 2026-07-04 | 2026-07-16 | 100% | 50% | 50% | 100% |  | PR issued
PR.RO.D09.MPO.1060 | RO l PO Placement for Floor | 18 | 0.0080962 | 2026-07-18 | 2026-08-06 | 0% | 0% | 100% | 100% |  | Waiting MAR approval
PR.RO.D08.MPO.1050 | RO l PO Placement for Steel doors | 18 | 0.010955 | 2026-08-01 | 2026-08-20 | 0% | 100% | 0% | 100%
PR.RO.D09.MPO.1055 | RO l PO Placement for Gypsum board | 18 | 0.013893 | 2026-08-29 | 2026-09-17 | 100% | 100% | 0% | 100%
PR.RO.D04.MPO.1045 | RO l PO Placement for Stone cladding | 12 | 0.01557 | 2026-09-12 | 2026-09-26 | 0% | 100% | 0% | 100%
Fire Supperssion Material PO |  | 20 |  | 2026-08-18 | 2026-09-09
PR.RO.D21.MPO.1065 | RO l PO Placement for Fire Suppression piping & fitting | 20 | 0.016366 | 2026-08-18 | 2026-09-09 | 0% | 100% | 0% | 100%
Plumbing Material PO |  | 42 |  | 2026-07-23 | 2026-09-09
PR.RO.D22.MPO.1075 | RO l PO Placement for Sanitary pipes & fitting | 18 | 0.0051344 | 2026-07-23 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.RO.D22.MPO.1070 | RO l PO Placement for Water supply pipes & Valves | 18 | 0.0081249 | 2026-07-28 | 2026-08-17 | 0% | 100% | 0% | 100%
PR.RO.D22.MPO.1080 | RO l PO Placement for Plumbing Fixtures | 20 | 0.0018247 | 2026-08-18 | 2026-09-09 | 0% | 100% | 0% | 100%
HVAC System Material PO |  | 39 |  | 2026-08-13 | 2026-09-28
PR.RO.D23.MPO.1090 | RO l PO Placement for HVAC Ducts | 20 | 0.022686 | 2026-08-13 | 2026-09-05 | 0% | 100% | 0% | 100%
PR.RO.D23.MPO.1085 | RO l PO Placement for HVAC piping & Valves | 20 | 0.0078071 | 2026-08-15 | 2026-09-06 | 0% | 100% | 0% | 100%
PR.RO.D23.MPO.1095 | RO l PO Placement for HVAC Accessories | 20 | 0.0063488 | 2026-09-05 | 2026-09-28 | 0% | 100% | 0% | 100%
Electrical System Material PO |  | 54 |  | 2026-08-13 | 2026-10-15
PR.RO.D26.MPO.1110 | RO l PO Placement for Cable routing matrial | 16 | 0.0062438 | 2026-08-13 | 2026-08-31 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1115 | RO l PO Placement for Sochets & switches matrial | 16 | 0.0026045 | 2026-09-03 | 2026-09-21 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1100 | RO l PO Placement for Distribution board | 20 | 0.011275 | 2026-09-05 | 2026-09-28 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1105 | RO l PO Placement for Uninterruptible Power Supply (UPS) | 16 | 0.012971 | 2026-09-28 | 2026-10-15 | 0% | 100% | 0% | 100%
Low Current Material PO |  | 52 |  | 2026-09-01 | 2026-11-01
PR.RO.D27.MPO.1125 | RO l PO Placement for Communication Cables | 18 | 0.004677 | 2026-09-01 | 2026-09-21 | 0% | 100% | 0% | 100%
PR.RO.D27.MPO.1135 | RO l PO Placement for Telecommunication components | 18 | 0.0049019 | 2026-09-15 | 2026-10-06 | 0% | 100% | 0% | 100%
PR.RO.D27.MPO.1130 | RO l PO Placement for Data communication components | 20 | 0.025362 | 2026-09-15 | 2026-10-08 | 0% | 100% | 0% | 100%
PR.RO.D27.MPO.1120 | RO l PO Placement for Communication equipment fitting | 20 | 0.0059764 | 2026-10-10 | 2026-11-01 | 0% | 100% | 0% | 100%
Security Material PO |  | 16 |  | 2026-10-28 | 2026-11-15
PR.RO.D28.MPO.1140 | RO l PO Placement for Access control components | 16 | 0.0069293 | 2026-10-28 | 2026-11-15 | 0% | 100% | 0% | 100%
PR.RO.D28.MPO.1145 | RO l PO Placement for CCTV system components | 16 | 0.011379 | 2026-10-28 | 2026-11-15 | 0% | 0% | 0% | 0%
PR.RO.D28.MPO.1150 | RO l PO Placement for Fire alarm components | 16 | 0.0065405 | 2026-10-28 | 2026-11-15 | 0% | 100% | 0% | 100%
External Improvement Material PO |  | 55 |  | 2026-08-08 | 2026-10-11
PR.RO.D32.MPO.1160 | RO l PO Placement for Precast concrete wall | 40 | 0.017901 | 2026-08-08 | 2026-09-22 | 0% | 100% | 0% | 100%
PR.RO.D32.MPO.1155 | RO l PO Placement for Precast concrete paving | 25 | 0.0047448 | 2026-09-12 | 2026-10-11 | 0% | 100% | 0% | 100%
RO Plant Material Delivery and Fabrication - Short Lead |  | 344 |  | 2026-01-04 | 2026-12-13
Structural Material Delivery and Fabrication |  | 122 |  | 2026-01-04 | 2026-05-05
PR.RO.D31.MTD.1035 | RO l MT Delivery for Concrete Piles & prestressed anchors | 14 | 0.58063 | 2026-01-04 | 2026-01-17 | 100% | 100% | 0% | 100%
PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation | 16 | 0.28414 | 2026-04-20 | 2026-05-05 | 0% | 30% | 0% | 30% |  | Upon Request
Finishes Material Delivery and Fabrication |  | 92 |  | 2026-07-17 | 2026-10-16
PR.RO.D04.MTD.1040 | RO l MT Delivery for Masonary | 30 | 0.041417 | 2026-07-17 | 2026-08-15 | 0% | 0% | 0% | 0% |  | Upon Request
PR.RO.D09.MTD.1060 | RO l MT Delivery for Floor | 35 | 0.024289 | 2026-08-07 | 2026-09-10 | 0% | 0% | 0% | 0% |  | Waiting Supplier
PR.RO.D08.MTD.1050 | RO l MT Delivery for Steel doors | 25 | 0.032865 | 2026-08-21 | 2026-09-14 | 0% | 0% | 0% | 0%
PR.RO.D09.MTD.1055 | RO l MT Delivery for Gypsum board | 25 | 0.041679 | 2026-09-18 | 2026-10-12 | 0% | 0% | 0% | 0%
PR.RO.D04.MTD.1045 | RO l MT Delivery for Stone cladding | 20 | 0.04671 | 2026-09-27 | 2026-10-16 | 0% | 0% | 0% | 0%
Fire Supperssion Material Delivery and Fabrication |  | 25 |  | 2026-09-10 | 2026-10-04
PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting | 25 | 0.049097 | 2026-09-10 | 2026-10-04 | 24% | 0% | 5% | 5%
Plumbing Material Delivery and Fabrication |  | 48 |  | 2026-08-13 | 2026-09-29
PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting | 20 | 0.015403 | 2026-08-13 | 2026-09-01 | 0% | 0% | 0% | 0%
PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves | 20 | 0.024375 | 2026-08-18 | 2026-09-06 | 0% | 0% | 0% | 0%
PR.RO.D22.MTD.1080 | RO l MT Delivery for Plumbing Fixtures | 20 | 0.0054741 | 2026-09-10 | 2026-09-29 | 0% | 0% | 0% | 0%
HVAC System Material Delivery and Fabrication |  | 45 |  | 2026-09-06 | 2026-10-20
PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts | 20 | 0.068057 | 2026-09-06 | 2026-09-25 | 0% | 0% | 0% | 0%
PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves | 25 | 0.023421 | 2026-09-07 | 2026-10-01 | 0% | 0% | 0% | 0%
PR.RO.D23.MTD.1095 | RO l MT Delivery for HVAC Accessories | 22 | 0.019046 | 2026-09-29 | 2026-10-20 | 0% | 0% | 0% | 0%
Electrical System Material Delivery and Fabrication |  | 67 |  | 2026-09-01 | 2026-11-06
PR.RO.D26.MTD.1110 | RO l MT Delivery for Cable routing matrial | 20 | 0.018731 | 2026-09-01 | 2026-09-20 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1115 | RO l MT Delivery for Sochets & switches matrial | 20 | 0.0078136 | 2026-09-22 | 2026-10-11 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board | 26 | 0.033826 | 2026-09-29 | 2026-10-24 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1105 | RO l MT Delivery for Uninterruptible Power Supply (UPS) | 22 | 0.038912 | 2026-10-16 | 2026-11-06 | 0% | 0% | 0% | 0%
Low Current Material Delivery and Fabrication |  | 69 |  | 2026-09-22 | 2026-11-29
PR.RO.D27.MTD.1125 | RO l MT Delivery for Communication Cables | 30 | 0.014031 | 2026-09-22 | 2026-10-21 | 0% | 0% | 0% | 0%
PR.RO.D27.MTD.1135 | RO l MT Delivery for Telecommunication components | 25 | 0.014706 | 2026-10-07 | 2026-10-31 | 0% | 0% | 0% | 0%
PR.RO.D27.MTD.1130 | RO l MT Delivery for Data communication components | 27 | 0.076085 | 2026-10-09 | 2026-11-04 | 0% | 0% | 0% | 0%
PR.RO.D27.MTD.1120 | RO l MT Delivery for Communication equipment fitting | 28 | 0.017929 | 2026-11-02 | 2026-11-29 | 0% | 0% | 0% | 0%
Security Material Delivery and Fabrication |  | 28 |  | 2026-11-16 | 2026-12-13
PR.RO.D28.MTD.1140 | RO l MT Delivery for Access control components | 26 | 0.020788 | 2026-11-16 | 2026-12-11 | 0% | 0% | 0% | 0%
PR.RO.D28.MTD.1150 | RO l MT Delivery for Fire alarm components | 26 | 0.019622 | 2026-11-16 | 2026-12-11 | 23.08% | 0% | 70% | 70%
PR.RO.D28.MTD.1145 | RO l MT Delivery for CCTV system components | 28 | 0.034138 | 2026-11-16 | 2026-12-13 | 0% | 0% | 0% | 0%
External Improvement Material Delivery and Fabrication |  | 55 |  | 2026-09-23 | 2026-11-16
PR.RO.D32.MTD.1155 | RO l MT Delivery for Precast concrete paving | 35 | 0.014234 | 2026-10-12 | 2026-11-15 | 0% | 0% | 0% | 0%
PR.RO.D32.MTD.1160 | RO l MT Delivery for Precast concrete wall | 55 | 0.053703 | 2026-09-23 | 2026-11-16 | 0% | 0% | 0% | 0%
Long Lead Item |  | 250 |  | 2026-04-19 | 2026-12-24
RO Plant Material Submittal - Long Lead |  | 114 |  | 2026-04-19 | 2026-09-01
Finishes Material Submittal |  | 95 |  | 2026-05-06 | 2026-08-27
PR.RO.D05.MTS.1165 | RO l MT Submission for Structural steel | 35 | 0.034706 | 2026-05-06 | 2026-06-18 | 0% | 100% | 0% | 100%
PR.RO.D08.MTS.1175 | RO l MT Submission for Acoustic & Fire rated doors | 30 | 0.0080848 | 2026-06-20 | 2026-07-23 | 0% | 75% | 0% | 75% |  | waiting PQD Approval
PR.RO.D07.MTS.1170 | RO l MT Submission for Aluminium cladding | 30 | 0.060338 | 2026-07-25 | 2026-08-27 | 0% | 100% | 0% | 100%
Elevator Material Submittal |  | 22 |  | 2026-07-19 | 2026-08-12
PR.RO.D14.MTS.1180 | RO l MT Submission for Elevators | 22 | 0.0070024 | 2026-07-19 | 2026-08-12 | 0% | 100% | 0% | 100%
Fire Supperssion Material Submittal |  | 84 |  | 2026-05-24 | 2026-09-01
PR.RO.D21.MTS.1185 | RO l MT Submission for Fire Suppression equipment | 28 | 0.10193 | 2026-05-24 | 2026-06-28 | 0% | 100% | 0% | 100%
PR.RO.D21.MTS.1190 | RO l MT Submission for Foam Water system | 28 | 0.02327 | 2026-06-29 | 2026-07-30 | 0% | 100% | 0% | 100%
PR.RO.D21.MTS.1195 | RO l MT Submission for Clean Agent FK-5.1.12 System | 28 | 0.10557 | 2026-08-01 | 2026-09-01 | 0% | 100% | 0% | 100%
Plumbing Material Submittal |  | 60 |  | 2026-04-19 | 2026-06-30
PR.RO.D22.MTS.1200 | RO l MT Submission for Plumping equipment | 30 | 0.12186 | 2026-04-19 | 2026-05-23 | 0% | 100% | 0% | 100%
PR.RO.D22.MTS.1205 | RO l MT Submission for R&T Equipments & valves | 30 | 0.0935 | 2026-05-24 | 2026-06-30 | 0% | 100% | 0% | 100%
HVAC System Material Submittal |  | 48 |  | 2026-06-20 | 2026-08-13
PR.RO.D23.MTS.1220 | RO l MT Submission for Split & Fan coil Units & Exhaust Fans | 24 | 0.015125 | 2026-06-20 | 2026-07-16 | 0% | 100% | 0% | 100%
PR.RO.D23.MTS.1215 | RO l MT Submission for Air Handlig Units | 28 | 0.081899 | 2026-07-01 | 2026-08-02 | 0% | 100% | 0% | 100%
PR.RO.D23.MTS.1210 | RO l MT Submission for HVAC equipment | 24 | 0.11598 | 2026-07-18 | 2026-08-13 | 0% | 100% | 0% | 100%
Electrical System Material Submittal |  | 76 |  | 2026-05-24 | 2026-08-23
PR.RO.D26.MTS.1235 | RO l MT Submission for Diesel Generators | 21 | 0.16254 | 2026-05-24 | 2026-06-20 | 0% | 100% | 0% | 100%
PR.RO.D26.MTS.1225 | RO l MT Submission for Meduim-Voltage switchgear | 24 | 0.074199 | 2026-06-21 | 2026-07-18 | 100% | 100% | 0% | 100%
PR.RO.D26.MTS.1230 | RO l MT Submission for Meduim-Voltage Transformers | 24 | 0.022557 | 2026-06-21 | 2026-07-18 | 100% | 100% | 0% | 100%
PR.RO.D26.MTS.1250 | RO l MT Submission for Low voltage electrical cables | 18 | 0.096629 | 2026-07-01 | 2026-07-21 | 0% | 100% | 0% | 100%
PR.RO.D26.MTS.1245 | RO l MT Submission for Lightning & Earthing | 18 | 0.0094044 | 2026-07-22 | 2026-08-11 | 0% | 100% | 0% | 100%
PR.RO.D26.MTS.1255 | RO l MT Submission for Lighting system | 21 | 0.031317 | 2026-07-22 | 2026-08-15 | 0% | 100% | 0% | 100%
PR.RO.D26.MTS.1240 | RO l MT Submission for Main distribution board (MDB) | 28 | 0.030913 | 2026-07-22 | 2026-08-23 | 100% | 100% | 0% | 100% |  | Waiting Al Fanar Calculation
Special System Material Submittal |  | 56 |  | 2026-04-23 | 2026-06-30
PR.RO.D33.MTS.1260 | RO l MT Submission for Brackish Water Reverse Osmosis Plant | 37 | 1.0051 | 2026-04-23 | 2026-06-08 | 0% | 100% | 0% | 100%
PR.RO.D40.MTS.1265 | RO l MT Submission for Process scada system and intrumentation | 30 | 0.097974 | 2026-05-24 | 2026-06-30 | 0% | 100% | 0% | 100%
RO Plant Material Approval - Long Lead |  | 84 |  | 2026-05-24 | 2026-09-21
Finishes Material Approval |  | 64 |  | 2026-06-21 | 2026-09-16
PR.RO.D05.MTA.1165 | RO l MT Approval for Structural steel | 14 | 0.034706 | 2026-06-21 | 2026-07-08 | 0% | 100% | 0% | 100%
PR.RO.D08.MTA.1175 | RO l MT Approval for Acoustic & Fire rated doors | 14 | 0.0080848 | 2026-07-26 | 2026-08-12 | 0% | 0% | 0% | 0% |  | Under Review
PR.RO.D07.MTA.1170 | RO l MT Approval for Aluminium cladding | 14 | 0.060338 | 2026-08-30 | 2026-09-16 | 0% | 90% | 0% | 90%
Elevator Material Approval |  | 14 |  | 2026-08-13 | 2026-09-01
PR.RO.D14.MTA.1180 | RO l MT Approval for Elevators | 14 | 0.0070024 | 2026-08-13 | 2026-09-01 | 0% | 100% | 0% | 100%
Fire Supperssion Material Approval |  | 61 |  | 2026-06-29 | 2026-09-21
PR.RO.D21.MTA.1185 | RO l MT Approval for Fire Suppression equipment | 14 | 0.10193 | 2026-06-29 | 2026-07-16 | 0% | 100% | 0% | 100%
PR.RO.D21.MTA.1190 | RO l MT Approval for Foam Water system | 14 | 0.02327 | 2026-08-02 | 2026-08-19 | 0% | 100% | 0% | 100%
PR.RO.D21.MTA.1195 | RO l MT Approval for Clean Agent FK-5.1.12 System | 14 | 0.10557 | 2026-09-02 | 2026-09-21 | 0% | 100% | 0% | 100%
Plumbing Material Approval |  | 39 |  | 2026-05-24 | 2026-07-20
PR.RO.D22.MTA.1200 | RO l MT Approval for Plumping equipment | 14 | 0.12186 | 2026-05-24 | 2026-06-15 | 0% | 100% | 0% | 100%
PR.RO.D22.MTA.1205 | RO l MT Approval for R&T Equipments & valves | 14 | 0.0935 | 2026-07-01 | 2026-07-20 | 0% | 100% | 0% | 100% |  | Automatic screen remaining
HVAC System Material Approval |  | 34 |  | 2026-07-19 | 2026-09-02
PR.RO.D23.MTA.1220 | RO l MT Approval for Split & Fan coil Units & Exhaust Fans | 14 | 0.015125 | 2026-07-19 | 2026-08-05 | 0% | 100% | 0% | 100%
PR.RO.D23.MTA.1215 | RO l MT Approval for Air Handlig Units | 14 | 0.081899 | 2026-08-03 | 2026-08-20 | 0% | 100% | 0% | 100%
PR.RO.D23.MTA.1210 | RO l MT Approval for HVAC equipment | 14 | 0.11598 | 2026-08-16 | 2026-09-02 | 0% | 100% | 0% | 100%
Electrical System Material Approval |  | 60 |  | 2026-06-21 | 2026-09-10
PR.RO.D26.MTA.1235 | RO l MT Approval for Diesel Generators | 14 | 0.16254 | 2026-06-21 | 2026-07-08 | 100% | 95% | 0% | 95% |  | Waiting Supplier to Review
PR.RO.D26.MTA.1225 | RO l MT Approval for Meduim-Voltage switchgear | 14 | 0.074199 | 2026-07-19 | 2026-08-05 | 100% | 70% | 0% | 70% |  | Approved | Manufacturing DWG still not submitted
PR.RO.D26.MTA.1230 | RO l MT Approval for Meduim-Voltage Transformers | 14 | 0.022557 | 2026-07-19 | 2026-08-05 | 100% | 100% | 0% | 100% |  | Approved | Manufacturing DWG still not submitted
PR.RO.D26.MTA.1250 | RO l MT Approval for Low voltage electrical cables | 14 | 0.096629 | 2026-07-22 | 2026-08-10 | 0% | 100% | 0% | 100%
PR.RO.D26.MTA.1245 | RO l MT Approval for Lightning & Earthing | 14 | 0.0094044 | 2026-08-12 | 2026-08-31 | 0% | 100% | 0% | 100%
PR.RO.D26.MTA.1255 | RO l MT Approval for Lighting system | 14 | 0.031317 | 2026-08-16 | 2026-09-02 | 0% | 100% | 0% | 100%
PR.RO.D26.MTA.1240 | RO l MT Approval for Main distribution board (MDB) | 14 | 0.030913 | 2026-08-24 | 2026-09-10 | 100% | 20% | 0% | 20%
Special System Material Approval |  | 30 |  | 2026-06-09 | 2026-07-20
PR.RO.D33.MTA.1260 | RO l MT Approval for Brackish Water Reverse Osmosis Plant | 14 | 1.0051 | 2026-06-09 | 2026-06-28 | 0% | 100% | 0% | 100%
PR.RO.D40.MTA.1265 | RO l MT Approval for Process scada system and intrumentation | 14 | 0.097974 | 2026-07-01 | 2026-07-20 | 0% | 100% | 0% | 100%
RO Plant Material PO - Long Lead |  | 104 |  | 2026-06-16 | 2026-10-15
Finishes Material PO |  | 76 |  | 2026-07-09 | 2026-10-06
PR.RO.D05.MPO.1165 | RO l PO Placement for Structural steel | 20 | 0.10412 | 2026-07-09 | 2026-08-01 | 0% | 100% | 0% | 100%
PR.RO.D08.MPO.1175 | RO l PO Placement for Acoustic & Fire rated doors | 22 | 0.024254 | 2026-08-13 | 2026-09-07 | 0% | 100% | 0% | 100%
PR.RO.D07.MPO.1170 | RO l PO Placement for Aluminium cladding | 16 | 0.18101 | 2026-09-17 | 2026-10-06 | 0% | 100% | 0% | 100%
Elevator Material PO |  | 24 |  | 2026-09-02 | 2026-09-30
PR.RO.D14.MPO.1180 | RO l PO Placement for Elevators | 24 | 0.021007 | 2026-09-02 | 2026-09-30 | 0% | 100% | 0% | 100%
Fire Supperssion Material PO |  | 77 |  | 2026-07-18 | 2026-10-15
PR.RO.D21.MPO.1185 | RO l PO Placement for Fire Suppression equipment | 24 | 0.20385 | 2026-07-18 | 2026-08-13 | 0% | 100% | 0% | 100%
PR.RO.D21.MPO.1190 | RO l PO Placement for Foam Water system | 22 | 0.046541 | 2026-08-20 | 2026-09-14 | 100% | 100% | 0% | 100%
PR.RO.D21.MPO.1195 | RO l PO Placement for Clean Agent FK-5.1.12 System | 20 | 0.21114 | 2026-09-22 | 2026-10-15 | 0% | 100% | 0% | 100%
Plumbing Material PO |  | 60 |  | 2026-06-16 | 2026-08-24
PR.RO.D22.MPO.1200 | RO l PO Placement for Plumping equipment | 30 | 0.24372 | 2026-06-16 | 2026-07-20 | 0% | 100% | 0% | 100%
PR.RO.D22.MPO.1205 | RO l PO Placement for R&T Equipments & valves | 30 | 0.187 | 2026-07-21 | 2026-08-24 | 0% | 100% | 0% | 100%
HVAC System Material PO |  | 49 |  | 2026-08-06 | 2026-10-03
PR.RO.D23.MPO.1220 | RO l PO Placement for Split & Fan coil Units & Exhaust Fans | 25 | 0.03025 | 2026-08-06 | 2026-09-03 | 0% | 100% | 0% | 100%
PR.RO.D23.MPO.1215 | RO l PO Placement for Air Handlig Units | 25 | 0.1638 | 2026-08-22 | 2026-09-19 | 0% | 100% | 0% | 100%
PR.RO.D23.MPO.1210 | RO l PO Placement for HVAC equipment | 25 | 0.23196 | 2026-09-03 | 2026-10-03 | 0% | 100% | 0% | 100%
Electrical System Material PO |  | 83 |  | 2026-07-09 | 2026-10-14
PR.RO.D26.MPO.1235 | RO l PO Placement for Diesel Generators | 25 | 0.32508 | 2026-07-09 | 2026-08-06 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1225 | RO l PO Placement for Meduim-Voltage switchgear | 20 | 0.1484 | 2026-08-06 | 2026-08-29 | 100% | 100% | 0% | 100% |  | Issued
PR.RO.D26.MPO.1250 | RO l PO Placement for Low voltage electrical cables | 18 | 0.28989 | 2026-08-11 | 2026-08-31 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1230 | RO l PO Placement for Meduim-Voltage Transformers | 28 | 0.045115 | 2026-08-06 | 2026-09-07 | 100% | 100% | 0% | 100% |  | Issued
PR.RO.D26.MPO.1245 | RO l PO Placement for Lightning & Earthing | 18 | 0.028213 | 2026-09-01 | 2026-09-21 | 100% | 100% | 0% | 100%
PR.RO.D26.MPO.1255 | RO l PO Placement for Lighting system | 20 | 0.093952 | 2026-09-03 | 2026-09-27 | 0% | 100% | 0% | 100%
PR.RO.D26.MPO.1240 | RO l PO Placement for Main distribution board (MDB) | 28 | 0.061825 | 2026-09-12 | 2026-10-14 | 0% | 100% | 0% | 100%
Special System Material PO |  | 55 |  | 2026-06-29 | 2026-08-31
PR.RO.D40.MPO.1265 | RO l PO Placement for Process scada system and intrumentation | 20 | 0.19595 | 2026-07-21 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.RO.D33.MPO.1260 | RO l PO Placement for Brackish Water Reverse Osmosis Plant | 55 | 2.0101 | 2026-06-29 | 2026-08-31 | 0% | 100% | 0% | 100%
RO Plant Material Delivery and Fabrication - Long Lead |  | 157 |  | 2026-07-21 | 2026-12-24
Finishes Material Delivery and Fabrication |  | 116 |  | 2026-08-02 | 2026-11-25
PR.RO.D05.MTD.1165 | RO l MT Delivery for Structural steel | 70 | 0.17353 | 2026-08-02 | 2026-10-10 | 0% | 0% | 0% | 0%
PR.RO.D08.MTD.1175 | RO l MT Delivery for Acoustic & Fire rated doors | 50 | 0.040424 | 2026-09-08 | 2026-10-27 | 0% | 0% | 0% | 0%
PR.RO.D07.MTD.1170 | RO l MT Delivery for Aluminium cladding | 50 | 0.30169 | 2026-10-07 | 2026-11-25 | 0% | 0% | 0% | 0%
Elevator Material Delivery and Fabrication |  | 65 |  | 2026-10-01 | 2026-12-04
PR.RO.D14.MTD.1180 | RO l MT Delivery for Elevators | 65 | 0.035012 | 2026-10-01 | 2026-12-04 | 0% | 0% | 0% | 0%
Fire Supperssion Material Delivery and Fabrication |  | 133 |  | 2026-08-14 | 2026-12-24
PR.RO.D21.MTD.1185 | RO l MT Delivery for Fire Suppression equipment | 65 | 0.27181 | 2026-08-14 | 2026-10-17 | 0% | 0% | 0% | 0%
PR.RO.D21.MTD.1190 | RO l MT Delivery for Foam Water system | 65 | 0.062054 | 2026-09-15 | 2026-11-18 | 0% | 0% | 0% | 0%
PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System | 70 | 0.28151 | 2026-10-16 | 2026-12-24 | 0% | 0% | 0% | 0%
Plumbing Material Delivery and Fabrication |  | 105 |  | 2026-07-21 | 2026-11-02
PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment | 90 | 0.32497 | 2026-07-21 | 2026-10-18 | 7.78% | 0% | 12% | 12% |  | Wating Storage Preparation
PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves | 70 | 0.24933 | 2026-08-25 | 2026-11-02 | 0% | 0% | 0% | 0%
HVAC System Material Delivery and Fabrication |  | 80 |  | 2026-09-04 | 2026-11-22
PR.RO.D23.MTD.1220 | RO l MT Delivery for Split & Fan coil Units & Exhaust Fans | 50 | 0.040333 | 2026-09-04 | 2026-10-23 | 14% | 0% | 35% | 35%
PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units | 60 | 0.2184 | 2026-09-20 | 2026-11-18 | 70% | 95% | 5% | 100%
PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment | 50 | 0.30928 | 2026-10-04 | 2026-11-22 | 0% | 0% | 0% | 0%
Electrical System Material Delivery and Fabrication |  | 122 |  | 2026-08-07 | 2026-12-06
PR.RO.D26.MTD.1250 | RO l MT Delivery for Low voltage electrical cables | 40 | 0.48315 | 2026-09-01 | 2026-10-10 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1245 | RO l MT Delivery for Lightning & Earthing | 40 | 0.047022 | 2026-09-22 | 2026-10-31 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1235 | RO l MT Delivery for Diesel Generators | 90 | 0.43344 | 2026-08-07 | 2026-11-04 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1255 | RO l MT Delivery for Lighting system | 40 | 0.15659 | 2026-09-28 | 2026-11-06 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1240 | RO l MT Delivery for Main distribution board (MDB) | 35 | 0.082434 | 2026-10-15 | 2026-11-18 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1225 | RO l MT Delivery for Meduim-Voltage switchgear | 90 | 0.19786 | 2026-08-30 | 2026-11-27 | 0% | 0% | 0% | 0%
PR.RO.D26.MTD.1230 | RO l MT Delivery for Meduim-Voltage Transformers | 90 | 0.060153 | 2026-09-08 | 2026-12-06 | 0% | 0% | 0% | 0%
Special System Material Delivery and Fabrication |  | 110 |  | 2026-08-13 | 2026-11-30
PR.RO.D40.MTD.1265 | RO l MT Delivery for Process scada system and intrumentation | 60 | 0.26126 | 2026-08-13 | 2026-10-11 | 0% | 0% | 0% | 0%
PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant | 91 | 2.6802 | 2026-09-01 | 2026-11-30 | 0% | 41.12% | 0% | 41.12% |  | The material under manufacturing /To be verified by KAFD
Pump-Station |  | 319 |  | 2026-02-01 | 2026-12-16
Short Lead Items |  | 254 |  | 2026-02-01 | 2026-10-12
Pump-Station Material Submittal - Short Lead |  | 162 |  | 2026-02-01 | 2026-08-16
Structural Material Submittal |  | 30 |  | 2026-02-01 | 2026-03-08
PR.PS.D31.MTS.1005 | IPS l MT Submission for Reinforced piles | 16 | 0.0047193 | 2026-02-01 | 2026-02-18 | 18.75% | 100% | 0% | 100%
PR.PS.D07.MTS.1000 | IPS l MT Submission for Thermal & Moisture insulation | 14 | 0.00089158 | 2026-02-19 | 2026-03-08 | 0% | 100% | 0% | 100%
Finishes Material Submittal |  | 84 |  | 2026-04-23 | 2026-08-02
PR.PS.D04.MTS.1010 | IPS l MT Submission for Masonry | 20 | 0.00029111 | 2026-04-23 | 2026-05-16 | 0% | 100% | 0% | 100%
PR.PS.D07.MTS.1020 | IPS l MT Submission for Aluminum cladding | 18 | 0.0011306 | 2026-05-17 | 2026-06-09 | 0% | 50% | 50% | 100% |  | KAFD-636-SBC-ARC-MAR-00014 Submittied | Related to RO, not IPS
PR.PS.D13.MTS.1035 | IPS l MT Submission for Aluminium Control booths | 16 | 0.00027363 | 2026-06-10 | 2026-06-28 | 100% | 100% | 0% | 100%
PR.PS.D08.MTS.1030 | IPS l MT Submission for Aluminium louvers | 18 | 0.00019085 | 2026-06-10 | 2026-06-30 | 100% | 100% | 0% | 100% |  | This Item is not applicable
PR.PS.D07.MTS.1025 | IPS l MT Submission for Terrazzo Tiles | 16 | 7.2259e-05 | 2026-07-01 | 2026-07-19 | 100% | 100% | 0% | 100%
PR.PS.D05.MTS.1015 | IPS l MT Submission for Trench covers | 12 | 0.00084208 | 2026-07-20 | 2026-08-02 | 100% | 100% | 0% | 100%
Plumbing Material Submittal |  | 36 |  | 2026-03-09 | 2026-04-22
PR.PS.D22.MTS.1045 | IPS l MT Submission for Domestic Water Piping GRP | 18 | 0.00095387 | 2026-03-09 | 2026-04-01 | 0% | 100% | 0% | 100%
PR.PS.D22.MTS.1040 | IPS l MT Submission for Plumbing valves | 18 | 0.0040502 | 2026-04-02 | 2026-04-22 | 0% | 100% | 0% | 100%
Low Current Material Submittal |  | 20 |  | 2026-05-17 | 2026-06-11
PR.PS.D27.MTS.1050 | IPS l MT Submission for Communication System | 20 | 0.0035663 | 2026-05-17 | 2026-06-11 | 0% | 100% | 0% | 100%
Security Material Submittal |  | 18 |  | 2026-06-13 | 2026-07-02
PR.PS.D28.MTS.1055 | IPS l MT Submission for Access control components | 18 | 0.00028416 | 2026-06-13 | 2026-07-02 | 0% | 100% | 0% | 100%
PR.PS.D28.MTS.1060 | IPS l MT Submission for CCTV system components | 18 | 0.00036099 | 2026-06-13 | 2026-07-02 | 0% | 100% | 0% | 100%
PR.PS.D28.MTS.1065 | IPS l MT Submission for Fire alarm system | 18 | 0.00052591 | 2026-06-13 | 2026-07-02 | 0% | 100% | 0% | 100%
External Improvement Material Submittal |  | 24 |  | 2026-07-20 | 2026-08-16
PR.PS.D32.MTS.1070 | IPS l MT Submission for concrete paving | 12 | 0.00062122 | 2026-07-20 | 2026-08-02 | 50% | 0% | 95% | 95% |  | Samples Provided
PR.PS.D32.MTS.1075 | IPS l MT Submission for Planting | 12 | 0.0011053 | 2026-08-03 | 2026-08-16 | 0% | 0% | 100% | 100% |  | Waiting Supplier
Pump-Station Material Approval - Short Lead |  | 134 |  | 2026-02-19 | 2026-09-03
Structural Material Approval |  | 25 |  | 2026-02-19 | 2026-03-31
PR.PS.D31.MTA.1005 | IPS l MT Approval for Reinforced piles | 14 | 0.0047193 | 2026-02-19 | 2026-03-11 | 0% | 100% | 0% | 100%
PR.PS.D07.MTA.1000 | IPS l MT Approval for Thermal & Moisture insulation | 14 | 0.00089158 | 2026-03-09 | 2026-03-31 | 0% | 100% | 0% | 100% |  | KAFD-636-SBC-ARC-MAR-00019 KAFD-636-SBC-CIV-MAR-00036 KAFD-636-SBC-CIV-MAR-00099 KAFD-636-SBC-CIV-MAR-00101 KAFD-636-SBC-CIV-MAR-00103 KAFD-636-SBC-CIV-MAR-00006
Finishes Material Approval |  | 67 |  | 2026-05-17 | 2026-08-20
PR.PS.D04.MTA.1010 | IPS l MT Approval for Masonry | 14 | 0.00029111 | 2026-05-17 | 2026-06-08 | 0% | 100% | 0% | 100% |  | KAFD-636-SBC-CIV-MAR-00028
PR.PS.D07.MTA.1020 | IPS l MT Approval for Aluminum cladding | 14 | 0.0011306 | 2026-06-10 | 2026-06-29 | 0% | 0% | 100% | 100% |  | KAFD-636-SBC-ARC-MAR-00014 | Related to RO, not IPS
PR.PS.D13.MTA.1035 | IPS l MT Approval for Aluminium Control booths | 14 | 0.00027363 | 2026-06-29 | 2026-07-16 | 100% | 100% | 0% | 100%
PR.PS.D08.MTA.1030 | IPS l MT Approval for Aluminium louvers | 14 | 0.00019085 | 2026-07-01 | 2026-07-20 | 100% | 100% | 0% | 100% |  | Code C Waiting Sedra to provide sub supplier PQD
PR.PS.D07.MTA.1025 | IPS l MT Approval for Terrazzo Tiles | 14 | 7.2259e-05 | 2026-07-20 | 2026-08-06 | 100% | 100% | 0% | 100% |  | Waiting Samples
PR.PS.D05.MTA.1015 | IPS l MT Approval for Trench covers | 14 | 0.00084208 | 2026-08-03 | 2026-08-20 | 0% | 0% | 0% | 0% |  | PO in progres
Plumbing Material Approval |  | 29 |  | 2026-04-02 | 2026-05-12
PR.PS.D22.MTA.1045 | IPS l MT Approval for Domestic Water Piping GRP | 14 | 0.00095387 | 2026-04-02 | 2026-04-21 | 0% | 100% | 0% | 100%
PR.PS.D22.MTA.1040 | IPS l MT Approval for Plumbing valves | 14 | 0.0040502 | 2026-04-23 | 2026-05-12 | 0% | 100% | 0% | 100%
Low Current Material Approval |  | 14 |  | 2026-06-14 | 2026-07-01
PR.PS.D27.MTA.1050 | IPS l MT Approval for Communication System | 14 | 0.0035663 | 2026-06-14 | 2026-07-01 | 0% | 100% | 0% | 100%
Security Material Approval |  | 14 |  | 2026-07-05 | 2026-07-22
PR.PS.D28.MTA.1055 | IPS l MT Approval for Access control components | 14 | 0.00028416 | 2026-07-05 | 2026-07-22 | 0% | 0% | 0% | 0% |  | waiting approval from KAFD
PR.PS.D28.MTA.1060 | IPS l MT Approval for CCTV system components | 14 | 0.00036099 | 2026-07-05 | 2026-07-22 | 0% | 0% | 0% | 0% |  | waiting approval from KAFD
PR.PS.D28.MTA.1065 | IPS l MT Approval for Fire alarm system | 14 | 0.00052591 | 2026-07-05 | 2026-07-22 | 0% | 100% | 0% | 100%
External Improvement Material Approval |  | 24 |  | 2026-08-03 | 2026-09-03
PR.PS.D32.MTA.1070 | IPS l MT Approval for concrete paving | 14 | 0.00062122 | 2026-08-03 | 2026-08-20 | 100% | 80% | 15% | 95%
PR.PS.D32.MTA.1075 | IPS l MT Approval for Planting | 14 | 0.0011053 | 2026-08-17 | 2026-09-03 | 0% | 0% | 0% | 0%
Pump-Station Material PO - Short Lead |  | 161 |  | 2026-03-12 | 2026-09-22
Structural Material PO |  | 29 |  | 2026-03-12 | 2026-04-18
PR.PS.D31.MPO.1005 | IPS l PO Placement for Reinforced piles | 15 | 0.0094386 | 2026-03-12 | 2026-04-01 | 0% | 100% | 0% | 100%
PR.PS.D07.MPO.1000 | IPS l PO Placement for Thermal & Moisture insulation | 15 | 0.0017832 | 2026-04-01 | 2026-04-18 | 0% | 100% | 0% | 100%
Finishes Material PO |  | 78 |  | 2026-06-09 | 2026-09-07
PR.PS.D04.MPO.1010 | IPS l PO Placement for Masonry | 16 | 0.00058223 | 2026-06-09 | 2026-06-27 | 0% | 100% | 0% | 100%
PR.PS.D07.MPO.1020 | IPS l PO Placement for Aluminum cladding | 18 | 0.0022612 | 2026-06-30 | 2026-07-20 | 0% | 100% | 0% | 100%
PR.PS.D13.MPO.1035 | IPS l PO Placement for Aluminium Control booths | 16 | 0.00054726 | 2026-07-18 | 2026-08-04 | 0% | 100% | 0% | 100%
PR.PS.D08.MPO.1030 | IPS l PO Placement for Aluminium louvers | 18 | 0.00038171 | 2026-07-21 | 2026-08-10 | 0% | 100% | 0% | 100%
PR.PS.D07.MPO.1025 | IPS l PO Placement for Terrazzo Tiles | 15 | 0.00014452 | 2026-08-08 | 2026-08-24 | 40% | 0% | 100% | 100% |  | Wating Samples from supplier
PR.PS.D05.MPO.1015 | IPS l PO Placement for Trench covers | 15 | 0.0016842 | 2026-08-22 | 2026-09-07 | 0% | 100% | 0% | 100%
Plumbing Material PO |  | 36 |  | 2026-04-22 | 2026-06-06
PR.PS.D22.MPO.1045 | IPS l PO Placement for Domestic Water Piping GRP | 20 | 0.0019077 | 2026-04-22 | 2026-05-14 | 0% | 100% | 0% | 100%
PR.PS.D22.MPO.1040 | IPS l PO Placement for Plumbing valves | 18 | 0.0081005 | 2026-05-13 | 2026-06-06 | 0% | 100% | 0% | 100%
Low Current Material PO |  | 20 |  | 2026-07-02 | 2026-07-25
PR.PS.D27.MPO.1050 | IPS l PO Placement for Communication System | 20 | 0.0071326 | 2026-07-02 | 2026-07-25 | 0% | 100% | 0% | 100%
Security Material PO |  | 18 |  | 2026-07-23 | 2026-08-12
PR.PS.D28.MPO.1055 | IPS l PO Placement for Access control components | 18 | 0.00056831 | 2026-07-23 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.PS.D28.MPO.1060 | IPS l PO Placement for CCTV system components | 18 | 0.00072198 | 2026-07-23 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.PS.D28.MPO.1065 | IPS l PO Placement for Fire alarm system | 18 | 0.0010518 | 2026-07-23 | 2026-08-12 | 0% | 100% | 0% | 100%
External Improvement Material PO |  | 28 |  | 2026-08-22 | 2026-09-22
PR.PS.D32.MPO.1070 | IPS l PO Placement for concrete paving | 16 | 0.0012424 | 2026-08-22 | 2026-09-08 | 0% | 100% | 0% | 100%
PR.PS.D32.MPO.1075 | IPS l PO Placement for Planting | 16 | 0.0022106 | 2026-09-05 | 2026-09-22 | 0% | 0% | 100% | 100%
Pump-Station Material Delivery and Fabrication - Short Lead |  | 194 |  | 2026-04-02 | 2026-10-12
Structural Material Delivery and Fabrication |  | 35 |  | 2026-04-02 | 2026-05-06
PR.PS.D31.MTD.1005 | IPS l MT Delivery for Reinforced piles | 20 | 0.028316 | 2026-04-02 | 2026-04-21 | 0% | 100% | 0% | 100%
PR.PS.D07.MTD.1000 | IPS l MT Delivery for Thermal & Moisture insulation | 18 | 0.0053495 | 2026-04-19 | 2026-05-06 | 0% | 95% | 0% | 95% |  | delivered
Finishes Material Delivery and Fabrication |  | 90 |  | 2026-06-28 | 2026-09-25
PR.PS.D04.MTD.1010 | IPS l MT Delivery for Masonry | 16 | 0.0017467 | 2026-06-28 | 2026-07-13 | 100% | 100% | 0% | 100%
PR.PS.D07.MTD.1020 | IPS l MT Delivery for Aluminum cladding | 18 | 0.0067835 | 2026-07-21 | 2026-08-07 | 0% | 0% | 0% | 0% |  | MAR under review
PR.PS.D13.MTD.1035 | IPS l MT Delivery for Aluminium Control booths | 15 | 0.0016418 | 2026-08-05 | 2026-08-19 | 100% | 100% | 0% | 100% |  | MAR under review
PR.PS.D08.MTD.1030 | IPS l MT Delivery for Aluminium louvers | 20 | 0.0011451 | 2026-08-11 | 2026-08-30 | 100% | 100% | 0% | 100% |  | MAR under review
PR.PS.D07.MTD.1025 | IPS l MT Delivery for Terrazzo Tiles | 18 | 0.00043355 | 2026-08-25 | 2026-09-11 | 0% | 100% | 0% | 100%
PR.PS.D05.MTD.1015 | IPS l MT Delivery for Trench covers | 18 | 0.0050525 | 2026-09-08 | 2026-09-25 | 0% | 0% | 0% | 0%
Plumbing Material Delivery and Fabrication |  | 43 |  | 2026-05-15 | 2026-06-26
PR.PS.D22.MTD.1045 | IPS l MT Delivery for Domestic Water Piping GRP | 16 | 0.0057232 | 2026-05-15 | 2026-05-30 | 0% | 100% | 0% | 100%
PR.PS.D22.MTD.1040 | IPS l MT Delivery for Plumbing valves | 20 | 0.024301 | 2026-06-07 | 2026-06-26 | 0% | 0% | 0% | 0% |  | to be delivered on 27-8-2026
Low Current Material Delivery and Fabrication |  | 20 |  | 2026-07-26 | 2026-08-14
PR.PS.D27.MTD.1050 | IPS l MT Delivery for Communication System | 20 | 0.021398 | 2026-07-26 | 2026-08-14 | 35% | 0% | 5% | 5% |  | Telephone Delivered
Security Material Delivery and Fabrication |  | 20 |  | 2026-08-13 | 2026-09-01
PR.PS.D28.MTD.1055 | IPS l MT Delivery for Access control components | 20 | 0.0017049 | 2026-08-13 | 2026-09-01 | 0% | 0% | 0% | 0%
PR.PS.D28.MTD.1060 | IPS l MT Delivery for CCTV system components | 20 | 0.0021659 | 2026-08-13 | 2026-09-01 | 0% | 0% | 0% | 0%
PR.PS.D28.MTD.1065 | IPS l MT Delivery for Fire alarm system | 20 | 0.0031555 | 2026-08-13 | 2026-09-01 | 100% | 80% | 0% | 80% |  | Delivered
External Improvement Material Delivery and Fabrication |  | 34 |  | 2026-09-09 | 2026-10-12
PR.PS.D32.MTD.1070 | IPS l MT Delivery for concrete paving | 15 | 0.0037273 | 2026-09-09 | 2026-09-23 | 0% | 0% | 0% | 0%
PR.PS.D32.MTD.1075 | IPS l MT Delivery for Planting | 20 | 0.0066318 | 2026-09-23 | 2026-10-12 | 0% | 0% | 0% | 0%
Long Lead Item |  | 259 |  | 2026-04-02 | 2026-12-16
Pump-Station Material Submittal - Long Lead |  | 112 |  | 2026-04-02 | 2026-08-13
Fire Supperssion Material Submittal |  | 20 |  | 2026-05-17 | 2026-06-11
PR.PS.D21.MTS.1080 | IPS l MT Submission for Clean Agent FK-5.1.12 cylinders | 20 | 0.011902 | 2026-05-17 | 2026-06-11 | 0% | 100% | 0% | 100%
Plumbing Material Submittal |  | 26 |  | 2026-04-02 | 2026-05-02
PR.PS.D22.MTS.1085 | IPS l MT Submission for Submersible pumps | 26 | 0.0049902 | 2026-04-02 | 2026-05-02 | 0% | 100% | 0% | 100%
HVAC System Material Submittal |  | 24 |  | 2026-05-17 | 2026-06-16
PR.PS.D23.MTS.1090 | IPS l MT Submission for HVAC System | 24 | 0.011395 | 2026-05-17 | 2026-06-16 | 0% | 100% | 0% | 100%
Electrical System Material Submittal |  | 54 |  | 2026-05-17 | 2026-07-21
PR.PS.D26.MTS.1100 | IPS l MT Submission for Low voltage electrical cables | 18 | 0.0037658 | 2026-05-17 | 2026-06-09 | 0% | 100% | 0% | 100%
PR.PS.D26.MTS.1095 | IPS l MT Submission for Panel boards | 20 | 0.012743 | 2026-06-10 | 2026-07-02 | 100% | 100% | 0% | 100%
PR.PS.D26.MTS.1105 | IPS l MT Submission for Lighting fixtures | 16 | 0.011475 | 2026-07-04 | 2026-07-21 | 0% | 100% | 0% | 100%
Special System Material Submittal |  | 20 |  | 2026-07-22 | 2026-08-13
PR.PS.D40.MTS.1110 | IPS l MT Submission for SCADA | 20 | 0.042429 | 2026-07-22 | 2026-08-13 | 0% | 100% | 0% | 100%
Pump-Station Material Approval - Long Lead |  | 86 |  | 2026-05-03 | 2026-09-02
Fire Supperssion Material Approval |  | 14 |  | 2026-06-14 | 2026-07-01
PR.PS.D21.MTA.1080 | IPS l MT Approval for Clean Agent FK-5.1.12 cylinders | 14 | 0.011902 | 2026-06-14 | 2026-07-01 | 0% | 100% | 0% | 100%
Plumbing Material Approval |  | 14 |  | 2026-05-03 | 2026-05-20
PR.PS.D22.MTA.1085 | IPS l MT Approval for Submersible pumps | 14 | 0.0049902 | 2026-05-03 | 2026-05-20 | 0% | 100% | 0% | 100%
HVAC System Material Approval |  | 14 |  | 2026-06-17 | 2026-07-06
PR.PS.D23.MTA.1090 | IPS l MT Approval for HVAC System | 14 | 0.011395 | 2026-06-17 | 2026-07-06 | 0% | 100% | 0% | 100%
Electrical System Material Approval |  | 44 |  | 2026-06-10 | 2026-08-10
PR.PS.D26.MTA.1100 | IPS l MT Approval for Low voltage electrical cables | 14 | 0.0037658 | 2026-06-10 | 2026-06-29 | 0% | 100% | 0% | 100%
PR.PS.D26.MTA.1095 | IPS l MT Approval for Panel boards | 14 | 0.012743 | 2026-07-05 | 2026-07-22 | 100% | 20% | 0% | 20% |  | waiting response from manufacturer alfanar
PR.PS.D26.MTA.1105 | IPS l MT Approval for Lighting fixtures | 14 | 0.011475 | 2026-07-22 | 2026-08-10 | 0% | 80% | 0% | 80% |  | items remaining 4 item only. Expected next Tuesday
Special System Material Approval |  | 14 |  | 2026-08-16 | 2026-09-02
PR.PS.D40.MTA.1110 | IPS l MT Approval for SCADA | 14 | 0.042429 | 2026-08-16 | 2026-09-02 | 0% | 100% | 0% | 100%
Pump-Station Material PO - Long Lead |  | 107 |  | 2026-05-21 | 2026-09-27
Fire Supperssion Material PO |  | 18 |  | 2026-07-02 | 2026-07-22
PR.PS.D21.MPO.1080 | IPS l PO Placement for Clean Agent FK-5.1.12 cylinders | 18 | 0.023803 | 2026-07-02 | 2026-07-22 | 0% | 100% | 0% | 100%
Plumbing Material PO |  | 16 |  | 2026-05-21 | 2026-06-11
PR.PS.D22.MPO.1085 | IPS l PO Placement for Submersible pumps | 16 | 0.0099803 | 2026-05-21 | 2026-06-11 | 0% | 100% | 0% | 100%
HVAC System Material PO |  | 20 |  | 2026-07-07 | 2026-07-29
PR.PS.D23.MPO.1090 | IPS l PO Placement for HVAC System | 20 | 0.022789 | 2026-07-07 | 2026-07-29 | 0% | 100% | 0% | 100%
Electrical System Material PO |  | 51 |  | 2026-06-30 | 2026-08-27
PR.PS.D26.MPO.1100 | IPS l PO Placement for Low voltage electrical cables | 15 | 0.011297 | 2026-06-30 | 2026-07-16 | 0% | 100% | 0% | 100%
PR.PS.D26.MPO.1095 | IPS l PO Placement for Panel boards | 18 | 0.025486 | 2026-07-23 | 2026-08-12 | 0% | 100% | 0% | 100%
PR.PS.D26.MPO.1105 | IPS l PO Placement for Lighting fixtures | 15 | 0.034426 | 2026-08-11 | 2026-08-27 | 0% | 100% | 0% | 100%
Special System Material PO |  | 20 |  | 2026-09-03 | 2026-09-27
PR.PS.D40.MPO.1110 | IPS l PO Placement for SCADA | 20 | 0.084857 | 2026-09-03 | 2026-09-27 | 0% | 100% | 0% | 100%
Pump-Station Material Delivery and Fabrication - Long Lead |  | 188 |  | 2026-06-12 | 2026-12-16
Fire Supperssion Material Delivery and Fabrication |  | 50 |  | 2026-07-23 | 2026-09-10
PR.PS.D21.MTD.1080 | IPS l MT Delivery for Clean Agent FK-5.1.12 cylinders | 50 | 0.031738 | 2026-07-23 | 2026-09-10 | 98% | 60% | 0% | 60% |  | Novec System and delivered MIR not raised due to site stop order
Plumbing Material Delivery and Fabrication |  | 70 |  | 2026-06-12 | 2026-08-20
PR.PS.D22.MTD.1085 | IPS l MT Delivery for Submersible pumps | 70 | 0.013307 | 2026-06-12 | 2026-08-20 | 0% | 0% | 0% | 0% |  | Issue in Progress with KSB to solve logistic Matter
HVAC System Material Delivery and Fabrication |  | 70 |  | 2026-07-30 | 2026-10-07
PR.PS.D23.MTD.1090 | IPS l MT Delivery for HVAC System | 70 | 0.030386 | 2026-07-30 | 2026-10-07 | 40% | 90% | 0% | 90% |  | PQD under review
Electrical System Material Delivery and Fabrication |  | 112 |  | 2026-07-17 | 2026-11-05
PR.PS.D26.MTD.1100 | IPS l MT Delivery for Low voltage electrical cables | 48 | 0.018829 | 2026-07-17 | 2026-09-02 | 0% | 0% | 0% | 0% |  | Order in Progress with CSC
PR.PS.D26.MTD.1095 | IPS l MT Delivery for Panel boards | 50 | 0.033981 | 2026-08-13 | 2026-10-01 | 0% | 0% | 0% | 0% |  | after MT approval
PR.PS.D26.MTD.1105 | IPS l MT Delivery for Lighting fixtures | 70 | 0.057376 | 2026-08-28 | 2026-11-05 | 0% | 0% | 0% | 0%
Special System Material Delivery and Fabrication |  | 80 |  | 2026-09-28 | 2026-12-16
PR.PS.D40.MTD.1110 | IPS l MT Delivery for SCADA | 80 | 0.11314 | 2026-09-28 | 2026-12-16 | 0% | 0% | 0% | 0%
Collection System |  | 323 |  | 2026-01-15 | 2026-12-03
Short Lead Items |  | 117 |  | 2026-01-15 | 2026-05-11
Collection System Material Submittal - Short Lead |  | 25 |  | 2026-01-15 | 2026-02-12
Plumbing Material Submittal |  | 25 |  | 2026-01-15 | 2026-02-12
PR.CL.D33.MTS.1000 | CLS l MT Submission for Precast Manholes | 25 | 0.0051851 | 2026-01-15 | 2026-02-12 | 68% | 100% | 0% | 100%
Collection System Material Approval - Short Lead |  | 14 |  | 2026-02-15 | 2026-03-05
Plumbing Material Approval |  | 14 |  | 2026-02-15 | 2026-03-05
PR.CL.D33.MTA.1000 | CLS l MT Approval for Precast Manholes | 14 | 0.0051851 | 2026-02-15 | 2026-03-05 | 0% | 100% | 0% | 100%
Collection System Material PO - Short Lead |  | 20 |  | 2026-03-07 | 2026-04-01
Plumbing Material PO |  | 20 |  | 2026-03-07 | 2026-04-01
PR.CL.D33.MPO.1000 | CLS l PO Placement for Precast Manholes | 20 | 0.01037 | 2026-03-07 | 2026-04-01 | 0% | 100% | 0% | 100%
Collection System Material Delivery and Fabrication - Short Lead |  | 40 |  | 2026-04-02 | 2026-05-11
Plumbing Material Delivery & Fabrication |  | 40 |  | 2026-04-02 | 2026-05-11
PR.CL.D33.MTD.1000 | CLS l MT Delivery for Precast Manholes | 40 | 0.031111 | 2026-04-02 | 2026-05-11 | 0% | 100% | 0% | 100%
Long Lead Item |  | 293 |  | 2026-02-14 | 2026-12-03
Collection System Material Submittal - Long Lead |  | 140 |  | 2026-02-14 | 2026-08-03
Plumbing Material Submittal |  | 60 |  | 2026-02-14 | 2026-04-28
PR.CL.D33.MTS.1015 | CLS l MT Submission for HDPE pipes | 20 | 0.14001 | 2026-02-14 | 2026-03-09 | 0% | 100% | 0% | 100%
PR.CL.D33.MTS.1010 | CLS l MT Submission for GRP pipes | 20 | 0.036165 | 2026-03-10 | 2026-04-05 | 0% | 100% | 0% | 100%
PR.CL.D33.MTS.1020 | CLS l MT Submission for General Duty valves | 20 | 0.015505 | 2026-03-10 | 2026-04-05 | 0% | 100% | 0% | 100%
PR.CL.D22.MTS.1005 | CLS l MT Submission for Submersible pumps | 20 | 0.129 | 2026-04-06 | 2026-04-28 | 0% | 100% | 0% | 100%
Electrical System Material Submittal |  | 80 |  | 2026-04-29 | 2026-08-03
PR.CL.D33.MTS.1035 | CLS l MT Submission for Fiber optic conduits | 25 | 0.066637 | 2026-04-29 | 2026-05-31 | 0% | 100% | 0% | 100%
PR.CL.D33.MTS.1030 | CLS l MT Submission for Fiber Optic Cables | 25 | 0.019085 | 2026-06-01 | 2026-06-29 | 0% | 100% | 0% | 100%
PR.CL.D33.MTS.1025 | CLS l MT Submission for Remote terminal unit (RTU) | 30 | 0.05634 | 2026-06-30 | 2026-08-03 | 0% | 100% | 0% | 100%
Collection System Material Approval - Long Lead |  | 113 |  | 2026-03-10 | 2026-08-23
Plumbing Material Approval |  | 47 |  | 2026-03-10 | 2026-05-18
PR.CL.D33.MTA.1015 | CLS l MT Approval for HDPE pipes | 14 | 0.14001 | 2026-03-10 | 2026-04-01 | 0% | 100% | 0% | 100%
PR.CL.D33.MTA.1010 | CLS l MT Approval for GRP pipes | 14 | 0.036165 | 2026-04-06 | 2026-04-23 | 0% | 100% | 0% | 100%
PR.CL.D33.MTA.1020 | CLS l MT Approval for General Duty valves | 14 | 0.015505 | 2026-04-06 | 2026-04-23 | 0% | 100% | 0% | 100%
PR.CL.D22.MTA.1005 | CLS l MT Approval for Submersible pumps | 14 | 0.129 | 2026-04-29 | 2026-05-18 | 0% | 100% | 0% | 100%
Electrical System Material Approval |  | 60 |  | 2026-06-01 | 2026-08-23
PR.CL.D33.MTA.1035 | CLS l MT Approval for Fiber optic conduits | 14 | 0.066637 | 2026-06-01 | 2026-06-18 | 0% | 100% | 0% | 100%
PR.CL.D33.MTA.1030 | CLS l MT Approval for Fiber Optic Cables | 14 | 0.019085 | 2026-06-30 | 2026-07-19 | 0% | 100% | 0% | 100%
PR.CL.D33.MTA.1025 | CLS l MT Approval for Remote terminal unit (RTU) | 14 | 0.05634 | 2026-08-04 | 2026-08-23 | 0% | 100% | 0% | 100%
Collection System Material PO - Long Lead |  | 155 |  | 2026-04-02 | 2026-10-04
Plumbing Material PO |  | 60 |  | 2026-04-02 | 2026-06-14
PR.CL.D33.MPO.1015 | CLS l PO Placement for HDPE pipes | 20 | 0.42004 | 2026-04-02 | 2026-04-25 | 0% | 100% | 0% | 100%
PR.CL.D33.MPO.1020 | CLS l PO Placement for General Duty valves | 10 | 0.046516 | 2026-04-25 | 2026-05-05 | 0% | 100% | 0% | 100%
PR.CL.D33.MPO.1010 | CLS l PO Placement for GRP pipes | 20 | 0.1085 | 2026-04-25 | 2026-05-17 | 0% | 100% | 0% | 100%
PR.CL.D22.MPO.1005 | CLS l PO Placement for Submersible pumps | 20 | 0.25801 | 2026-05-19 | 2026-06-14 | 0% | 100% | 0% | 100%
Electrical System Material PO |  | 91 |  | 2026-06-20 | 2026-10-04
PR.CL.D33.MPO.1035 | CLS l PO Placement for Fiber optic conduits | 30 | 0.19991 | 2026-06-20 | 2026-07-23 | 0% | 100% | 0% | 100%
PR.CL.D33.MPO.1030 | CLS l PO Placement for Fiber Optic Cables | 35 | 0.057255 | 2026-07-20 | 2026-08-29 | 0% | 100% | 0% | 100%
PR.CL.D33.MPO.1025 | CLS l PO Placement for Remote terminal unit (RTU) | 35 | 0.11268 | 2026-08-24 | 2026-10-04 | 0% | 100% | 0% | 100%
Collection System Material Delivery and Fabrication - Long Lead |  | 222 |  | 2026-04-26 | 2026-12-03
Plumbing Material Delivery & Fabrication |  | 120 |  | 2026-04-26 | 2026-08-23
PR.CL.D33.MTD.1015 | CLS l MT Delivery for HDPE pipes | 40 | 0.70006 | 2026-04-26 | 2026-06-04 | 0% | 100% | 0% | 100% |  | all matrial deliveried to site
PR.CL.D33.MTD.1020 | CLS l MT Delivery for General Duty valves | 30 | 0.077526 | 2026-05-06 | 2026-06-04 | 0% | 0% | 0% | 0% |  | to be delivered on 27-8-2026
PR.CL.D33.MTD.1010 | CLS l MT Delivery for GRP pipes | 50 | 0.18083 | 2026-05-18 | 2026-07-06 | 0% | 97% | 0% | 97% |  | Delivered | Remaining GRP – IPS Room
PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps | 70 | 0.34401 | 2026-06-15 | 2026-08-23 | 0% | 0% | 0% | 0% |  | Issue in Progress with KSB to solve logistic Matter
Electrical System Material Delivery & Fabrication |  | 133 |  | 2026-07-24 | 2026-12-03
PR.CL.D33.MTD.1035 | CLS l MT Delivery for Fiber optic conduits | 40 | 0.33319 | 2026-07-24 | 2026-09-01 | 0% | 40% | 0% | 40% |  | No material inside the Tunnel
PR.CL.D33.MTD.1030 | CLS l MT Delivery for Fiber Optic Cables | 50 | 0.095425 | 2026-08-30 | 2026-10-18 | 0% | 60% | 0% | 60%
PR.CL.D33.MTD.1025 | CLS l MT Delivery for Remote terminal unit (RTU) | 60 | 0.15024 | 2026-10-05 | 2026-12-03 | 0% | 0% | 0% | 0%
Construction |  | 422 |  | 2025-10-25 | 2027-03-14 | 32.96% | 33.52% | 1.338% | 34.86%
RO Plant |  | 422 |  | 2025-10-25 | 2027-03-14 | 35.69% | 33.32% | 1.5% | 34.82%
Under Ground Floor |  | 352 |  | 2025-11-08 | 2026-12-31
Earthwork |  | 282 |  | 2025-11-08 | 2026-10-11
CO.RO.D31.0UG.1020 | RO l Excavation Works pre-piles part1 (Segment1,2,5) UG | 12 | 0.24141 | 2025-11-13 | 2025-11-26 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1560 | RO l Preparation and utilities relocation UG | 25 | 0.16094 | 2025-11-08 | 2025-12-06 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1025 | RO l Excavation Works pre-piles part2 (Segment3,4,6) UG | 10 | 0.24141 | 2025-11-27 | 2025-12-08 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1030 | RO l Concrete Piles works part 1 UG | 24 | 1.6286 | 2025-12-09 | 2026-01-05 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1035 | RO l Concrete Piles works part 2 UG | 21 | 1.6286 | 2026-01-06 | 2026-01-29 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1010 | RO l Temporary prestressed anchors works part 1 UG | 11 | 0.1859 | 2026-01-18 | 2026-01-29 | 100% | 100% | 0% | 100%
CO.RO.D31.0UG.1015 | RO l Temporary prestressed anchors works part 2 UG | 11 | 0.1859 | 2026-01-31 | 2026-02-11 | 36.36% | 100% | 0% | 100%
CO.RO.D31.0UG.1040 | RO l Excavation Works post-piles part1 (Segment1,2,5) UG | 35 | 0.48281 | 2026-01-31 | 2026-03-12 | 8.57% | 100% | 0% | 100%
CO.RO.D31.0UG.1045 | RO l Excavation Works post-piles part2 (Segment3,4,6) UG | 38 | 0.48281 | 2026-03-14 | 2026-04-29 | 0% | 100% | 0% | 100%
CO.RO.D31.0UG.1005 | RO l Under Foundation Probe Holes works UG | 3 | 0.044394 | 2026-04-30 | 2026-05-03 | 0% | 100% | 0% | 100%
CO.RO.D31.0UG.1000 | RO l Groundwater Control System works UG | 30 | 0.45685 | 2026-09-06 | 2026-10-11 | 0% | 0% | 0% | 0%
Concrete Work |  | 143 |  | 2026-05-04 | 2026-10-21
CO.RO.D03.0UG.1055 | RO l Plain Concrete works for foundation UG | 6 | 0.11104 | 2026-05-04 | 2026-05-10 | 100% | 100% | 0% | 100%
CO.RO.D03.0UG.1060 | RO l Shuttering for Raft Foundation part 1 UG | 6 | 0.88215 | 2026-05-11 | 2026-05-17 | 100% | 96% | 0% | 96%
CO.RO.D03.0UG.1065 | RO l Steel fixing & Pouring for Raft Foundation part 1 UG | 7 | 1.3232 | 2026-05-18 | 2026-05-25 | 100% | 96% | 0% | 96%
CO.RO.D03.0UG.1070 | RO l Shuttering for Raft Foundation part 2 UG | 6 | 0.88215 | 2026-05-30 | 2026-06-04 | 100% | 100% | 0% | 100%
CO.RO.D03.0UG.1075 | RO l Steel fixing & Pouring for Raft Foundation part 2 UG | 7 | 1.3232 | 2026-06-06 | 2026-06-13 | 100% | 100% | 0% | 100%
CO.RO.D03.0UG.1085 | RO l Steel fixing for Tank walls part 1 UG | 8 | 1.561 | 2026-06-14 | 2026-06-22 | 100% | 100% | 0% | 100%
CO.RO.D03.0UG.1080 | RO l Shuttering & Pouring for Tank walls part 1 UG | 10 | 2.3415 | 2026-06-23 | 2026-07-04 | 100% | 100% | 0% | 100%
CO.RO.D03.0UG.1095 | RO l Steel fixing for Tank walls part 2 UG | 8 | 1.561 | 2026-07-05 | 2026-07-13 | 100% | 63% | 22% | 85%
CO.RO.D03.0UG.1090 | RO l Shuttering & Pouring for Tank walls part 2 UG | 10 | 2.3415 | 2026-07-14 | 2026-07-25 | 100% | 34% | 16% | 50%
CO.RO.D03.0UG.1105 | RO l Steel fixing for Tank walls part 3 UG | 8 | 1.561 | 2026-07-26 | 2026-08-03 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1100 | RO l Shuttering & Pouring for Tank walls part 3 UG | 10 | 2.3415 | 2026-08-04 | 2026-08-15 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1115 | RO l Steel fixing for Tank walls part 4 UG | 8 | 1.561 | 2026-08-16 | 2026-08-24 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1110 | RO l Shuttering & Pouring for Tank walls part 4 UG | 10 | 2.3415 | 2026-08-25 | 2026-09-05 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1120 | RO l Shuttering for Tank slab part 1 UG | 9 | 0.46942 | 2026-09-06 | 2026-09-15 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1145 | RO l Tank walls Deshuttering works UG | 14 | 0 | 2026-09-06 | 2026-09-21 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1125 | RO l Steel fixing & Pouring Tank slab part 1 UG | 7 | 0.70413 | 2026-09-16 | 2026-09-24 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1130 | RO l Shuttering for Tank slab part 2 UG | 9 | 0.46942 | 2026-09-16 | 2026-09-27 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1135 | RO l Steel fixing & Pouring Tank slab part 2 UG | 7 | 0.70413 | 2026-09-28 | 2026-10-05 | 0% | 0% | 0% | 0%
CO.RO.D03.0UG.1155 | RO l Tank slab Deshuttering works UG | 14 | 0 | 2026-10-06 | 2026-10-21 | 0% | 0% | 0% | 0%
Metal Works |  | 5 |  | 2026-12-27 | 2026-12-31
CO.RO.D05.0UG.1185 | RO l Install of Metal Ladders UG | 5 | 0.0064731 | 2026-12-27 | 2026-12-31 | 0% | 0% | 0% | 0%
Wood & Plastics |  | 4 |  | 2026-12-27 | 2026-12-30
CO.RO.D06.0UG.1195 | RO l Install of GRP ladder UG | 4 | 0.045877 | 2026-12-27 | 2026-12-30 | 0% | 0% | 0% | 0%
Thermal & Moisture Protection |  | 148 |  | 2026-05-30 | 2026-11-18
CO.RO.D07.0UG.1215 | RO l Install of Bottom of raft HDPE sheets UG | 6 | 0.49979 | 2026-05-30 | 2026-06-04 | 100% | 98% | 0% | 98%
CO.RO.D07.0UG.1220 | RO l Water Tank Membrene sheets waterproofing UG | 12 | 0.062129 | 2026-09-22 | 2026-10-06 | 0% | 0% | 0% | 0%
CO.RO.D07.0UG.1225 | RO l Water Tank Chemical waterproof coating UG | 12 | 0.79162 | 2026-10-22 | 2026-11-04 | 0% | 0% | 0% | 0%
CO.RO.D07.0UG.1210 | RO l Water Tank Slab Bituminous Coating UG | 4 | 0.029281 | 2026-11-15 | 2026-11-18 | 0% | 0% | 0% | 0%
Plumbing |  | 32 |  | 2026-11-19 | 2026-12-26
CO.RO.D22.0UG.1440 | RO l Install of Sanitary Pipes UG | 4 | 0.012462 | 2026-11-19 | 2026-11-23 | 0% | 0% | 0% | 0%
CO.RO.D22.0UG.1445 | RO l Install of Domestic water pipes (R&T water pump station) UG | 5 | 0.093851 | 2026-11-24 | 2026-11-29 | 0% | 0% | 0% | 0%
CO.RO.D22.0UG.1450 | RO l Install of General Duty plumbing valves (R&T water pump station) UG | 6 | 0.093025 | 2026-11-30 | 2026-12-06 | 0% | 0% | 0% | 0%
CO.RO.D22.0UG.1460 | RO l Install of Domestic water filter (R&T water pump station) UG | 6 | 0.027947 | 2026-12-07 | 2026-12-13 | 0% | 0% | 0% | 0%
CO.RO.D22.0UG.1455 | RO l Install of water pumps (R&T water pump station) UG | 11 | 0.14701 | 2026-12-14 | 2026-12-26 | 0% | 0% | 0% | 0%
Electrical |  | 8 |  | 2026-11-19 | 2026-11-28
CO.RO.D26.0UG.1605 | RO l Install of Underground Cable ducts, manholes and trenches UG | 8 | 0.066397 | 2026-11-19 | 2026-11-28 | 0% | 0% | 0% | 0%
Ground Floor |  | 129 |  | 2026-10-06 | 2027-03-06
Concrete Work |  | 82 |  | 2026-10-06 | 2027-01-09
CO.RO.D03.0GF.1145 | RO l Steel fixing for Columns GF | 4 | 0.051053 | 2026-10-06 | 2026-10-10 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1140 | RO l Shuttering & Pouring for Columns GF | 4 | 0.07658 | 2026-10-11 | 2026-10-14 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1120 | RO l Shuttering for Slab GF | 7 | 0.27719 | 2026-10-15 | 2026-10-22 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1125 | RO l Steel fixing & Pouring for Slab GF | 7 | 0.41578 | 2026-10-24 | 2026-10-31 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1175 | RO l Deshuttering works for Slab GF | 12 | 0 | 2026-11-01 | 2026-11-14 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1150 | RO l Concete works for Slab on grade GF | 6 | 0.39768 | 2026-11-24 | 2026-11-30 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1160 | RO l Concete works for Roof screed GF | 7 | 0.019028 | 2026-12-15 | 2026-12-22 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1165 | RO l Concete works for Floor screed GF | 7 | 0.060456 | 2026-12-19 | 2026-12-26 | 0% | 0% | 0% | 0%
CO.RO.D03.0GF.1155 | RO l Install of Precast Shaft cover GF | 12 | 0.045734 | 2026-12-27 | 2027-01-09 | 0% | 0% | 0% | 0%
Masonry Works |  | 9 |  | 2026-12-01 | 2026-12-10
CO.RO.D04.0GF.1170 | RO l Masonry works GF | 9 | 0.12943 | 2026-12-01 | 2026-12-10 | 0% | 0% | 0% | 0%
Metal Works |  | 6 |  | 2027-02-11 | 2027-02-17
CO.RO.D05.0GF.1185 | RO l Install of Metal Ladders GF | 5 | 0.0064731 | 2027-02-11 | 2027-02-16 | 0% | 0% | 0% | 0%
CO.RO.D05.0GF.1175 | RO l Install of Steel covers GF | 6 | 0.16111 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D05.0GF.1180 | RO l Install of Handrail GF | 6 | 0.016971 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
Thermal And Moisture Protection |  | 50 |  | 2026-12-12 | 2027-02-07
CO.RO.D07.0GF.1230 | RO l Rockwool insulation works GF | 6 | 0.045944 | 2026-12-12 | 2026-12-17 | 0% | 0% | 0% | 0%
CO.RO.D07.0GF.1570 | RO l Wet areas insulation works GF | 6 | 0.0017356 | 2026-12-12 | 2026-12-17 | 0% | 0% | 0% | 0%
CO.RO.D07.0GF.1235 | RO l Install of Concrete tiles GF | 6 | 0.034441 | 2027-02-01 | 2027-02-07 | 0% | 0% | 0% | 0%
Openings |  | 12 |  | 2027-02-11 | 2027-02-25
CO.RO.D08.0GF.1255 | RO l Install of Aluminum windows & Louvers GF | 6 | 0.041367 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D08.0GF.1250 | RO l Install of Steel doors GF | 8 | 0.021096 | 2027-02-11 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D08.0GF.1245 | RO l Install of Roller shutter doors GF | 8 | 0.16321 | 2027-02-11 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D08.0GF.1240 | RO l Install of Acoustic & Fire rated doors GF | 12 | 0.044915 | 2027-02-11 | 2027-02-25 | 0% | 0% | 0% | 0%
Finishes |  | 53 |  | 2026-12-12 | 2027-02-10
CO.RO.D09.0GF.1300 | RO l Gypsum & cement board walls works GF | 8 | 0.14068 | 2026-12-12 | 2026-12-20 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1310 | RO l Internal Plaster works GF | 10 | 0.076403 | 2026-12-12 | 2026-12-22 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1280 | RO l Floor Ceramic tiles & Stones works GF | 6 | 0.016119 | 2026-12-23 | 2026-12-29 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1305 | RO l Floor epoxy painting GF | 6 | 0.043665 | 2026-12-27 | 2027-01-02 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1295 | RO l Wall epoxy painting GF | 5 | 0.042938 | 2027-01-03 | 2027-01-07 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1285 | RO l Wall Ceramic tiles works GF | 7 | 0.013425 | 2027-01-24 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1275 | RO l Gypsum board ceiling works GF | 8 | 0.014881 | 2027-01-24 | 2027-02-01 | 0% | 0% | 0% | 0%
CO.RO.D09.0GF.1290 | RO l Wall & Ceiling painting works GF | 8 | 0.099276 | 2027-02-02 | 2027-02-10 | 0% | 0% | 0% | 0%
Specialities |  | 15 |  | 2027-02-01 | 2027-02-17
CO.RO.D10.0GF.1340 | RO l Install of Toilet Accessories GF | 4 | 0.008088 | 2027-02-01 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D10.0GF.1335 | RO l Corner guards GF | 3 | 0.0093604 | 2027-02-11 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D10.0GF.1330 | RO l Install of Fire Extinguisher GF | 6 | 0.018957 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
Special Construction |  | 6 |  | 2027-02-18 | 2027-02-25
CO.RO.D13.0GF.1350 | RO l Install of Aluminium Control booths GF | 6 | 0.013681 | 2027-02-18 | 2027-02-25 | 0% | 0% | 0% | 0%
Fire Supression |  | 41 |  | 2026-12-23 | 2027-02-08
CO.RO.D21.0GF.1415 | RO l Install of Fire Suppression standpipes GF | 10 | 0.10526 | 2026-12-23 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1390 | RO l Install of Vibration and Seismic controls GF | 10 | 0.13506 | 2026-12-27 | 2027-01-06 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1360 | RO l Install of Siamese Connection GF | 6 | 0.0028766 | 2027-01-04 | 2027-01-10 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1370 | RO l Install of Fire Hose Cabinets GF | 7 | 0.0085948 | 2027-01-04 | 2027-01-11 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1380 | RO l Install of Foam Bladder Tank GF | 4 | 0.057371 | 2027-01-07 | 2027-01-11 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1365 | RO l Install of Fire Suppression valves GF | 10 | 0.024976 | 2027-01-04 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1400 | RO l Install of Cold Water Pipes GF | 12 | 0.00053722 | 2027-01-04 | 2027-01-17 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1425 | RO l Install of Electrical Fire Pump GF | 10 | 0.023802 | 2027-01-07 | 2027-01-18 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1405 | RO l Install of Recirculating Pumps GF | 14 | 0.0056729 | 2027-01-07 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1375 | RO l Install of Foam Water fire extinguishing system GF | 14 | 0.0022963 | 2027-01-12 | 2027-01-27 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1385 | RO l Install of Clean Agent FK-5.1.12 System GF | 11 | 0.13534 | 2027-01-16 | 2027-01-27 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1430 | RO l Install of Diesel Fire Pump GF | 10 | 0.032863 | 2027-01-19 | 2027-01-30 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1410 | RO l Install of Diesel Fire Pump fuel tank GF | 5 | 0.049334 | 2027-01-31 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1420 | RO l Install of Fire Suppersion Sprinkls GF | 6 | 0.0029278 | 2027-02-02 | 2027-02-08 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1435 | RO l Install of Diesel Fire Pump Pipes & Valves GF | 8 | 0.0038153 | 2027-01-31 | 2027-02-08 | 0% | 0% | 0% | 0%
CO.RO.D21.0GF.1395 | RO l Install of Pressure Maintenance Fire Pump GF | 8 | 0.01027 | 2027-01-31 | 2027-02-08 | 0% | 0% | 0% | 0%
Plumbing |  | 55 |  | 2026-12-12 | 2027-02-13
CO.RO.D22.0GF.1440 | RO l Install of Sanitary Pipes GF | 10 | 0.018694 | 2026-12-12 | 2026-12-22 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1480 | RO l Install of Sanitary drains & Cleanouts GF | 7 | 0.011921 | 2026-12-23 | 2026-12-30 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1490 | RO l Install of Domestic water pipes GF | 10 | 0.01672 | 2026-12-23 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1485 | RO l Install of Inspection Chamber GF | 5 | 0.015199 | 2026-12-31 | 2027-01-05 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1815 | RO l Install of Plumbing water meter GF | 6 | 0.0059489 | 2027-01-04 | 2027-01-10 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1475 | RO l Install of General Duty Plumbing Valves GF | 9 | 0.0044735 | 2027-01-04 | 2027-01-13 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1470 | RO l Install of Plumbing pipes insulation GF | 8 | 0.010197 | 2027-01-14 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D22.0GF.1465 | RO l Install of Plumbing Fixtures GF | 11 | 0.017107 | 2027-02-01 | 2027-02-13 | 0% | 0% | 0% | 0%
Heating, Ventilating And Air Conditioning |  | 50 |  | 2026-12-23 | 2027-02-18
CO.RO.D23.0GF.1575 | RO l Install of Hydronic pipes GF | 10 | 0.016883 | 2026-12-23 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works GF | 11 | 0.040719 | 2026-12-23 | 2027-01-04 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1590 | RO l Install of HVAC Metal ducts GF | 12 | 0.039227 | 2026-12-23 | 2027-01-05 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1560 | RO l Install of HVAC Flexible ducts GF | 7 | 0.060023 | 2027-01-06 | 2027-01-13 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1535 | RO l Install of Condensate drain pipes GF | 7 | 0.002165 | 2027-01-06 | 2027-01-13 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1530 | RO l Install of HVAC dampers GF | 7 | 0.013424 | 2027-01-06 | 2027-01-13 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1550 | RO l Install of HVAC system equipments GF | 10 | 0.10613 | 2027-01-05 | 2027-01-16 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1545 | RO l Install of Genetal duty HVAC valves GF | 12 | 0.015108 | 2027-01-04 | 2027-01-17 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1555 | RO l Install of HVAC water treatment GF | 14 | 0.028385 | 2027-01-05 | 2027-01-20 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1580 | RO l Install of Ducts thermal insulation GF | 8 | 0.034688 | 2027-01-14 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1540 | RO l Install of Chilled water Pipes Insulation GF | 10 | 0.017486 | 2027-01-18 | 2027-01-28 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1565 | RO l Install of Split & Fan coil Units GF | 12 | 0.0057234 | 2027-01-24 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles GF | 8 | 0.014352 | 2027-02-02 | 2027-02-10 | 0% | 0% | 0% | 0%
CO.RO.D23.0GF.1525 | RO l HVAC Monitoring and Controlling System GF | 7 | 0.068501 | 2027-02-11 | 2027-02-18 | 0% | 0% | 0% | 0%
Electrical |  | 83 |  | 2026-11-29 | 2027-03-06
CO.RO.D26.0GF.1650 | RO l Install of Meduim-Vlotage Cables GF | 6 | 0.018025 | 2026-11-29 | 2026-12-05 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1610 | RO l Install of Meduim-Voltage switchgear GF | 10 | 0.2283 | 2026-12-06 | 2026-12-16 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1615 | RO l Install of Meduim-Voltage Transformers GF | 10 | 0.069407 | 2026-12-07 | 2026-12-17 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1655 | RO l Install of Enclosed bus assemblies GF | 5 | 0.32085 | 2026-12-19 | 2026-12-23 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1620 | RO l Install of Diesel Generators GF | 7 | 0.50012 | 2026-12-19 | 2026-12-26 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1680 | RO l Install of Cable tray and trunk GF | 8 | 0.046222 | 2026-12-23 | 2026-12-31 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1640 | RO l Install of Automatic Transfer Switches (ATS) GF | 7 | 0.076777 | 2026-12-27 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1695 | RO l Install of Main distribution board (MDB) GF | 10 | 0.079263 | 2026-12-24 | 2027-01-04 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1670 | RO l Install of Disconnecting Switches GF | 5 | 0.028175 | 2027-01-05 | 2027-01-10 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1690 | RO l Install of Low voltage electrical power conductors GF | 12 | 0.18183 | 2027-01-02 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1635 | RO l Install of Distribution and power panel boards GF | 9 | 0.048443 | 2027-01-16 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1685 | RO l Install of Low voltage electrical power Cables GF | 10 | 0.30132 | 2027-01-26 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1675 | RO l Install of Interior lighting GF | 7 | 0.038965 | 2027-02-02 | 2027-02-09 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1645 | RO l Install of Lightning & Earthing Protection Systems GF | 7 | 0.047022 | 2027-02-07 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1630 | RO l Install of Motor control Centers (MCC) GF | 8 | 0.12812 | 2027-02-07 | 2027-02-15 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1660 | RO l Install of Sochets & lighting switches GF | 9 | 0.02279 | 2027-02-11 | 2027-02-21 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1625 | RO l Install of VFD with inlet air filters and MCPr GF | 7 | 0.045202 | 2027-02-16 | 2027-02-24 | 0% | 0% | 0% | 0%
CO.RO.D26.0GF.1665 | RO l Install of Network lighting control system GF | 10 | 0.080119 | 2027-02-23 | 2027-03-06 | 0% | 0% | 0% | 0%
Communication System |  | 48 |  | 2027-01-02 | 2027-02-27
CO.RO.D27.0GF.1730 | RO l Install of Communication Cables GF | 6 | 0.020462 | 2027-01-02 | 2027-01-07 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1735 | RO l Install of Telecommunication outlets/connector GF | 6 | 0.005501 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1720 | RO l Install of Communication equipment room fitting GF | 8 | 0.016878 | 2027-02-11 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1715 | RO l Install of Network systems GF | 5 | 0.011653 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1725 | RO l Install of Data communication components GF | 5 | 0.076209 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1740 | RO l Install of Wireless data network components GF | 5 | 0.023094 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D27.0GF.1745 | RO l Install of IP Based telephony communication system GF | 5 | 0.015945 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
Electronic Safety And Security |  | 56 |  | 2026-12-23 | 2027-02-27
CO.RO.D28.0GF.1755 | RO l Install of Access control 1st & 2nd Fix GF | 6 | 0.030316 | 2026-12-23 | 2026-12-29 | 0% | 0% | 0% | 0%
CO.RO.D28.0GF.1765 | RO l Install of CCTV system 1st & 2nd Fix GF | 6 | 0.049785 | 2026-12-23 | 2026-12-29 | 0% | 0% | 0% | 0%
CO.RO.D28.0GF.1775 | RO l Install of Fire alarm system 1st & 2nd Fix GF | 10 | 0.030659 | 2026-12-23 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D28.0GF.1770 | RO l Install of CCTV system 3nd Fix GF | 6 | 0.039828 | 2027-02-11 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D28.0GF.1760 | RO l Install of Access control 3nd Fix GF | 7 | 0.024252 | 2027-02-11 | 2027-02-18 | 0% | 0% | 0% | 0%
CO.RO.D28.0GF.1780 | RO l Install of Fire alarm system 3nd Fix GF | 7 | 0.024527 | 2027-02-18 | 2027-02-27 | 0% | 0% | 0% | 0%
Utilities |  | 71 |  | 2026-12-01 | 2027-02-21
CO.RO.D33.0GF.1805 | RO l Install of Brackish Water Reverse Osmosis Plant GF | 71 | 2.5771 | 2026-12-01 | 2027-02-21 | 0% | 0% | 0% | 0%
First Floor |  | 111 |  | 2026-11-01 | 2027-03-14
Concrete Work |  | 73 |  | 2026-11-01 | 2027-01-24
CO.RO.D03.1ST.1145 | RO l Steel fixing for Columns 1st | 6 | 0.051053 | 2026-11-01 | 2026-11-07 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1140 | RO l Shuttering & Pouring for Columns 1st | 6 | 0.07658 | 2026-11-08 | 2026-11-14 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1120 | RO l Shuttering for Slab 1st | 8 | 0.27719 | 2026-11-15 | 2026-11-23 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1125 | RO l Steel fixing & Pouring for Slab 1st | 8 | 0.41578 | 2026-11-24 | 2026-12-02 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1155 | RO l Deshuttering works for Slab 1st | 10 | 0 | 2026-12-03 | 2026-12-14 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1165 | RO l Concete works for Floor screed 1st | 7 | 0.030228 | 2027-01-05 | 2027-01-12 | 0% | 0% | 0% | 0%
CO.RO.D03.1ST.1160 | RO l Concete works for Roof screed 1st | 7 | 0.038056 | 2027-01-17 | 2027-01-24 | 0% | 0% | 0% | 0%
Masonry Works |  | 12 |  | 2026-12-15 | 2026-12-28
CO.RO.D04.1ST.1170 | RO l Masonry works 1st | 12 | 0.064715 | 2026-12-15 | 2026-12-28 | 0% | 0% | 0% | 0%
Metal Works |  | 33 |  | 2027-01-17 | 2027-02-24
CO.RO.D05.1ST.1190 | RO l Structural steel works 1st | 8 | 0.11569 | 2027-01-17 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D05.1ST.1185 | RO l Install of Metal Ladders 1st | 3 | 0.0064731 | 2027-02-17 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D05.1ST.1175 | RO l Install of Steel covers 1st | 5 | 0.080556 | 2027-02-18 | 2027-02-24 | 0% | 0% | 0% | 0%
CO.RO.D05.1ST.1180 | RO l Install of Handrail 1st | 5 | 0.0084853 | 2027-02-18 | 2027-02-24 | 0% | 0% | 0% | 0%
Wood & Plastics |  | 4 |  | 2027-01-24 | 2027-01-27
CO.RO.D06.1ST.1200 | RO l Install of Pantry cabinet 1st | 4 | 0.013466 | 2027-01-24 | 2027-01-27 | 0% | 0% | 0% | 0%
Thermal And Moisture Protection |  | 35 |  | 2026-12-29 | 2027-02-07
CO.RO.D07.1ST.1230 | RO l Rockwool insulation works 1st | 5 | 0.022972 | 2026-12-29 | 2027-01-03 | 0% | 0% | 0% | 0%
CO.RO.D07.1ST.1565 | RO l Wet areas insulation works 1st | 6 | 0.0017356 | 2026-12-29 | 2027-01-04 | 0% | 0% | 0% | 0%
CO.RO.D07.1ST.1260 | RO l Roofing insulation System works 1st | 6 | 0.14884 | 2027-01-25 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D07.1ST.1235 | RO l Install of Concrete tiles 1st | 4 | 0.068882 | 2027-02-01 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D07.1ST.1265 | RO l Canopy aluminium panels cladding 1st | 11 | 0.098397 | 2027-01-26 | 2027-02-07 | 0% | 0% | 0% | 0%
Openings |  | 9 |  | 2027-02-16 | 2027-02-27
CO.RO.D08.1ST.1255 | RO l Install of Aluminum windows & Louvers 1st | 5 | 0.020683 | 2027-02-18 | 2027-02-24 | 0% | 0% | 0% | 0%
CO.RO.D08.1ST.1250 | RO l Install of Steel doors 1st | 5 | 0.010548 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D08.1ST.1240 | RO l Install of Acoustic & Fire rated doors 1st | 9 | 0.022458 | 2027-02-16 | 2027-02-27 | 0% | 0% | 0% | 0%
Finishes |  | 46 |  | 2026-12-29 | 2027-02-20
CO.RO.D09.1ST.1300 | RO l Gypsum & cement board walls works 1st | 6 | 0.060291 | 2026-12-29 | 2027-01-04 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1310 | RO l Internal Plaster works 1st | 9 | 0.038202 | 2026-12-29 | 2027-01-07 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1280 | RO l Floor Ceramic tiles & Stones works 1st | 6 | 0.032237 | 2027-01-13 | 2027-01-19 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1305 | RO l Floor epoxy painting 1st | 6 | 0.021832 | 2027-01-13 | 2027-01-19 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1285 | RO l Wall Ceramic tiles works 1st | 6 | 0.031325 | 2027-01-17 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1295 | RO l Wall epoxy painting 1st | 3 | 0.021469 | 2027-01-20 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1275 | RO l Gypsum board ceiling works 1st | 10 | 0.029763 | 2027-01-26 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1290 | RO l Wall & Ceiling painting works 1st | 8 | 0.049638 | 2027-02-07 | 2027-02-15 | 0% | 0% | 0% | 0%
CO.RO.D09.1ST.1315 | RO l Carpet tiles works 1st | 4 | 0.022295 | 2027-02-16 | 2027-02-20 | 0% | 0% | 0% | 0%
Specialities |  | 29 |  | 2027-01-24 | 2027-02-27
CO.RO.D10.1ST.1340 | RO l Install of Toilet Accessories 1st | 5 | 0.018872 | 2027-01-24 | 2027-01-28 | 0% | 0% | 0% | 0%
CO.RO.D10.1ST.1335 | RO l Corner guards 1st | 3 | 0.0046802 | 2027-02-16 | 2027-02-18 | 0% | 0% | 0% | 0%
CO.RO.D10.1ST.1330 | RO l Install of Fire Extinguisher 1st | 4 | 0.0094786 | 2027-02-23 | 2027-02-27 | 0% | 0% | 0% | 0%
Furnishing |  | 4 |  | 2027-01-24 | 2027-01-27
CO.RO.D12.1ST.1345 | RO l Install of Vanity Counter 1st | 4 | 0.010835 | 2027-01-24 | 2027-01-27 | 0% | 0% | 0% | 0%
Fire Superssion |  | 42 |  | 2027-01-04 | 2027-02-21
CO.RO.D21.1ST.1415 | RO l Install of Fire Suppression standpipes 1st | 10 | 0.052632 | 2027-01-04 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D21.1ST.1365 | RO l Install of Fire Suppression valves 1st | 9 | 0.012488 | 2027-01-16 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D21.1ST.1385 | RO l Install of Clean Agent FK-5.1.12 System 1st | 11 | 0.067672 | 2027-01-16 | 2027-01-27 | 0% | 0% | 0% | 0%
CO.RO.D21.1ST.1420 | RO l Install of Fire Suppersion Sprinkls 1st | 6 | 0.0014639 | 2027-02-07 | 2027-02-13 | 0% | 0% | 0% | 0%
CO.RO.D21.1ST.1370 | RO l Install of Fire Hose Cabinets 1st | 5 | 0.0042974 | 2027-02-16 | 2027-02-21 | 0% | 0% | 0% | 0%
Plumbing |  | 26 |  | 2026-12-29 | 2027-01-27
CO.RO.D22.1ST.1440 | RO l Install of Sanitary Pipes 1st | 4 | 0.018694 | 2026-12-29 | 2027-01-02 | 0% | 0% | 0% | 0%
CO.RO.D22.1ST.1480 | RO l Install of Sanitary drains & Cleanouts 1st | 4 | 0.0059606 | 2027-01-03 | 2027-01-06 | 0% | 0% | 0% | 0%
CO.RO.D22.1ST.1490 | RO l Install of Domestic water pipes 1st | 6 | 0.00836 | 2027-01-03 | 2027-01-09 | 0% | 0% | 0% | 0%
CO.RO.D22.1ST.1475 | RO l Install of General Duty Plumbing Valves 1st | 5 | 0.0022368 | 2027-01-10 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D22.1ST.1470 | RO l Install of Plumbing pipes insulation 1st | 6 | 0.0050986 | 2027-01-10 | 2027-01-16 | 0% | 0% | 0% | 0%
CO.RO.D22.1ST.1465 | RO l Install of Plumbing Fixtures 1st | 4 | 0.017107 | 2027-01-24 | 2027-01-27 | 0% | 0% | 0% | 0%
Heating, Ventilating And Air Conditioning |  | 33 |  | 2027-01-09 | 2027-02-15
CO.RO.D23.1ST.1535 | RO l Install of Condensate drain pipes 1st | 5 | 0.0043299 | 2027-01-09 | 2027-01-13 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1590 | RO l Install of HVAC Metal ducts 1st | 8 | 0.078454 | 2027-01-09 | 2027-01-17 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1575 | RO l Install of Hydronic pipes 1st | 9 | 0.033767 | 2027-01-09 | 2027-01-18 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1530 | RO l Install of HVAC dampers 1st | 4 | 0.026847 | 2027-01-18 | 2027-01-21 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1560 | RO l Install of HVAC Flexible ducts 1st | 5 | 0.12005 | 2027-01-18 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1545 | RO l Install of Genetal duty HVAC valves 1st | 5 | 0.030215 | 2027-01-19 | 2027-01-24 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1600 | RO l Install of Exhaust Fans 1st | 6 | 0.0047665 | 2027-01-18 | 2027-01-24 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1540 | RO l Install of Chilled water Pipes Insulation 1st | 6 | 0.034971 | 2027-01-19 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1580 | RO l Install of Ducts thermal insulation 1st | 7 | 0.069375 | 2027-01-18 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1565 | RO l Install of Split & Fan coil Units 1st | 7 | 0.011447 | 2027-01-19 | 2027-01-26 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles 1st | 4 | 0.028705 | 2027-01-23 | 2027-01-26 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works 1st | 6 | 0.081437 | 2027-01-25 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1595 | RO l Install of Air Handlig Units 1st | 7 | 0.062999 | 2027-02-01 | 2027-02-08 | 0% | 0% | 0% | 0%
CO.RO.D23.1ST.1525 | RO l HVAC Monitoring and Controlling System 1st | 6 | 0.137 | 2027-02-09 | 2027-02-15 | 0% | 0% | 0% | 0%
Electrical |  | 52 |  | 2027-01-09 | 2027-03-14
CO.RO.D26.1ST.1680 | RO l Install of Cable tray and trunk 1st | 7 | 0.023111 | 2027-01-09 | 2027-01-16 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1690 | RO l Install of Low voltage electrical power conductors 1st | 8 | 0.090916 | 2027-01-17 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1685 | RO l Install of Low voltage electrical power Cables 1st | 8 | 0.15066 | 2027-01-17 | 2027-01-25 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1635 | RO l Install of Distribution and power panel boards 1st | 10 | 0.020761 | 2027-01-17 | 2027-01-27 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1645 | RO l Install of Lightning & Earthing Protection Systems 1st | 5 | 0.023511 | 2027-01-26 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1670 | RO l Install of Disconnecting Switches 1st | 6 | 0.014088 | 2027-01-28 | 2027-02-03 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1660 | RO l Install of Sochets & lighting switches 1st | 6 | 0.011395 | 2027-02-16 | 2027-02-23 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1675 | RO l Install of Interior lighting 1st | 7 | 0.019483 | 2027-02-16 | 2027-02-24 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1700 | RO l Install of Uninterruptible Power Supply (UPS) 1st | 5 | 0.22699 | 2027-02-24 | 2027-03-01 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1705 | RO l Install of Power Factor Corrections Capacitors 1st | 7 | 0.092138 | 2027-02-24 | 2027-03-03 | 0% | 0% | 0% | 0%
CO.RO.D26.1ST.1665 | RO l Install of Network lighting control system 1st | 6 | 0.040059 | 2027-03-04 | 2027-03-14 | 0% | 0% | 0% | 0%
Communication System |  | 33 |  | 2027-01-17 | 2027-02-24
CO.RO.D27.1ST.1730 | RO l Install of Communication Cables 1st | 5 | 0.040924 | 2027-01-17 | 2027-01-21 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1740 | RO l Install of Wireless data network components 1st | 7 | 0.046189 | 2027-01-23 | 2027-01-30 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1745 | RO l Install of IP Based telephony communication system 1st | 8 | 0.03189 | 2027-01-23 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1720 | RO l Install of Communication equipment room fitting 1st | 10 | 0.033756 | 2027-01-23 | 2027-02-02 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1750 | RO l Install of Computers & Related Peripherals 1st | 7 | 0.037075 | 2027-02-03 | 2027-02-10 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1715 | RO l Install of Network systems 1st | 8 | 0.023307 | 2027-02-11 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1725 | RO l Install of Data communication components 1st | 7 | 0.15242 | 2027-02-16 | 2027-02-24 | 0% | 0% | 0% | 0%
CO.RO.D27.1ST.1735 | RO l Install of Telecommunication outlets/connector 1st | 7 | 0.011002 | 2027-02-16 | 2027-02-24 | 0% | 0% | 0% | 0%
Electronic Safety And Security |  | 42 |  | 2027-01-09 | 2027-02-27
CO.RO.D28.1ST.1755 | RO l Install of Access control 1st & 2nd Fix 1st | 6 | 0.018189 | 2027-01-09 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D28.1ST.1765 | RO l Install of CCTV system 1st & 2nd Fix 1st | 6 | 0.029871 | 2027-01-09 | 2027-01-14 | 0% | 0% | 0% | 0%
CO.RO.D28.1ST.1775 | RO l Install of Fire alarm system 1st & 2nd Fix 1st | 10 | 0.018395 | 2027-01-09 | 2027-01-19 | 0% | 0% | 0% | 0%
CO.RO.D28.1ST.1770 | RO l Install of CCTV system 3nd Fix 1st | 9 | 0.024892 | 2027-02-16 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D28.1ST.1780 | RO l Install of Fire alarm system 3nd Fix 1st | 9 | 0.015329 | 2027-02-16 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D28.1ST.1760 | RO l Install of Access control 3nd Fix 1st | 9 | 0.015158 | 2027-02-16 | 2027-02-27 | 0% | 0% | 0% | 0%
Second Floor |  | 78 |  | 2026-12-03 | 2027-03-04
Existing Condition |  | 53 |  | 2026-12-03 | 2027-02-02
CO.RO.D03.2ND.1145 | RO l Steel fixing for Columns 2nd | 6 | 0.025527 | 2026-12-03 | 2026-12-09 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1140 | RO l Shuttering & Pouring for Columns 2nd | 6 | 0.03829 | 2026-12-10 | 2026-12-16 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1120 | RO l Shuttering for Slab 2nd | 7 | 0.13859 | 2026-12-17 | 2026-12-24 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1125 | RO l Steel fixing & Pouring for Slab 2nd | 7 | 0.20789 | 2026-12-26 | 2027-01-02 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1155 | RO l Deshuttering works for Slab 2nd | 12 | 0 | 2027-01-03 | 2027-01-16 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1160 | RO l Concete works for Roof screed 2nd | 7 | 0.019028 | 2027-01-17 | 2027-01-24 | 0% | 0% | 0% | 0%
CO.RO.D03.2ND.1165 | RO l Concete works for Floor screed 2nd | 7 | 0.030228 | 2027-01-26 | 2027-02-02 | 0% | 0% | 0% | 0%
Masonry Works |  | 8 |  | 2027-01-17 | 2027-01-25
CO.RO.D04.2ND.1170 | RO l Masonry works 2nd | 8 | 0.064715 | 2027-01-17 | 2027-01-25 | 0% | 0% | 0% | 0%
Metal Works |  | 27 |  | 2027-01-26 | 2027-02-27
CO.RO.D05.2ND.1190 | RO l Structural steel works 2nd | 10 | 0.23137 | 2027-01-26 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D05.2ND.1191 | RO l overhead crane | 10 | 0.038562 | 2027-01-26 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D05.2ND.1185 | RO l Install of Metal Ladders 2nd | 5 | 0.0064731 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D05.2ND.1180 | RO l Install of Handrail 2nd | 5 | 0.0084853 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D05.2ND.1175 | RO l Install of Steel covers 2nd | 5 | 0.080556 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
Thermal And Moisture Protection |  | 19 |  | 2027-01-25 | 2027-02-15
CO.RO.D07.2ND.1260 | RO l Roofing insulation System works 2nd | 5 | 0.14884 | 2027-01-25 | 2027-01-30 | 0% | 0% | 0% | 0%
CO.RO.D07.2ND.1230 | RO l Rockwool insulation works 2nd | 5 | 0.022972 | 2027-01-26 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D07.2ND.1235 | RO l Install of Concrete tiles 2nd | 4 | 0.034441 | 2027-01-31 | 2027-02-03 | 0% | 0% | 0% | 0%
CO.RO.D07.2ND.1265 | RO l Canopy aluminium panels cladding 2nd | 8 | 0.22959 | 2027-02-07 | 2027-02-15 | 0% | 0% | 0% | 0%
Openings |  | 6 |  | 2027-02-16 | 2027-02-23
CO.RO.D08.2ND.1250 | RO l Install of Steel doors 2nd | 2 | 0.010548 | 2027-02-16 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D08.2ND.1255 | RO l Install of Aluminum windows & Louvers 2nd | 4 | 0.020683 | 2027-02-16 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D08.2ND.1240 | RO l Install of Acoustic & Fire rated doors 2nd | 6 | 0.022458 | 2027-02-16 | 2027-02-23 | 0% | 0% | 0% | 0%
Finishes |  | 17 |  | 2027-01-26 | 2027-02-14
CO.RO.D09.2ND.1310 | RO l Internal Plaster works 2nd | 4 | 0.038202 | 2027-01-26 | 2027-01-30 | 0% | 0% | 0% | 0%
CO.RO.D09.2ND.1305 | RO l Floor epoxy painting 2nd | 5 | 0.021832 | 2027-02-03 | 2027-02-08 | 0% | 0% | 0% | 0%
CO.RO.D09.2ND.1280 | RO l Floor Ceramic tiles & Stones works 2nd | 6 | 0.016119 | 2027-02-03 | 2027-02-09 | 0% | 0% | 0% | 0%
CO.RO.D09.2ND.1275 | RO l Gypsum board ceiling works 2nd | 4 | 0.014881 | 2027-02-06 | 2027-02-09 | 0% | 0% | 0% | 0%
CO.RO.D09.2ND.1295 | RO l Wall epoxy painting 1st | 3 | 0.021469 | 2027-02-09 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D09.2ND.1290 | RO l Wall & Ceiling painting works 2nd | 4 | 0.049638 | 2027-02-10 | 2027-02-14 | 0% | 0% | 0% | 0%
Specialities |  | 4 |  | 2027-02-15 | 2027-02-18
CO.RO.D10.2ND.1335 | RO l Corner guards 2nd | 4 | 0.0046802 | 2027-02-15 | 2027-02-18 | 0% | 0% | 0% | 0%
CO.RO.D10.2ND.1330 | RO l Install of Fire Extinguisher 2nd | 4 | 0.0094786 | 2027-02-15 | 2027-02-18 | 0% | 0% | 0% | 0%
Fire Superssion |  | 25 |  | 2027-01-31 | 2027-03-01
CO.RO.D21.2ND.1415 | RO l Install of Fire Suppression standpipes 2nd | 5 | 0.052632 | 2027-01-31 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D21.2ND.1365 | RO l Install of Fire Suppression valves 2nd | 5 | 0.012488 | 2027-02-06 | 2027-02-10 | 0% | 0% | 0% | 0%
CO.RO.D21.2ND.1370 | RO l Install of Fire Hose Cabinets 2nd | 3 | 0.0042974 | 2027-02-11 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D21.2ND.1420 | RO l Install of Fire Suppersion Sprinkls 2nd | 7 | 0.0014639 | 2027-02-10 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D21.2ND.1385 | RO l Install of Clean Agent FK-5.1.12 System 2nd | 9 | 0.067672 | 2027-02-18 | 2027-03-01 | 0% | 0% | 0% | 0%
Plumbing |  | 27 |  | 2027-01-25 | 2027-02-25
CO.RO.D22.2ND.1440 | RO l Install of Sanitary Pipes 2nd | 5 | 0.012462 | 2027-01-26 | 2027-01-31 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1520 | RO l Install of Vibration & Seismic controls For Plumbing 2nd | 8 | 0.2599 | 2027-01-25 | 2027-02-02 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1480 | RO l Install of Sanitary drains & Cleanouts 2nd | 3 | 0.0059606 | 2027-02-01 | 2027-02-03 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1490 | RO l Install of Domestic water pipes 2nd | 6 | 0.00836 | 2027-02-01 | 2027-02-07 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1500 | RO l Install of Domestic Water Packaged Booster Pumpsr 2nd | 6 | 0.007736 | 2027-02-03 | 2027-02-09 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1495 | RO l Install of Electrical water heater 2nd | 4 | 0.020111 | 2027-02-08 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1470 | RO l Install of Plumbing pipes insulation 2nd | 4 | 0.0050986 | 2027-02-08 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1475 | RO l Install of General Duty Plumbing Valves 2nd | 6 | 0.0022368 | 2027-02-08 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1505 | RO l Install of Circulating Pumps 2nd | 6 | 0.011052 | 2027-02-10 | 2027-02-16 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1510 | RO l Install of GRP water tank 2nd | 3 | 0.0037082 | 2027-02-17 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D22.2ND.1515 | RO l Install of Water Filters 2nd | 4 | 0.029691 | 2027-02-21 | 2027-02-25 | 0% | 0% | 0% | 0%
Heating, Ventilating And Air Conditioning |  | 30 |  | 2027-01-25 | 2027-03-01
CO.RO.D23.2ND.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works 2nd | 7 | 0.040719 | 2027-01-25 | 2027-02-01 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1575 | RO l Install of Hydronic pipes 2nd | 5 | 0.016883 | 2027-01-31 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1535 | RO l Install of Condensate drain pipes 2nd | 5 | 0.002165 | 2027-01-31 | 2027-02-04 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1590 | RO l Install of HVAC Metal ducts 2nd | 7 | 0.039227 | 2027-01-31 | 2027-02-07 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1540 | RO l Install of Chilled water Pipes Insulation 2nd | 4 | 0.017486 | 2027-02-06 | 2027-02-09 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1600 | RO l Install of Exhaust Fans 2nd | 4 | 0.011122 | 2027-02-08 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1595 | RO l Install of Air Handlig Units 2nd | 10 | 0.147 | 2027-02-02 | 2027-02-13 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1545 | RO l Install of Genetal duty HVAC valves 2nd | 7 | 0.015108 | 2027-02-06 | 2027-02-13 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1560 | RO l Install of HVAC Flexible ducts 2nd | 5 | 0.060023 | 2027-02-08 | 2027-02-13 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles 1st | 4 | 0.014352 | 2027-02-10 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1580 | RO l Install of Ducts thermal insulation 2nd | 3 | 0.034688 | 2027-02-14 | 2027-02-16 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1530 | RO l Install of HVAC dampers 2nd | 4 | 0.013424 | 2027-02-14 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1565 | RO l Install of Split & Fan coil Units 2nd | 6 | 0.0057234 | 2027-02-14 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D23.2ND.1525 | RO l HVAC Monitoring and Controlling System 2nd | 7 | 0.068501 | 2027-02-21 | 2027-03-01 | 0% | 0% | 0% | 0%
Electrical |  | 28 |  | 2027-01-31 | 2027-03-04
CO.RO.D26.2ND.1680 | RO l Install of Cable tray and trunk 2nd | 6 | 0.023111 | 2027-01-31 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1690 | RO l Install of Low voltage electrical power conductors 2nd | 5 | 0.090916 | 2027-02-07 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1685 | RO l Install of Low voltage electrical power Cables 2nd | 5 | 0.15066 | 2027-02-07 | 2027-02-11 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1645 | RO l Install of Lightning & Earthing Protection Systems 2nd | 5 | 0.023511 | 2027-02-13 | 2027-02-17 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1670 | RO l Install of Disconnecting Switches 2nd | 6 | 0.014088 | 2027-02-13 | 2027-02-18 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1660 | RO l Install of Sochets & lighting switches 2nd | 6 | 0.011395 | 2027-02-15 | 2027-02-21 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1675 | RO l Install of Interior lighting 2nd | 6 | 0.019483 | 2027-02-15 | 2027-02-21 | 0% | 0% | 0% | 0%
CO.RO.D26.2ND.1665 | RO l Install of Network lighting control system 2nd | 5 | 0.040059 | 2027-02-28 | 2027-03-04 | 0% | 0% | 0% | 0%
Communication System |  | 17 |  | 2027-02-07 | 2027-02-27
CO.RO.D27.2ND.1730 | RO l Install of Communication Cables 2nd | 7 | 0.020462 | 2027-02-07 | 2027-02-14 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1745 | RO l Install of IP Based telephony communication system 2nd | 5 | 0.015945 | 2027-02-15 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1720 | RO l Install of Communication equipment room fitting 2nd | 6 | 0.016878 | 2027-02-15 | 2027-02-21 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1725 | RO l Install of Data communication components 2nd | 6 | 0.076209 | 2027-02-15 | 2027-02-21 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1740 | RO l Install of Wireless data network components 2nd | 7 | 0.023094 | 2027-02-15 | 2027-02-23 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1715 | RO l Install of Network systems 2nd | 4 | 0.011653 | 2027-02-23 | 2027-02-27 | 0% | 0% | 0% | 0%
CO.RO.D27.2ND.1735 | RO l Install of Telecommunication outlets/connector 2nd | 4 | 0.005501 | 2027-02-23 | 2027-02-27 | 0% | 0% | 0% | 0%
Electronic Safety And Security |  | 23 |  | 2027-01-31 | 2027-02-27
CO.RO.D28.2ND.1755 | RO l Install of Access control 1st & 2nd Fix 2nd | 6 | 0.018189 | 2027-01-31 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D28.2ND.1765 | RO l Install of CCTV system 1st & 2nd Fix 2nd | 6 | 0.029871 | 2027-01-31 | 2027-02-06 | 0% | 0% | 0% | 0%
CO.RO.D28.2ND.1775 | RO l Install of Fire alarm system 1st & 2nd Fix 2nd | 10 | 0.018395 | 2027-01-31 | 2027-02-10 | 0% | 0% | 0% | 0%
CO.RO.D28.2ND.1760 | RO l Install of Access control 3nd Fix 2nd | 5 | 0.015158 | 2027-02-15 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D28.2ND.1770 | RO l Install of CCTV system 3nd Fix 2nd | 5 | 0.024892 | 2027-02-15 | 2027-02-20 | 0% | 0% | 0% | 0%
CO.RO.D28.2ND.1780 | RO l Install of Fire alarm system 3nd Fix 1st | 5 | 0.015329 | 2027-02-21 | 2027-02-27 | 0% | 0% | 0% | 0%
External Work |  | 414 |  | 2025-10-25 | 2027-03-01
Earthworks |  | 12 |  | 2025-10-25 | 2025-11-06
CO.RO.D31.0EX.1050 | RO l Site clearing wrosk EX | 12 | 0.058809 | 2025-10-25 | 2025-11-06 | 100% | 100% | 0% | 100%
Masonary works |  | 6 |  | 2027-01-17 | 2027-01-23
CO.RO.D04.0EX.1205 | RO l Stone cladding EX | 6 | 0.29194 | 2027-01-17 | 2027-01-23 | 0% | 0% | 0% | 0%
Thermal And Moisture Protection |  | 12 |  | 2027-02-04 | 2027-02-17
CO.RO.D07.0EX.1270 | RO l aluminium panels cladding EX | 12 | 0.34243 | 2027-02-04 | 2027-02-17 | 0% | 0% | 0% | 0%
Finishes |  | 32 |  | 2026-12-29 | 2027-02-03
CO.RO.D09.0EX.1320 | RO l Plaster works EX | 16 | 0.05936 | 2026-12-29 | 2027-01-16 | 0% | 0% | 0% | 0%
CO.RO.D09.0EX.1325 | RO l painting works EX | 16 | 0.020042 | 2027-01-17 | 2027-02-03 | 0% | 0% | 0% | 0%
Conveying System |  | 9 |  | 2027-02-18 | 2027-03-01
CO.RO.D14.0GN.1355 | RO l Elevators GN | 9 | 0.063022 | 2027-02-18 | 2027-03-01 | 0% | 0% | 0% | 0%
CO.RO.D14.0GN.1356 | RO l Submersibl Pump for Elevator GN | 9 | 0.0070024 | 2027-02-18 | 2027-03-01 | 0% | 0% | 0% | 0%
Electrical |  | 14 |  | 2027-02-04 | 2027-02-20
CO.RO.D26.0EX.1710 | RO l Install of Exterior lighting EX | 14 | 0.018654 | 2027-02-04 | 2027-02-20 | 0% | 0% | 0% | 0%
Exterior Improvement |  | 46 |  | 2026-12-10 | 2027-02-01
CO.RO.D32.0EX.1790 | RO l Install of Precast concrete wall EX | 17 | 0.26852 | 2026-12-10 | 2026-12-29 | 0% | 0% | 0% | 0%
CO.RO.D32.0EX.1791 | RO l Wayfinding works EX | 10 | 0.067129 | 2026-12-30 | 2027-01-10 | 0% | 0% | 0% | 0%
CO.RO.D32.0EX.1785 | RO l Install of Sliding gates EX | 8 | 0.046272 | 2027-01-11 | 2027-01-19 | 0% | 0% | 0% | 0%
CO.RO.D32.0EX.1800 | RO l Precast concrete paving works EX | 11 | 0.071172 | 2027-01-11 | 2027-01-23 | 0% | 0% | 0% | 0%
CO.RO.D32.0EX.1795 | RO l Road works EX | 17 | 0.040101 | 2027-01-11 | 2027-01-30 | 0% | 0% | 0% | 0%
CO.RO.D32.0EX.1801 | RO l Car Park shade EX | 8 | 0.017793 | 2027-01-24 | 2027-02-01 | 0% | 0% | 0% | 0%
Process Scada System And Instrumentation |  | 6 |  | 2027-02-20 | 2027-02-27
CO.RO.D40.0GN.1810 | RO l Process scada system and intrumentation GN | 6 | 0.25122 | 2027-02-20 | 2027-02-27 | 0% | 0% | 0% | 0%
Pump-Station |  | 296 |  | 2026-01-06 | 2026-12-26 | 19.8% | 39.71% | 0.05348% | 39.76%
Electrical Room |  | 284 |  | 2026-01-20 | 2026-12-26
Existing Condition |  | 12 |  | 2026-01-20 | 2026-02-02
CO.PS.D02.ELC.1000 | IPS l Geotechnical Investigations works | 12 | 0.0050206 | 2026-01-20 | 2026-02-02 | 100% | 100% | 0% | 100%
Earthwork |  | 117 |  | 2026-02-03 | 2026-06-27
CO.PS.D31.ELC.1010 | IPS l Site clearing works | 8 | 0.0093953 | 2026-02-03 | 2026-02-11 | 12.5% | 100% | 0% | 100%
CO.PS.D31.ELC.1020 | IPS l Piles rainforced concrete works | 17 | 0.035395 | 2026-05-09 | 2026-05-31 | 0% | 100% | 0% | 100%
CO.PS.D31.ELC.1015 | IPS l Excavation Works | 12 | 0.0029439 | 2026-06-01 | 2026-06-14 | 0% | 100% | 0% | 100%
CO.PS.D31.ELC.1005 | IPS l Under Foundation Probe Holes works | 11 | 0.0073991 | 2026-06-15 | 2026-06-27 | 0% | 100% | 0% | 100%
Concrete Work |  | 71 |  | 2026-06-30 | 2026-09-20
CO.PS.D03.ELC.1030 | IPS l Plain Concrete works for foundation | 5 | 0.0010285 | 2026-06-30 | 2026-07-05 | 0% | 100% | 0% | 100%
CO.PS.D03.ELC.1040 | IPS l Concrete works for Isolated footings | 14 | 0.0041089 | 2026-07-06 | 2026-07-21 | 0% | 100% | 0% | 100%
CO.PS.D03.ELC.1045 | IPS l Concrete works for Columns neck & Ground beams | 6 | 0.0041083 | 2026-07-22 | 2026-07-28 | 0% | 100% | 0% | 100%
CO.PS.D03.ELC.1035 | IPS l Concrete works for Slab on grade | 5 | 0.0073917 | 2026-08-03 | 2026-08-08 | 100% | 100% | 0% | 100%
CO.PS.D03.ELC.1050 | IPS l Concrete works for Columns | 7 | 0.0040201 | 2026-08-09 | 2026-08-16 | 100% | 100% | 0% | 100%
CO.PS.D03.ELC.1055 | IPS l Concrete works for Slabs | 12 | 0.015885 | 2026-08-17 | 2026-08-30 | 100% | 100% | 0% | 100%
CO.PS.D03.ELC.1065 | IPS l Deshuttering works for Slabs | 14 | 0 | 2026-08-31 | 2026-09-15 | 100% | 100% | 0% | 100%
CO.PS.D03.ELC.1060 | IPS l Concrete works for Roof screed | 4 | 0.0021268 | 2026-09-16 | 2026-09-20 | 100% | 100% | 0% | 100%
Masonry Works |  | 6 |  | 2026-09-16 | 2026-09-22
CO.PS.D04.ELC.1170 | IPS l Masonry works | 6 | 0.010917 | 2026-09-16 | 2026-09-22 | 100% | 100% | 0% | 100%
Metal Works |  | 2 |  | 2026-11-05 | 2026-11-07
CO.PS.D05.ELC.1185 | IPS l Install of Metal ladder | 2 | 0.0040375 | 2026-11-05 | 2026-11-07 | 0% | 0% | 0% | 0%
Thermal And Moisture Protection |  | 121 |  | 2026-06-28 | 2026-11-16
CO.PS.D07.ELC.1215 | IPS l Install of HDPE Waterproofing Sheets | 2 | 0.0071291 | 2026-06-28 | 2026-06-29 | 100% | 100% | 0% | 100%
CO.PS.D07.ELC.1210 | IPS l Foundation Waterproofing works | 4 | 0.001209 | 2026-07-29 | 2026-08-02 | 0% | 100% | 0% | 100%
CO.PS.D07.ELC.1260 | IPS l Roofing System works | 7 | 0.0082517 | 2026-09-21 | 2026-09-29 | 100% | 100% | 0% | 100%
CO.PS.D07.ELC.1235 | IPS l Terrazzo Tiles works | 4 | 0.0028904 | 2026-09-30 | 2026-10-04 | 0% | 90% | 10% | 100%
CO.PS.D07.ELC.1265 | IPS l Install of aluminum cladding | 14 | 0.042397 | 2026-11-01 | 2026-11-16 | 0% | 0% | 0% | 0%
Openings |  | 4 |  | 2026-11-01 | 2026-11-04
CO.PS.D08.ELC.1255 | IPS l Install of Aluminium louvers | 4 | 0.007157 | 2026-11-01 | 2026-11-04 | 0% | 0% | 0% | 0%
CO.PS.D08.ELC.1250 | IPS l Install of Steel doors | 4 | 0.010521 | 2026-11-01 | 2026-11-04 | 0% | 0% | 0% | 0%
Finishes |  | 24 |  | 2026-10-04 | 2026-10-31
CO.PS.D09.ELC.1310 | IPS l Plaster works | 7 | 0.0052187 | 2026-10-04 | 2026-10-11 | 100% | 100% | 0% | 100%
CO.PS.D09.ELC.1305 | IPS l Floor Epoxy Painting works | 7 | 0.0019552 | 2026-10-12 | 2026-10-19 | 0% | 10% | -10% | 0%
CO.PS.D09.ELC.1290 | IPS l Painting works | 10 | 0.0058862 | 2026-10-20 | 2026-10-31 | 0% | 30% | 15% | 45%
Specialties |  | 3 |  | 2026-11-01 | 2026-11-03
CO.PS.D10.ELC.1330 | IPS l Install of Fire Extinguisher | 3 | 0.0012094 | 2026-11-01 | 2026-11-03 | 0% | 0% | 0% | 0%
Fire Suppression |  | 12 |  | 2026-11-01 | 2026-11-14
CO.PS.D21.ELC.1385 | IPS l Install of Clean Agent FK-5.1.12 cylinders | 12 | 0.030517 | 2026-11-01 | 2026-11-14 | 0% | 0% | 0% | 0%
Plumbing |  | 4 |  | 2026-09-24 | 2026-09-28
CO.PS.D22.ELC.1475 | IPS l Install of Plumbing pipes & valves | 4 | 0.0046449 | 2026-09-24 | 2026-09-28 | 0% | 0% | 0% | 0%
Heating, Ventilating And Air Conditioning |  | 10 |  | 2026-11-01 | 2026-11-11
CO.PS.D23.ELC.1590 | IPS l Install of HVAC Field Instrumentation | 6 | 0.023072 | 2026-11-01 | 2026-11-07 | 0% | 0% | 0% | 0%
CO.PS.D23.ELC.1565 | IPS l Install of Split units | 4 | 0.0024988 | 2026-11-08 | 2026-11-11 | 0% | 0% | 0% | 0%
Electrical |  | 89 |  | 2026-08-09 | 2026-11-21
CO.PS.D26.ELC.1680 | IPS l Underground cable duct, manholes and trench works | 3 | 0.026889 | 2026-08-09 | 2026-08-11 | 100% | 70% | 0% | 70% |  | Waiting the Backfilling works
CO.PS.D26.ELC.1655 | IPS l Coordination for connection of electrical supply | 4 | 0.10296 | 2026-08-12 | 2026-08-16 | 0% | 0% | 0% | 0% |  | coordination done,approved by client.next step final shop drawing will be submitted this week
CO.PS.D26.ELC.1685 | IPS l Install of Low voltage cables & conductors | 4 | 0.02636 | 2026-09-03 | 2026-09-07 | 0% | 0% | 0% | 0%
CO.PS.D26.ELC.1645 | IPS l Install of Grounding and Bonding for Electrical Systems | 4 | 0.021539 | 2026-09-08 | 2026-09-12 | 0% | 10% | 0% | 10%
CO.PS.D26.ELC.1670 | IPS l Install of Power Factor Corrections Capacitors | 11 | 0.030591 | 2026-10-03 | 2026-10-14 | 0% | 0% | 0% | 0%
CO.PS.D26.ELC.1695 | IPS l Install of Main distribution board (MDB) | 8 | 0.0077348 | 2026-10-15 | 2026-10-24 | 0% | 0% | 0% | 0%
CO.PS.D26.ELC.1635 | IPS l Install of Distribution and power panel boards | 6 | 0.019867 | 2026-10-25 | 2026-10-31 | 0% | 0% | 0% | 0%
CO.PS.D26.ELC.1660 | IPS l Install of Switches & Socket outlets | 4 | 0.0025824 | 2026-11-01 | 2026-11-04 | 0% | 20% | 0% | 20%
CO.PS.D26.ELC.1630 | IPS l Install of Motor control Centers (MCC) | 5 | 0.0050723 | 2026-11-01 | 2026-11-05 | 0% | 0% | 0% | 0%
CO.PS.D26.ELC.1675 | IPS l Install of Lighting fixtures | 4 | 0.008256 | 2026-11-17 | 2026-11-21 | 0% | 20% | 0% | 20%
Communication System |  | 23 |  | 2026-11-01 | 2026-11-26
CO.PS.D27.ELC.1720 | IPS l Install of Communication equipment room fitting | 4 | 0.030732 | 2026-11-01 | 2026-11-04 | 0% | 0% | 0% | 0%
CO.PS.D27.ELC.1725 | IPS l Install of Data communication components | 4 | 0.052994 | 2026-11-05 | 2026-11-09 | 0% | 0% | 0% | 0%
CO.PS.D27.ELC.1740 | IPS l Install of Wireless data network components | 5 | 0.016608 | 2026-11-10 | 2026-11-15 | 0% | 0% | 0% | 0%
CO.PS.D27.ELC.1745 | IPS l Install of IP Based telephony communication system | 4 | 0.0067291 | 2026-11-16 | 2026-11-19 | 0% | 0% | 0% | 0%
CO.PS.D27.ELC.1715 | IPS l Install of Network Systems | 6 | 0.017758 | 2026-11-21 | 2026-11-26 | 0% | 0% | 0% | 0%
Electronic Safety And Security |  | 50 |  | 2026-09-24 | 2026-11-21
CO.PS.D28.ELC.1755 | IPS l Install of Access control 1st & 2nd Fix | 5 | 0.0059673 | 2026-09-24 | 2026-09-29 | 100% | 25% | 0% | 25%
CO.PS.D28.ELC.1765 | IPS l Install of CCTV system 1st & 2nd Fix | 5 | 0.0075808 | 2026-09-24 | 2026-09-29 | 0% | 0% | 0% | 0%
CO.PS.D28.ELC.1775 | IPS l Install of Fire alarm system 1st & 2nd Fix | 8 | 0.0055221 | 2026-09-24 | 2026-10-03 | 100% | 25% | 0% | 25%
CO.PS.D28.ELC.1780 | IPS l Install of Fire alarm system 3nd Fix | 8 | 0.0036814 | 2026-11-01 | 2026-11-09 | 0% | 0% | 0% | 0%
CO.PS.D28.ELC.1760 | IPS l Install of Access control 3nd Fix | 4 | 0.0039782 | 2026-11-05 | 2026-11-09 | 0% | 0% | 0% | 0%
CO.PS.D28.ELC.1770 | IPS l Install of CCTV system 3nd Fix | 4 | 0.0050539 | 2026-11-17 | 2026-11-21 | 0% | 0% | 0% | 0%
Process Scada System And Instrumentation |  | 8 |  | 2026-12-17 | 2026-12-26
CO.PS.D40.ELC.1810 | IPS l Process Control Systems | 8 | 0.10879 | 2026-12-17 | 2026-12-26 | 0% | 0% | 0% | 0%
Pump Room |  | 273 |  | 2026-01-06 | 2026-11-29
Existing Condition |  | 12 |  | 2026-01-06 | 2026-01-19
CO.PS.D02.PUM.1000 | IPS l Geotechnical Investigations works | 12 | 0.0050206 | 2026-01-06 | 2026-01-19 | 100% | 100% | 0% | 100%
EARTHWORK |  | 103 |  | 2026-01-20 | 2026-05-24
CO.PS.D31.PUM.1010 | IPS l Site clearing works | 10 | 0.0093953 | 2026-01-20 | 2026-01-31 | 100% | 100% | 0% | 100%
CO.PS.D31.PUM.1020 | IPS l Piles rainforced concrete works | 14 | 0.14158 | 2026-04-22 | 2026-05-07 | 0% | 100% | 0% | 100%
CO.PS.D31.PUM.1025 | IPS l Groundwater Control System works | 10 | 0.21365 | 2026-05-09 | 2026-05-19 | 100% | 90% | 0% | 90%
CO.PS.D31.PUM.1015 | IPS l Excavation Works | 10 | 0.011776 | 2026-05-09 | 2026-05-19 | 0% | 100% | 0% | 100%
CO.PS.D31.PUM.1005 | IPS l Under Foundation Probe Holes works | 4 | 0.0073991 | 2026-05-20 | 2026-05-24 | 0% | 100% | 0% | 100%
Concrete Work |  | 86 |  | 2026-06-03 | 2026-09-10
CO.PS.D03.PUM.1070 | IPS l Plain Concrete works for foundation stage (1) | 4 | 0.0010285 | 2026-06-03 | 2026-06-07 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1080 | IPS l Concrete works for Foundation stage (1) | 7 | 0.015028 | 2026-06-08 | 2026-06-15 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1090 | IPS l Concrete works for Basement walls stage (1) | 14 | 0.043102 | 2026-06-16 | 2026-07-01 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1075 | IPS l Plain Concrete works for foundation stage (2) | 4 | 0.0013713 | 2026-07-08 | 2026-07-12 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1085 | IPS l Concrete works for Foundation stage (2) | 7 | 0.022543 | 2026-07-13 | 2026-07-20 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1095 | IPS l Concrete works for Basement walls stage (2) | 14 | 0.064653 | 2026-07-21 | 2026-08-05 | 0% | 100% | 0% | 100%
CO.PS.D03.PUM.1055 | IPS l Concrete works for Slabs | 10 | 0.015885 | 2026-08-06 | 2026-08-17 | 100% | 100% | 0% | 100%
CO.PS.D03.PUM.1105 | IPS l Deshuttering works for Slabs | 14 | 0 | 2026-08-18 | 2026-09-02 | 100% | 100% | 0% | 100%
CO.PS.D03.PUM.1065 | IPS l Concrete works for Floors screed works | 7 | 0.0040133 | 2026-09-03 | 2026-09-10 | 100% | 70% | 0% | 70%
Metal Works |  | 4 |  | 2026-09-12 | 2026-09-15
CO.PS.D05.PUM.1175 | IPS l Install of Trench covers | 4 | 0.031578 | 2026-09-12 | 2026-09-15 | 0% | 0% | 0% | 0%
Wood & Plastics |  | 4 |  | 2026-09-12 | 2026-09-15
CO.PS.D06.PUM.1195 | IPS l Install of GRB ladders | 4 | 0.0039934 | 2026-09-12 | 2026-09-15 | 0% | 0% | 0% | 0%
Thermal & Moisture Protection |  | 94 |  | 2026-05-25 | 2026-09-14
CO.PS.D07.PUM.1215 | IPS l Install of HDPE Waterproofing Sheets stage (1) | 5 | 0.0071291 | 2026-05-25 | 2026-06-02 | 0% | 100% | 0% | 100%
CO.PS.D07.PUM.1225 | IPS l Install of HDPE Waterproofing Sheets stage (2) | 5 | 0.0095054 | 2026-07-02 | 2026-07-07 | 0% | 100% | 0% | 100%
CO.PS.D07.PUM.1220 | IPS l Basement wall Waterproofing works | 10 | 0.0024391 | 2026-09-03 | 2026-09-14 | 100% | 30% | 0% | 30%
Plumbing |  | 28 |  | 2026-09-03 | 2026-10-06
CO.PS.D22.PUM.1490 | IPS l Install of GRP Domestic Water Pipes | 6 | 0.033386 | 2026-09-03 | 2026-09-09 | 0% | 30% | 0% | 30%
CO.PS.D22.PUM.1475 | IPS l Install of General Duty Plumbing Valves | 8 | 0.11799 | 2026-09-10 | 2026-09-19 | 0% | 0% | 0% | 0%
CO.PS.D22.PUM.1815 | IPS l Install of Flow meter | 6 | 0.019119 | 2026-09-20 | 2026-09-27 | 0% | 0% | 0% | 0%
CO.PS.D22.PUM.1505 | IPS l Install of Submersible sump pumps | 8 | 0.012795 | 2026-09-28 | 2026-10-06 | 0% | 0% | 0% | 0%
Heating, Ventilation & Air Conditioning |  | 4 |  | 2026-10-08 | 2026-10-12
CO.PS.D23.PUM.1600 | IPS l Install of Exhaust Fans | 4 | 0.0036465 | 2026-10-08 | 2026-10-12 | 0% | 0% | 0% | 0%
Electrical |  | 70 |  | 2026-09-08 | 2026-11-29
CO.PS.D26.PUM.1685 | IPS l Install of Low voltage cables & conductors | 5 | 0.011297 | 2026-09-08 | 2026-09-13 | 0% | 0% | 0% | 0%
CO.PS.D26.PUM.1695 | IPS l Install of Lighting fixtures | 7 | 0.0035383 | 2026-11-22 | 2026-11-29 | 0% | 0% | 0% | 0%
Electronic Safety & Security |  | 42 |  | 2026-10-04 | 2026-11-21
CO.PS.D28.PUM.1775 | IPS l Install of Fire alarm system 1st & 2nd Fix | 10 | 0.0055221 | 2026-10-04 | 2026-10-14 | 100% | 30% | 0% | 30%
CO.PS.D28.PUM.1780 | IPS l Install of Fire alarm system 3nd Fix | 10 | 0.0036814 | 2026-11-10 | 2026-11-21 | 0% | 0% | 0% | 0%
Pump-Station ( External Works ) |  | 33 |  | 2026-11-17 | 2026-12-24
Special Constrction |  | 8 |  | 2026-11-17 | 2026-11-25
CO.PS.D13.0EX.1270 | IPS l Install of Aluminium Control booths | 8 | 0.010261 | 2026-11-17 | 2026-11-25 | 0% | 0% | 0% | 0%
Exterior Improvement |  | 25 |  | 2026-11-26 | 2026-12-24
CO.PS.D32.0EX.1790 | IPS l Install of Precast concrete wall | 10 | 0.12123 | 2026-11-26 | 2026-12-07 | 0% | 0% | 0% | 0%
CO.PS.D32.0EX.1800 | IPS l Pre-cast concrete paving works | 4 | 0.019175 | 2026-12-08 | 2026-12-12 | 0% | 0% | 0% | 0%
CO.PS.D32.0EX.1785 | IPS l Install of Sliding gates | 5 | 0.021979 | 2026-12-08 | 2026-12-13 | 0% | 0% | 0% | 0%
CO.PS.D32.0EX.1805 | IPS l Install of Precast concrete curb | 6 | 0.0041211 | 2026-12-13 | 2026-12-19 | 0% | 0% | 0% | 0%
CO.PS.D32.0EX.1820 | IPS l Planting works | 5 | 0.041449 | 2026-12-20 | 2026-12-24 | 0% | 0% | 0% | 0%
Collection System |  | 284 |  | 2026-02-14 | 2027-01-19 | 6.621% | 33.12% | 0% | 33.12%
Plumbing |  | 284 |  | 2026-02-14 | 2027-01-19
Pumps inside Parcels |  | 237 |  | 2026-02-14 | 2026-11-25
CO.CL.D22.0EX.1040 | CLS l Pump room MEC Piping& fitting P5.02 | 10 | 0.0050889 | 2026-02-14 | 2026-02-25 | 0% | 85% | 0% | 85% |  | Method of statement for pump assessment under review 25-08-2026
CO.CL.D22.0EX.1045 | CLS l Pump room MEC Piping& fitting P2.15 | 10 | 0.0050889 | 2026-02-26 | 2026-03-09 | 0% | 85% | 0% | 85% |  | Pump delivery delay 15-12-2026
CO.CL.D22.0EX.1050 | CLS l Pump room MEC Piping& fitting P5.03 | 10 | 0.0050889 | 2026-03-10 | 2026-03-24 | 0% | 85% | 0% | 85% |  | Pump delivery delay 29 -09-2026
CO.CL.D22.0EX.1055 | CLS l Pump room MEC Piping& fitting P5.04 | 10 | 0.0050889 | 2026-03-25 | 2026-04-05 | 0% | 85% | 0% | 85% |  | Method of statement for pump assessment under review 03-09-2026
CO.CL.D22.0EX.1060 | CLS l Pump room MEC Piping& fitting P5.05 | 10 | 0.0050889 | 2026-04-06 | 2026-04-16 | 0% | 85% | 0% | 85% |  | Method of statement for pump assessment under review 10-09-2026
CO.CL.D22.0EX.1065 | CLS l Pump room MEC Piping& fitting P2.09 | 10 | 0.0050889 | 2026-04-18 | 2026-04-28 | 0% | 85% | 0% | 85% |  | Pump delivery delay 25 -09-2026
CO.CL.D22.0EX.1070 | CLS l Pump room MEC Piping& fitting P4.11 | 10 | 0.0050889 | 2026-04-29 | 2026-05-10 | 0% | 85% | 0% | 85% |  | Pump delivery delay 30 -09-2026
CO.CL.D22.0EX.1075 | CLS l Pump room MEC Piping& fitting P3.09 | 10 | 0.0050889 | 2026-05-11 | 2026-05-21 | 0% | 85% | 0% | 85% |  | Method of statement for pump assessment under review 23-09-2026
CO.CL.D22.0EX.1120 | CLS l Civil works For Pump room P5.02 | 7 | 0.0010178 | 2026-05-23 | 2026-06-02 | 0% | 90% | 0% | 90% |  | Method of statement for pump assessment under review 23-09-2026
CO.CL.D22.0EX.1076 | CLS l Pump room MEC Piping& fitting P1.11 | 10 | 0.0050889 | 2026-05-23 | 2026-06-06 | 0% | 85% | 0% | 85% |  | Pump delivery delay 30 -08-2026
CO.CL.D22.0EX.1078 | CLS l Pump room MEC Piping& fitting P5.01 | 10 | 0.0050889 | 2026-05-23 | 2026-06-06 | 0% | 85% | 0% | 85% |  | Method of satatment for pump assassment under review 30-09-2026
CO.CL.D22.0EX.1125 | CLS l Civil works For Pump room P2.15 | 7 | 0.0010178 | 2026-06-03 | 2026-06-10 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1021 | CLS l Valve works For Piping P5.02 | 7 | 0.0020356 | 2026-06-03 | 2026-06-10 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1077 | CLS l Pump room MEC Piping& fitting P3.10 | 10 | 0.0050889 | 2026-06-07 | 2026-06-17 | 100% | 85% | 0% | 85% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1079 | CLS l Pump room MEC Piping& fitting P5.06 | 10 | 0.0050889 | 2026-06-07 | 2026-06-17 | 100% | 85% | 0% | 85% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1130 | CLS l Civil works For Pump room P5.03 | 7 | 0.0010178 | 2026-06-11 | 2026-06-18 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1022 | CLS l Valve works For Piping P2.15 | 7 | 0.0020356 | 2026-06-11 | 2026-06-18 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1135 | CLS l Civil works For Pump room P5.04 | 7 | 0.0010178 | 2026-06-20 | 2026-06-27 | 0% | 90% | 0% | 90%
CO.CL.D22.0EX.1023 | CLS l Valve works For Piping P5.03 | 7 | 0.0020356 | 2026-06-20 | 2026-06-27 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1024 | CLS l Valve works For Piping P5.04 | 7 | 0.0020356 | 2026-06-20 | 2026-06-27 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1071 | CLS l Pump room MEC Piping& fitting P3.11 | 10 | 0.0050889 | 2026-06-18 | 2026-06-29 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1140 | CLS l Civil works For Pump room P5.05 | 7 | 0.0010178 | 2026-06-28 | 2026-07-05 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1145 | CLS l Civil works For Pump room P2.09 | 7 | 0.0010178 | 2026-07-06 | 2026-07-13 | 0% | 90% | 0% | 90%
CO.CL.D22.0EX.1150 | CLS l Civil works For Pump room P4.11 | 7 | 0.0010178 | 2026-07-14 | 2026-07-21 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1155 | CLS l Civil works For Pump room P3.09 | 7 | 0.0010178 | 2026-07-22 | 2026-07-29 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1083 | CLS l Civil works For Pump room P5.01 | 7 | 0.0010178 | 2026-07-22 | 2026-07-29 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1084 | CLS l Civil works For Pump room P5.06 | 7 | 0.0010178 | 2026-07-22 | 2026-07-29 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1086 | CLS l Civil works For Pump room P3.11 | 7 | 0.0010178 | 2026-07-22 | 2026-07-29 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1026 | CLS l Valve works For Piping P5.05 | 7 | 0.0020356 | 2026-07-22 | 2026-07-29 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1029 | CLS l Valve works For Piping P3.09 | 7 | 0.0020356 | 2026-07-30 | 2026-08-06 | 0% | 0% | 0% | 0% |  | Valve will be supply 15-09-2026 and compleate supply 15-11-2026
CO.CL.D22.0EX.1081 | CLS l Civil works For Pump room P1.11 | 7 | 0.0010178 | 2026-08-08 | 2026-08-15 | 100% | 100% | 0% | 100%
CO.CL.D22.0EX.1082 | CLS l Civil works For Pump room P3.10 | 7 | 0.0010178 | 2026-08-16 | 2026-08-23 | 100% | 90% | 0% | 90%
CO.CL.D22.0EX.1027 | CLS l Valve works For Piping P2.09 | 7 | 0.0020356 | 2026-08-16 | 2026-08-23 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1028 | CLS l Valve works For Piping P4.11 | 7 | 0.0020356 | 2026-08-24 | 2026-08-31 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1031 | CLS l Valve works For Piping P1.11 | 7 | 0.0020356 | 2026-08-24 | 2026-08-31 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1034 | CLS l Valve works For Piping P5.06 | 7 | 0.0020356 | 2026-08-24 | 2026-08-31 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1000 | CLS l Install of Submersible pumps P2.15 | 8 | 0.028352 | 2026-08-24 | 2026-09-01 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1080 | CLS l Pump room Electrical connection P5.02 | 6 | 0.0020356 | 2026-09-02 | 2026-09-08 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1032 | CLS l Valve works For Piping P3.10 | 7 | 0.0020356 | 2026-09-01 | 2026-09-08 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1041 | CLS l Valve works For Piping P3.11 | 7 | 0.0020356 | 2026-09-01 | 2026-09-08 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1005 | CLS l Install of Submersible pumps P5.03 | 8 | 0.028352 | 2026-09-02 | 2026-09-10 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1033 | CLS l Valve works For Piping P5.01 | 7 | 0.0020356 | 2026-09-09 | 2026-09-16 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1085 | CLS l Pump room Electrical connection P2.15 | 6 | 0.0020356 | 2026-09-12 | 2026-09-17 | 100% | 20% | 0% | 20%
CO.CL.D22.0EX.1010 | CLS l Install of Submersible pumps P2.09 | 8 | 0.028352 | 2026-09-12 | 2026-09-20 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1090 | CLS l Pump room Electrical connection P5.03 | 6 | 0.0020356 | 2026-09-21 | 2026-09-28 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1015 | CLS l Install of Submersible pumps P4.11 | 8 | 0.028352 | 2026-09-21 | 2026-09-30 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1095 | CLS l Pump room Electrical connection P5.04 | 6 | 0.0020356 | 2026-10-01 | 2026-10-07 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1020 | CLS l Install of Submersible pumps P1.11 | 8 | 0.028352 | 2026-10-01 | 2026-10-10 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1100 | CLS l Pump room Electrical connection P5.05 | 6 | 0.0020356 | 2026-10-11 | 2026-10-17 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1025 | CLS l Install of Submersible pumps P3.10 | 8 | 0.028352 | 2026-10-11 | 2026-10-19 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1105 | CLS l Pump room Electrical connection P2.09 | 6 | 0.0020356 | 2026-10-20 | 2026-10-26 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1035 | CLS l Install of Submersible pumps P5.06 | 8 | 0.028352 | 2026-10-20 | 2026-10-28 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1110 | CLS l Pump room Electrical connection P4.11 | 6 | 0.0020356 | 2026-10-27 | 2026-11-02 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1115 | CLS l Pump room Electrical connection P3.09 | 6 | 0.0020356 | 2026-10-29 | 2026-11-04 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1072 | CLS l Pump room Electrical connection P1.11 | 6 | 0.0020356 | 2026-10-29 | 2026-11-04 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1073 | CLS l Pump room Electrical connection P3.10 | 6 | 0.0020356 | 2026-10-29 | 2026-11-04 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1074 | CLS l Pump room Electrical connection P5.01 | 6 | 0.0020356 | 2026-11-05 | 2026-11-11 | 0% | 20% | 0% | 20%
CO.CL.D22.0EX.1036 | CLS l Pump room Electrical connection P5.06 | 6 | 0.0020356 | 2026-11-12 | 2026-11-18 | 0% | 0% | 0% | 0%
CO.CL.D22.0EX.1037 | CLS l Pump room Electrical connection P3.11 | 6 | 0.0020356 | 2026-11-19 | 2026-11-25 | 0% | 20% | 0% | 20%
Gravity Network Piping |  | 106 |  | 2026-06-30 | 2026-11-01
CO.CL.D33.0EX.1160 | CLS l Excavation works for GRP pipes and manholes part 1 | 10 | 0.026936 | 2026-06-30 | 2026-07-11 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1195 | CLS l Install of Precast Manholes part 1 | 14 | 0.097221 | 2026-07-12 | 2026-07-27 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1180 | CLS l Install of GRP pipes between manholes part 1 | 15 | 0.080808 | 2026-07-28 | 2026-08-13 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1165 | CLS l Backfilling works for GRP pipes and manholes part 1 | 14 | 0.026936 | 2026-08-15 | 2026-08-30 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1175 | CLS l Excavation works for GRP pipes and manholes part 2 | 10 | 0.026936 | 2026-08-31 | 2026-09-10 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1190 | CLS l Install of Precast Manholes part 2 | 14 | 0.097221 | 2026-09-12 | 2026-09-28 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1185 | CLS l Install of GRP pipes between manholes part 2 | 15 | 0.080808 | 2026-09-29 | 2026-10-15 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1170 | CLS l Backfilling works for GRP pipes and manholes part 2 | 14 | 0.026936 | 2026-10-17 | 2026-11-01 | 0% | 80% | 0% | 80%
Piping Between 5 Parcels and Manholes |  | 180 |  | 2026-06-09 | 2027-01-05
CO.CL.D33.0EX.1225 | CLS l Excavation works for HDPE pipes P5.01 | 10 | 0.0075425 | 2026-06-09 | 2026-06-20 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1200 | CLS l Install of HDPE pipes P5.01 | 12 | 0.015085 | 2026-06-21 | 2026-07-04 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1201 | CLS l Break chamber works for HDPE pipes P5.01 | 12 | 0.0045255 | 2026-06-21 | 2026-07-04 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1250 | CLS l Backfilling works for HDPE pipes P5.01 | 14 | 0.003017 | 2026-07-05 | 2026-07-20 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1230 | CLS l Excavation works for HDPE pipes P3.09 | 10 | 0.0075425 | 2026-07-21 | 2026-08-01 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1205 | CLS l Install of HDPE pipes P3.09 | 12 | 0.015085 | 2026-08-02 | 2026-08-15 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1202 | CLS l Break chamber works for HDPE pipes P3.09 | 12 | 0.0045255 | 2026-08-02 | 2026-08-15 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1255 | CLS l Backfilling works for HDPE pipes P3.09 | 14 | 0.003017 | 2026-08-16 | 2026-08-31 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1235 | CLS l Excavation works for HDPE pipes P5.02 | 10 | 0.0075425 | 2026-09-01 | 2026-09-12 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1210 | CLS l Install of HDPE pipes P5.02 | 12 | 0.015085 | 2026-09-13 | 2026-09-27 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1203 | CLS l Break chamber works for HDPE pipes P5.02 | 12 | 0.0045255 | 2026-09-13 | 2026-09-27 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1260 | CLS l Backfilling works for HDPE pipes P5.02 | 14 | 0.003017 | 2026-09-28 | 2026-10-13 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1240 | CLS l Excavation works for HDPE pipes P3.10 | 10 | 0.0075425 | 2026-10-14 | 2026-10-25 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1215 | CLS l Install of HDPE pipes P3.10 | 12 | 0.015085 | 2026-10-26 | 2026-11-08 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1204 | CLS l Break chamber works for HDPE pipes P3.10 | 12 | 0.0045255 | 2026-10-26 | 2026-11-08 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1265 | CLS l Backfilling works for HDPE pipes P3.10 | 14 | 0.003017 | 2026-11-09 | 2026-11-24 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1245 | CLS l Excavation works for HDPE pipes P3.11 | 10 | 0.0075425 | 2026-11-25 | 2026-12-06 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1220 | CLS l Install of HDPE pipes P3.11 | 12 | 0.015085 | 2026-12-07 | 2026-12-20 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1206 | CLS l Break chamber works for HDPE pipes P3.11 | 12 | 0.0045255 | 2026-12-07 | 2026-12-20 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1270 | CLS l Backfilling works for HDPE pipes P3.11 | 14 | 0.003017 | 2026-12-21 | 2027-01-05 | 0% | 90% | 0% | 90%
CO.CL.D33.0EX.1275 | CLS l Install of General Duty valves | 14 | 0.03101 | 2026-12-21 | 2027-01-05 | 0% | 0% | 0% | 0%
Piping Between 4 Parcels and Pump station& 4 Parecl to RO |  | 160 |  | 2026-06-09 | 2026-12-13
CO.CL.D33.0EX.1300 | CLS l Excavation works for HDPE pipes P5.03 | 10 | 0.0075425 | 2026-06-09 | 2026-06-20 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1305 | CLS l Excavation works for HDPE pipes P5.04 | 10 | 0.0090509 | 2026-06-21 | 2026-07-01 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1280 | CLS l Install of HDPE pipes P5.03 | 12 | 0.015085 | 2026-06-21 | 2026-07-04 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1296 | CLS l Break chamber for HDPE pipes P5.03 | 12 | 0.0045255 | 2026-06-21 | 2026-07-04 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1285 | CLS l Install of HDPE pipes P5.04 | 12 | 0.018102 | 2026-07-02 | 2026-07-15 | 0% | 100% | 0% | 100% |  | inside parcell only remining connection after valve supply
CO.CL.D33.0EX.1320 | CLS l Backfilling works for HDPE pipes P5.03 | 14 | 0.003017 | 2026-07-05 | 2026-07-20 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1325 | CLS l Backfilling works for HDPE pipes P5.04 | 14 | 0.003017 | 2026-07-16 | 2026-08-01 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1310 | CLS l Excavation works for HDPE pipes P5.05 | 10 | 0.0090509 | 2026-08-02 | 2026-08-12 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1290 | CLS l Install of HDPE pipes P5.05 | 12 | 0.018102 | 2026-08-13 | 2026-08-26 | 0% | 100% | 0% | 100% |  | inside parcell only remining connection after valve supply
CO.CL.D33.0EX.1330 | CLS l Backfilling works for HDPE pipes P5.05 | 14 | 0.003017 | 2026-08-27 | 2026-09-12 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1315 | CLS l Excavation works for HDPE pipes P5.06 | 10 | 0.0090509 | 2026-09-13 | 2026-09-24 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1295 | CLS l Install of HDPE pipes P5.06 | 12 | 0.018102 | 2026-09-26 | 2026-10-08 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1340 | CLS l Install of General Duty valves | 14 | 0.03101 | 2026-10-10 | 2026-10-25 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1335 | CLS l Backfilling works for HDPE pipes P5.06 | 14 | 0.003017 | 2026-10-10 | 2026-10-25 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1301 | CLS l Excavation works for HDPE pipes P2.09 | 14 | 0.0090509 | 2026-10-10 | 2026-10-25 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1302 | CLS l Excavation works for HDPE pipes P2.15 | 14 | 0.0090509 | 2026-10-26 | 2026-11-10 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1303 | CLS l Excavation works for HDPE pipes P1.11 | 14 | 0.0090509 | 2026-10-26 | 2026-11-10 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1304 | CLS l Excavation works for HDPE pipes P4.11 | 14 | 0.0090509 | 2026-10-26 | 2026-11-10 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1306 | CLS l Install of HDPE pipes P2.09 | 14 | 0.018102 | 2026-10-26 | 2026-11-10 | 0% | 95% | 0% | 95%
CO.CL.D33.0EX.1307 | CLS l Install of HDPE pipes P2.15 | 14 | 0.018102 | 2026-11-11 | 2026-11-26 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1308 | CLS l Install of HDPE pipes P1.11 | 14 | 0.018102 | 2026-11-11 | 2026-11-26 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1309 | CLS l Install of HDPE pipes P4.11 | 14 | 0.018102 | 2026-11-11 | 2026-11-26 | 0% | 100% | 0% | 100%
CO.CL.D33.0EX.1311 | CLS l Backfilling works for HDPE pipes P2.09 | 14 | 0.003017 | 2026-11-11 | 2026-11-26 | 100% | 95% | 0% | 95%
CO.CL.D33.0EX.1312 | CLS l Backfilling works for HDPE pipes P2.15 | 14 | 0.003017 | 2026-11-28 | 2026-12-13 | 100% | 95% | 0% | 95%
CO.CL.D33.0EX.1313 | CLS l Backfilling works for HDPE pipes P1.11 | 14 | 0.003017 | 2026-11-28 | 2026-12-13 | 100% | 95% | 0% | 95%
CO.CL.D33.0EX.1314 | CLS l Backfilling works for HDPE pipes P4.11 | 14 | 0.003017 | 2026-11-28 | 2026-12-13 | 100% | 95% | 0% | 95%
Piping Inside Tunnels |  | 126 |  | 2026-06-30 | 2026-11-24
CO.CL.D33.0EX.1350 | CLS l Install of HDPE pipes inside tunnels part 1 (9 Parcel) | 25 | 0.50396 | 2026-06-30 | 2026-07-28 | 0% | 0% | 0% | 0% |  | untill permite from KAFD - need acsses opening
CO.CL.D33.0EX.1355 | CLS l Install of HDPE pipes inside tunnels part 2 (P1.11) | 20 | 0.15119 | 2026-07-29 | 2026-08-20 | 0% | 0% | 0% | 0% |  | untill permite from KAFD - need acsses opening
CO.CL.D33.0EX.1360 | CLS l Install of HDPE pipes inside tunnels part 3 (P2.09) | 20 | 0.15119 | 2026-08-22 | 2026-09-13 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1365 | CLS l Install of HDPE pipes inside tunnels part 4 (P2.15) | 20 | 0.12095 | 2026-09-14 | 2026-10-07 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1370 | CLS l Install of HDPE pipes inside tunnels part 5 (P4.11) | 20 | 0.080633 | 2026-10-08 | 2026-10-31 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1345 | CLS l Install of GRP pipes inside tunnels | 21 | 0.10255 | 2026-11-01 | 2026-11-24 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1390 | CLS l Install of General Duty valves | 21 | 0.093031 | 2026-11-01 | 2026-11-24 | 0% | 0% | 0% | 0%
Fabricated Drainage Channel |  | 32 |  | 2026-12-14 | 2027-01-19
CO.CL.D33.0EX.1395 | CLS l Excavation works for Fabricated Channel | 8 | 0.039049 | 2026-12-14 | 2026-12-22 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1400 | CLS l Concrete Works for Fabricated Channel | 8 | 0.27334 | 2026-12-23 | 2026-12-31 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1410 | CLS l Protection works for Fabricated Channel | 8 | 0.039049 | 2027-01-02 | 2027-01-10 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1405 | CLS l Backfilling works for Fabricated Channel | 8 | 0.039049 | 2027-01-11 | 2027-01-19 | 0% | 0% | 0% | 0%
Connecting Works to Existing Networks |  | 40 |  | 2026-09-09 | 2026-10-26
CO.CL.D33.0EX.1415 | CLS l Connecting Works to Existing Networks part 1 (9 Parcel) | 8 | 0.099171 | 2026-09-09 | 2026-09-17 | 0% | 40% | 0% | 40%
CO.CL.D33.0EX.1420 | CLS l Connecting Works to Existing Networks part 2 (P1.11) | 8 | 0.029751 | 2026-09-19 | 2026-09-28 | 0% | 40% | 0% | 40%
CO.CL.D33.0EX.1425 | CLS l Connecting Works to Existing Networks part 3 (P2.09) | 8 | 0.029751 | 2026-09-29 | 2026-10-07 | 0% | 40% | 0% | 40%
CO.CL.D33.0EX.1430 | CLS l Connecting Works to Existing Networks part 4 (P2.15) | 8 | 0.023801 | 2026-10-08 | 2026-10-17 | 0% | 40% | 0% | 40%
CO.CL.D33.0EX.1435 | CLS l Connecting Works to Existing Networks part 5 (P4.11) | 8 | 0.015867 | 2026-10-18 | 2026-10-26 | 0% | 40% | 0% | 40%
Electrical |  | 24 |  | 2026-12-05 | 2026-12-31
Remote terminal unit (RTU) |  | 24 |  | 2026-12-05 | 2026-12-31
CO.CL.D33.0EX.1470 | CLS l Remote terminal unit connection works part 1 | 6 | 0.021669 | 2026-12-05 | 2026-12-10 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1460 | CLS l Remote terminal unit connection works part 2 | 6 | 0.021669 | 2026-12-12 | 2026-12-17 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1465 | CLS l Remote terminal unit connection works part 3 | 6 | 0.021669 | 2026-12-19 | 2026-12-24 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1455 | CLS l Install of Remote terminal unit panel | 8 | 0.057785 | 2026-12-23 | 2026-12-31 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1475 | CLS l Remote terminal unit connection works part 4 | 6 | 0.021669 | 2026-12-26 | 2026-12-31 | 0% | 0% | 0% | 0%
Communication System |  | 95 |  | 2026-09-02 | 2026-12-22
Fiber Optic Cable Network |  | 95 |  | 2026-09-02 | 2026-12-22
CO.CL.D33.0EX.1480 | CLS l Install of Fiber optic conduits part 1 (9 Parcel) | 11 | 0.33319 | 2026-09-02 | 2026-09-14 | 0% | 60% | 0% | 60%
CO.CL.D33.0EX.1485 | CLS l Install of Fiber optic conduits part 2 (P1.11) | 11 | 0.099956 | 2026-09-15 | 2026-09-28 | 0% | 50% | 0% | 50%
CO.CL.D33.0EX.1490 | CLS l Install of Fiber optic conduits part 3 (P2.09) | 11 | 0.099956 | 2026-09-29 | 2026-10-11 | 100% | 50% | 0% | 50%
CO.CL.D33.0EX.1495 | CLS l Install of Fiber optic conduits part 4 (P2.15) | 11 | 0.079964 | 2026-10-12 | 2026-10-24 | 100% | 50% | 0% | 50%
CO.CL.D33.0EX.1500 | CLS l Install of Fiber optic conduits part 5 (P4.11) | 11 | 0.05331 | 2026-10-25 | 2026-11-05 | 100% | 50% | 0% | 50%
CO.CL.D33.0EX.1520 | CLS l Install of Fiber optic Cables part 1 (9 Parcel) | 8 | 0.095425 | 2026-11-07 | 2026-11-15 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1525 | CLS l Install of Fiber optic Cables part 2 (P1.11) | 8 | 0.028627 | 2026-11-16 | 2026-11-24 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1530 | CLS l Install of Fiber optic Cables part 3 (P2.09) | 8 | 0.028627 | 2026-11-25 | 2026-12-03 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1535 | CLS l Install of Fiber optic Cables part 4 (P2.15) | 8 | 0.022902 | 2026-12-05 | 2026-12-13 | 0% | 0% | 0% | 0%
CO.CL.D33.0EX.1540 | CLS l Install of Fiber optic Cables part 5 (P4.11) | 8 | 0.015268 | 2026-12-14 | 2026-12-22 | 0% | 0% | 0% | 0%
Testing & Commissioning |  | 138 |  | 2026-10-07 | 2027-03-21 |  |  | 0%
RO Plant |  | 38 |  | 2027-02-01 | 2027-03-21
TC.RO.D07.GEN.1000 | RO l Testing & Termination for Thermal & Moisture insulation works | 7 | 0.11839 | 2027-02-01 | 2027-02-08 | 0% | 0% | 0% | 0%
TC.RO.D27.GEN.1040 | RO l Testing & Termination for Communication System | 6 | 0.051146 | 2027-02-28 | 2027-03-06 | 0% | 0% | 0% | 0%
TC.RO.D40.GEN.1055 | RO l Testing & Termination for Process scada system and intrumentation | 6 | 0.050243 | 2027-02-28 | 2027-03-06 | 0% | 0% | 0% | 0%
TC.RO.D28.GEN.1045 | RO l Testing & Termination for Access control CCTV system | 6 | 0.022886 | 2027-02-28 | 2027-03-06 | 0% | 0% | 0% | 0%
TC.RO.D22.GEN.1015 | RO l Testing & Termination for Plumbing Works | 8 | 0.12044 | 2027-02-27 | 2027-03-07 | 0% | 0% | 0% | 0%
TC.RO.D26.GEN.1030 | RO l Testing & Termination for MDB & UPS | 7 | 0.04616 | 2027-03-02 | 2027-03-09 | 0% | 0% | 0% | 0%
TC.RO.D23.GEN.1020 | RO l Testing & Termination for HVAC Piping | 8 | 0.17781 | 2027-03-02 | 2027-03-14 | 0% | 0% | 0% | 0%
TC.RO.D21.GEN.1010 | RO l Testing & Termination for Fire Suppression | 8 | 0.1388 | 2027-03-02 | 2027-03-14 | 0% | 0% | 0% | 0%
TC.RO.D14.GEN.1005 | RO l Testing & Termination for Elevator | 8 | 0.0077804 | 2027-03-02 | 2027-03-14 | 0% | 0% | 0% | 0%
TC.RO.D26.GEN.1025 | RO l Testing & Termination for Meduim Voltage & Diesel Generators | 8 | 0.13297 | 2027-03-04 | 2027-03-16 | 0% | 0% | 0% | 0%
TC.RO.D33.GEN.1050 | RO l Testing & Termination for Brackish Water Reverse Osmosis Plant | 20 | 0.51542 | 2027-02-23 | 2027-03-21 | 0% | 0% | 0% | 0%
TC.RO.D26.GEN.1035 | RO l Testing & Termination for Lightning System and Low current | 6 | 0.18143 | 2027-03-15 | 2027-03-21 | 0% | 0% | 0% | 0%
Pump-Station |  | 79 |  | 2026-10-07 | 2027-01-06
TC.PS.D22.GEN.1065 | IPS l Testing & Termination for Plumbing Works | 10 | 0.015069 | 2026-10-07 | 2026-10-18 | 0% | 0% | 0% | 0%
TC.PS.D10.GEN.1060 | IPS l Testing & Termination for Fire Extinguisher | 10 | 6.3653e-05 | 2026-11-04 | 2026-11-15 | 0% | 0% | 0% | 0%
TC.PS.D23.GEN.1070 | IPS l Testing & Termination for HVAC System | 10 | 0.0058434 | 2026-11-12 | 2026-11-23 | 0% | 0% | 0% | 0%
TC.PS.D21.GEN.1075 | IPS l Testing & Termination for Fire Suppression | 10 | 0.0061035 | 2026-11-15 | 2026-11-25 | 0% | 0% | 0% | 0%
TC.PS.D28.GEN.1085 | IPS l Testing & Termination for Electronic Safety and Security | 10 | 0.0029276 | 2026-11-22 | 2026-12-02 | 0% | 0% | 0% | 0%
TC.PS.D27.GEN.1080 | IPS l Testing & Termination for Communication System | 10 | 0.0089157 | 2026-11-28 | 2026-12-08 | 0% | 0% | 0% | 0%
TC.PS.D26.GEN.1075 | IPS l Testing & Termination for Electrical Works | 10 | 0.027924 | 2026-11-30 | 2026-12-10 | 0% | 0% | 0% | 0%
TC.PS.D40.GEN.1085 | IPS l Testing & Termination for Process scada system and intrumentation | 10 | 0.021758 | 2026-12-27 | 2027-01-06 | 0% | 0% | 0% | 0%
Collection System |  | 71 |  | 2026-10-27 | 2027-01-17
TC.CL.D33.GEN.1120 | CLS l Testing & Termination for Connecting Works to Existing Networks | 10 | 0.010439 | 2026-10-27 | 2026-11-07 | 0% | 0% | 0% | 0%
TC.CL.D33.GEN.1095 | CLS l Testing & Termination for GRP pipes | 10 | 0.029929 | 2026-11-25 | 2026-12-06 | 0% | 0% | 0% | 0%
TC.CL.D22.GEN.1090 | CLS l Testing & Termination for Submersible pumps | 10 | 0.066156 | 2026-11-26 | 2026-12-07 | 0% | 0% | 0% | 0%
TC.CL.D33.GEN.1115 | CLS l Testing & Termination for Fiber Optic Cables and Conduits | 10 | 0.095247 | 2026-12-23 | 2027-01-03 | 0% | 0% | 0% | 0%
TC.CL.D33.GEN.1110 | CLS l Testing & Termination for Remote terminal unit (RTU) | 10 | 0.028892 | 2027-01-02 | 2027-01-12 | 0% | 0% | 0% | 0%
TC.CL.D33.GEN.1100 | CLS l Testing & Termination for HDPE pipes | 10 | 0.15557 | 2027-01-06 | 2027-01-17 | 0% | 0% | 0% | 0%
TC.CL.D33.GEN.1105 | CLS l Testing & Termination for Valves Work | 10 | 0.017228 | 2027-01-06 | 2027-01-17 | 0% | 0% | 0% | 0%
Hand-Over |  | 151 |  | 2026-11-01 | 2027-03-31 |  |  | 0%
RO Plant |  | 65 |  | 2027-01-26 | 2027-03-31
RO Plant As-Built Drawings |  | 65 |  | 2027-01-26 | 2027-03-31
RO Plant As-Built Drawing Submittal |  | 36 |  | 2027-01-26 | 2027-03-09
HO.RO.0GN.ADS.1005 | RO l As-built drawings Submission for Masonry Works | 7 | 0.015942 | 2027-01-26 | 2027-02-02 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1015 | RO l As-built drawings Submission for Wood and Plastics | 7 | 0.015942 | 2027-01-28 | 2027-02-04 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1055 | RO l As-built drawings Submission for Earth Work | 7 | 0.015942 | 2027-01-31 | 2027-02-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1060 | RO l As-built drawings Submission for Exterior Improvement | 7 | 0.015942 | 2027-02-02 | 2027-02-09 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1000 | RO l As-built drawings Submission for Concrete Works | 7 | 0.015942 | 2027-02-03 | 2027-02-10 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1020 | RO l As-built drawings Submission for Thermal and Moisture Protection | 7 | 0.015942 | 2027-02-08 | 2027-02-15 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1065 | RO l As-built drawings Submission for Utilities | 7 | 0.015942 | 2027-02-23 | 2027-03-02 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1035 | RO l As-built drawings Submission for Plumbing Works | 7 | 0.015942 | 2027-02-27 | 2027-03-06 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1010 | RO l As-built drawings Submission for Metal Works | 7 | 0.015942 | 2027-02-28 | 2027-03-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1025 | RO l As-built drawings Submission for Doors and Windows | 7 | 0.015942 | 2027-02-28 | 2027-03-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1070 | RO l As-built drawings Submission for Process scada system | 7 | 0.015942 | 2027-02-28 | 2027-03-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1045 | RO l As-built drawings Submission for Communication System | 7 | 0.015942 | 2027-02-28 | 2027-03-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1050 | RO l As-built drawings Submission for Electronic Safety and Security | 7 | 0.015942 | 2027-02-28 | 2027-03-07 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1030 | RO l As-built drawings Submission for Fire Fighting | 7 | 0.015942 | 2027-03-02 | 2027-03-09 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1040 | RO l As-built drawings Submission for HVAC System | 7 | 0.015942 | 2027-03-02 | 2027-03-09 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADS.1080 | RO l As-built drawings Submission for Elevators | 7 | 0.015942 | 2027-03-02 | 2027-03-09 | 0% | 0% | 0% | 0%
RO Plant As-Built Drawing Approval |  | 37 |  | 2027-02-03 | 2027-03-31
HO.RO.0GN.ADA.1005 | RO l As-built drawings Approval for Masonry Works | 14 | 0.015942 | 2027-02-03 | 2027-02-23 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1015 | RO l As-built drawings Approval for Wood and Plastics | 14 | 0.015942 | 2027-02-07 | 2027-02-25 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1055 | RO l As-built drawings Approval for Earth Work | 14 | 0.015942 | 2027-02-08 | 2027-02-28 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1060 | RO l As-built drawings Approval for Exterior Improvement | 14 | 0.015942 | 2027-02-10 | 2027-03-02 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1000 | RO l As-built drawings Approval for Concrete Works | 14 | 0.015942 | 2027-02-11 | 2027-03-03 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1020 | RO l As-built drawings Approval for Thermal and Moisture Protection | 14 | 0.015942 | 2027-02-16 | 2027-03-08 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1065 | RO l As-built drawings Approval for Utilities | 14 | 0.015942 | 2027-03-03 | 2027-03-25 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1035 | RO l As-built drawings Approval for Plumbing Works | 14 | 0.015942 | 2027-03-07 | 2027-03-29 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1010 | RO l As-built drawings Approval for Metal Works | 14 | 0.015942 | 2027-03-08 | 2027-03-30 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1025 | RO l As-built drawings Approval for Doors and Windows | 14 | 0.015942 | 2027-03-08 | 2027-03-30 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1070 | RO l As-built drawings Approval for Process scada system | 14 | 0.015942 | 2027-03-08 | 2027-03-30 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1045 | RO l As-built drawings Approval for Communication System | 14 | 0.015942 | 2027-03-08 | 2027-03-30 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1050 | RO l As-built drawings Approval for Electronic Safety and Security | 14 | 0.015942 | 2027-03-08 | 2027-03-30 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1030 | RO l As-built drawings Approval for Fire Fighting | 14 | 0.015942 | 2027-03-14 | 2027-03-31 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1040 | RO l As-built drawings Approval for HVAC System | 14 | 0.015942 | 2027-03-14 | 2027-03-31 | 0% | 0% | 0% | 0%
HO.RO.0GN.ADA.1080 | RO l As-built drawings Approval for Elevators | 14 | 0.015942 | 2027-03-14 | 2027-03-31 | 0% | 0% | 0% | 0%
RO Plant Snagging& Desnagging |  | 29 |  | 2027-02-04 | 2027-03-14
HO.RO.0GN.SNG.1085 | RO l Snagging & desnagging for Furnishings Work | 10 | 0.091098 | 2027-02-04 | 2027-02-15 | 0% | 0% | 0% | 0%
HO.RO.0GN.SNG.1075 | RO l Snagging & desnagging for Finishing Works | 10 | 0.091098 | 2027-02-21 | 2027-03-04 | 0% | 0% | 0% | 0%
HO.RO.0GN.SNG.1090 | RO l Snagging & desnagging for Aluminium Control booths | 10 | 0.091098 | 2027-02-27 | 2027-03-09 | 0% | 0% | 0% | 0%
HO.RO.0GN.SNG.1080 | RO l Snagging & desnagging for Specialtes Work | 10 | 0.091098 | 2027-02-28 | 2027-03-14 | 0% | 0% | 0% | 0%
RO Plant Manual and Maintenance |  | 8 |  | 2027-03-22 | 2027-03-30
HO.RO.0GN.0OM.1095 | RO l Operation and Maintenance Manuals | 8 | 0.14576 | 2027-03-22 | 2027-03-30 | 0% | 0% | 0% | 0%
RO Plant Demobilization |  | 9 |  | 2027-03-15 | 2027-03-24
HO.RO.0GN.0DM.1100 | RO l Demobilization works | 9 | 0.14576 | 2027-03-15 | 2027-03-24 | 0% | 0% | 0% | 0%
RO Plant TOC |  | 1 |  | 2027-03-31 | 2027-03-31
HO.RO.0GN.TOC.1105 | RO l Completion of TOC (Take Over Certificate) | 1 | 0.14576 | 2027-03-31 | 2027-03-31 | 0% | 0% | 0% | 0%
RO Plant CDC and CDA |  | 19 |  | 2027-03-02 | 2027-03-31
HO.RO.0GN.CDC.1120 | RO l Civil Defense Certificate | 5 | 0.072878 | 2027-03-02 | 2027-03-08 | 0% | 0% | 0% | 0%
HO.RO.0GN.CDA.1130 | RO l Civil Defense Approval | 14 | 0.072878 | 2027-03-14 | 2027-03-31 | 0% | 0% | 0% | 0%
Pump-Station |  | 123 |  | 2026-11-01 | 2027-03-03
Pump Station As-Built Drawings |  | 83 |  | 2026-11-12 | 2027-02-02
Pump Station As-Built Drawings Submittal |  | 54 |  | 2026-11-12 | 2027-01-13
HO.PS.0GN.ADS.1045 | IPS l As-built drawings Submission for HVAC System | 7 | 0.00070269 | 2026-11-12 | 2026-11-19 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1035 | IPS l As-built drawings Submission for Fire Fighting | 7 | 0.00070269 | 2026-11-15 | 2026-11-22 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1055 | IPS l As-built drawings Submission for Electronic Safety and Security | 7 | 0.00070269 | 2026-11-22 | 2026-11-29 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1040 | IPS l As-built drawings Submission for Plumbing Works | 7 | 0.00070269 | 2026-11-23 | 2026-11-30 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1050 | IPS l As-built drawings Submission for Communication System | 7 | 0.00070269 | 2026-11-28 | 2026-12-05 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1060 | IPS l As-built drawings Submission for Electronic Earth Work | 7 | 0.00070269 | 2026-12-13 | 2026-12-20 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1000 | IPS l As-built drawings Submission for Existing Condition | 7 | 0.00070269 | 2026-12-13 | 2026-12-20 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1025 | IPS l As-built drawings Submission for Thermal and Moisture Protection | 7 | 0.00070269 | 2026-12-21 | 2026-12-28 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1005 | IPS l As-built drawings Submission for Concrete Works | 7 | 0.00070269 | 2026-12-21 | 2026-12-28 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1065 | IPS l As-built drawings Submission for Exterior Improvement | 7 | 0.00070269 | 2026-12-26 | 2027-01-02 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1070 | IPS l As-built drawings Submission for Process scada system | 7 | 0.00070269 | 2026-12-27 | 2027-01-03 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1010 | IPS l As-built drawings Submission for Masonry Works | 7 | 0.00070269 | 2026-12-29 | 2027-01-05 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1030 | IPS l As-built drawings Submission for Doors and Windows | 7 | 0.00070269 | 2026-12-29 | 2027-01-05 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1015 | IPS l As-built drawings Submission for Metal Works | 7 | 0.00070269 | 2027-01-06 | 2027-01-13 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADS.1020 | IPS l As-built drawings Submission for Wood and Plastics | 7 | 0.00070269 | 2027-01-06 | 2027-01-13 | 0% | 0% | 0% | 0%
Pump Station As-Built Drawings Approval |  | 53 |  | 2026-11-22 | 2027-02-02
HO.PS.0GN.ADA.1045 | IPS l As-built drawings Approval for HVAC System | 14 | 0.00070269 | 2026-11-22 | 2026-12-09 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1035 | IPS l As-built drawings Approval for Fire Fighting | 14 | 0.00070269 | 2026-11-23 | 2026-12-10 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1055 | IPS l As-built drawings Approval for Electronic Safety and Security | 14 | 0.00070269 | 2026-11-30 | 2026-12-17 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1040 | IPS l As-built drawings Approval for Plumbing Works | 14 | 0.00070269 | 2026-12-01 | 2026-12-20 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1050 | IPS l As-built drawings Approval for Communication System | 14 | 0.00070269 | 2026-12-06 | 2026-12-23 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1060 | IPS l As-built drawings Approval for Electronic Earth Work | 14 | 0.00070269 | 2026-12-21 | 2027-01-07 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1000 | IPS l As-built drawings Approval for Existing Condition | 14 | 0.00070269 | 2026-12-21 | 2027-01-07 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1025 | IPS l As-built drawings Approval for Thermal and Moisture Protection | 14 | 0.00070269 | 2026-12-29 | 2027-01-17 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1005 | IPS l As-built drawings Approval for Concrete Works | 14 | 0.00070269 | 2026-12-29 | 2027-01-17 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1065 | IPS l As-built drawings Approval for Exterior Improvement | 14 | 0.00070269 | 2027-01-03 | 2027-01-20 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1070 | IPS l As-built drawings Approval for Process scada system | 14 | 0.00070269 | 2027-01-04 | 2027-01-21 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1010 | IPS l As-built drawings Approval for Masonry Works | 14 | 0.00070269 | 2027-01-06 | 2027-01-25 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1030 | IPS l As-built drawings Approval for Doors and Windows | 14 | 0.00070269 | 2027-01-06 | 2027-01-25 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1015 | IPS l As-built drawings Approval for Metal Works | 14 | 0.00070269 | 2027-01-14 | 2027-02-02 | 0% | 0% | 0% | 0%
HO.PS.0GN.ADA.1020 | IPS l As-built drawings Approval for Wood and Plastics | 14 | 0.00070269 | 2027-01-14 | 2027-02-02 | 0% | 0% | 0% | 0%
Pump Station Snagging& Desnagging |  | 36 |  | 2026-11-01 | 2026-12-12
HO.PS.0GN.SNG.1075 | IPS l Snagging & desnagging for Finishing Works | 14 | 0.0050192 | 2026-11-01 | 2026-11-16 | 0% | 0% | 0% | 0%
HO.PS.0GN.SNG.1080 | IPS l Snagging & desnagging for Specialtes Work | 14 | 0.0050192 | 2026-11-04 | 2026-11-19 | 0% | 0% | 0% | 0%
HO.PS.0GN.SNG.1085 | IPS l Snagging & desnagging for Aluminium Control booths | 14 | 0.0050192 | 2026-11-26 | 2026-12-12 | 0% | 0% | 0% | 0%
Pump Station Manual and Maintenance |  | 7 |  | 2027-02-03 | 2027-02-10
HO.PS.0GN.0OM.1090 | IPS l Operation and Maintenance Manuals | 7 | 0.006023 | 2027-02-03 | 2027-02-10 | 0% | 0% | 0% | 0%
Pump-Station Demobilization |  | 14 |  | 2026-12-13 | 2026-12-28
HO.PS.0GN.0DM.1095 | IPS l Demobilization works | 14 | 0.006023 | 2026-12-13 | 2026-12-28 | 0% | 0% | 0% | 0%
Pump-Station TOC |  | 14 |  | 2027-02-11 | 2027-03-03
HO.PS.0GN.TOC.1100 | IPS l Completion of TOC (Take Over Certificate) | 14 | 0.006023 | 2027-02-11 | 2027-03-03 | 0% | 0% | 0% | 0%
Pump-Station CDC and CDA |  | 21 |  | 2027-01-07 | 2027-02-04
HO.PS.0GN.CDC.1130 | IPS l Civil Defense Certificate | 7 | 0.0030115 | 2027-01-07 | 2027-01-17 | 0% | 0% | 0% | 0%
HO.PS.0GN.CDA.1140 | IPS l Civil Defense Approval | 14 | 0.0030115 | 2027-01-18 | 2027-02-04 | 0% | 0% | 0% | 0%
Collection System |  | 117 |  | 2026-11-25 | 2027-03-21
Collection System As-Built Drawing |  | 71 |  | 2026-11-25 | 2027-02-03
Collection System As-Built Drawing Submittal |  | 44 |  | 2026-11-25 | 2027-01-14
HO.CL.0GN.ADS.1000 | CLS l As-built drawings Submission for Plumbing Works | 8 | 0.015972 | 2026-11-25 | 2026-12-03 | 0% | 0% | 0% | 0%
HO.CL.0GN.ADS.1005 | CLS l As-built drawings Submission for Pipes and Valves Work | 8 | 0.015972 | 2027-01-06 | 2027-01-14 | 0% | 0% | 0% | 0%
Collection System As-Built Drawing Approval |  | 44 |  | 2026-12-06 | 2027-02-03
HO.CL.0GN.ADA.1000 | CLS l As-built drawings Approval for Plumbing Works | 14 | 0.015972 | 2026-12-06 | 2026-12-23 | 0% | 0% | 0% | 0%
HO.CL.0GN.ADA.1005 | CLS l As-built drawings Approval for Pipes and Valves Work | 14 | 0.015972 | 2027-01-17 | 2027-02-03 | 0% | 0% | 0% | 0%
Collection System Snagging& Desnagging |  | 14 |  | 2027-01-20 | 2027-02-04
HO.CL.0GN.SNG.1010 | CLS l Snagging & desnagging | 14 | 0.045636 | 2027-01-20 | 2027-02-04 | 0% | 0% | 0% | 0%
Collection System Manual and Maintenance |  | 14 |  | 2027-01-18 | 2027-02-02
HO.CL.0GN.0OM.1015 | CLS l Operation and Maintenance Manuals | 14 | 0.018254 | 2027-01-18 | 2027-02-02 | 0% | 0% | 0% | 0%
Collection System Demobilization |  | 14 |  | 2027-01-07 | 2027-01-23
HO.CL.0GN.0DM.1020 | CLS l Demobilization works | 14 | 0.018254 | 2027-01-07 | 2027-01-23 | 0% | 0% | 0% | 0%
Collection System TOC |  | 7 |  | 2027-03-08 | 2027-03-21
HO.CL.0GN.TOC.1025 | CLS l Completion of TOC (Take Over Certificate) | 7 | 0.018254 | 2027-03-08 | 2027-03-21 | 0% | 0% | 0% | 0%
Collection System CDC and CDA |  | 21 |  | 2027-02-04 | 2027-03-07
HO.CL.0GN.CDC.1140 | CLS l Civil Defense Certificate | 7 | 0.0091271 | 2027-02-04 | 2027-02-14 | 0% | 0% | 0% | 0%
HO.CL.0GN.CDA.1150 | CLS l Civil Defense Approval | 14 | 0.0091271 | 2027-02-15 | 2027-03-07 | 0% | 0% | 0% | 0%

## QT Segment (RC Wall)
1. Qunatity for RC WALLS
Stage / Segment | Hight | Segment1 | Chamfer | Segment 2 | Chamfer | Segment 3 | Chamfer | Segment 4 | Chamfer | Segment 5 | Chamfer | Segment 6 | Chamfer | Segment 7 | Chamfer | Segment 8 | Chamfer | Total
Area (m2) |  | 86.2142 | 0.36 | 117.4783 | 0.36 | 103.1957 | 0.36 | 53.7477 | 0.36 | 147.4684 | 0.36 | 112.6832 | 0.36 | 77.8146 | 0.36 | 97.5485 | 0.36 | 798.6706
Stage 1 (1.5m) | 1.5 | 129.3213 | 34.6932 | 176.2175 | 83.3796 | 154.7936 | 46.0296 | 80.6215 | 12.7908 | 221.2026 | 74.3652 | 169.0248 | 90.4104 | 116.7219 | 64.1808 | 146.3228 | 22.644 | 1622.7195
Stage 2 (4.3m) | 4.3 | 370.7211 |  | 505.1567 |  | 443.7415 |  | 231.1151 |  | 634.1141 |  | 484.5378 |  | 334.6028 |  | 419.4586 |  | 3423.4476
Stage 3 (4.3m) | 4.3 | 370.7211 |  | 505.1567 |  | 443.7415 |  | 231.1151 |  | 634.1141 |  | 484.5378 |  | 334.6028 |  | 419.4586 |  | 3423.4476
Stage 4 (4.7m) | 4.7 | 405.2067 |  | 552.148 |  | 485.0198 |  | 252.6142 |  | 693.1015 |  | 529.611 |  | 365.7286 |  | 458.478 |  | 3741.9078
2. Weightage for RC WALLS
Stage / Segment | Hight | Segment1 |  | Segment 2 |  | Segment 3 |  | Segment 4 |  | Segment 5 |  | Segment 6 |  | Segment 7 |  | Segment 8 |  | Total Actual progress
Area |  | 86.2142 |  | 117.4783 |  | 103.1957 |  | 53.7477 |  | 147.4684 |  | 112.6832 |  | 77.8146 |  | 97.5485 |  | 796.1506
|  | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Weightage | Actual progress | Total
Stage 1 (1.5m) | 1.5 | 10.11% | 100% | 16% | 50% | 12.38% | 15% | 5.757% |  | 18.21% |  | 15.99% |  | 11.15% |  | 10.41% |  | 19.96%
Stage 2 (4.3m) | 4.3 | 10.83% |  | 14.76% |  | 12.96% |  | 6.751% |  | 18.52% |  | 14.15% |  | 9.774% |  | 12.25% |  | 0%
Stage 3 (4.3m) | 4.3 | 10.83% |  | 14.76% |  | 12.96% |  | 6.751% |  | 18.52% |  | 14.15% |  | 9.774% |  | 12.25% |  | 0%
Stage 4 (4.7m) | 4.7 | 10.83% |  | 14.76% |  | 12.96% |  | 6.751% |  | 18.52% |  | 14.15% |  | 9.774% |  | 12.25% |  | 0%

## Breakdown for Raft found
|  | Area (m^2) | Volume (m^3) |  | Steel progress | Concret progress | Site progreess | Steel fixing Watage | 75%
Part-01 | Strip 1 | 544.9 | 953.575 | 31.61% | 100% | 100% | 100% | Pouring for Raft Foundation Watage | 25%
| Strip 7 | 645.86 | 1130.255 | 37.47% | 100% | 100% | 100%
| Strip 2 | 212.57 | 371.9975 | 12.33% | 100% | 100% | 100%
| Strip 6 | 251.92 | 440.86 | 14.61% | 95% |  | 71.25%
| Water Chamber | 200 | 120 | 3.978% | 20%
Total |  | 1855.25 | 3016.6875 | 100% |  |  | 91.82%
Part-02 | Strip 3 | 143.46 | 251.055 | 8.967% | 80% | 0% | 60%
| Strip 4 | 488.61 | 855.0675 | 30.54% | 70% |  | 52.5%
| Strip 5 | 368.04 | 644.07 | 23.01% | 50% |  | 37.5%
| Strip 2 | 249.81 | 437.1675 | 15.62% | 100% | 100% | 100%
| Strip 6 | 349.87 | 612.2725 | 21.87% | 95% |  | 71.25%
Total |  | 1599.79 | 2799.6325 | 100% |  |  | 61.24%
| Area (m^2) | Thikness (m) | Volume (m^3)
Strip 1 | 544.92 | 1.75 | 953.61 | 16.4%
Strip 2 | 462.38 | 1.75 | 809.165 | 13.91%
Strip 3 | 143.46 | 1.75 | 251.055 | 4.316%
Strip 4 | 488.61 | 1.75 | 855.0675 | 14.7%
Strip 5 | 368.04 | 1.75 | 644.07 | 11.07%
Strip 6 | 601.76 | 1.75 | 1053.08 | 18.11%
Strip 7 | 645.86 | 1.75 | 1130.255 | 19.43%
Water Chamber | 200 | 0.6 | 120 | 2.063%
Total | 3455.03 |  | 5816.3025 | 100%

## Sheet2
Activity ID | Activity Name | Original Duration | Remaining Duration | Start | Finish | Schedule % Complete | Performance % Complete | Total Float
KAFD00330-636-SBC-UP-261029KAFD00330 ¦ 636 ¦ SBC-Update-29-Oct-26 |  | 547 | 269 | 01-Oct-25 A | 2027-07-25 | 23.43% | 46.91% | -116
KAFD00330-636-SBC-UP-261029.1Project Milestones |  | 360 | 249 | 01-Oct-25 A | 2027-07-25 | 0% | 0% | -116
KAFD00330-636-SBC-UP-261029.1.1Key Milestone |  | 360 | 0 | 01-Oct-25 A | 2027-07-25 | 0% | 0% | -116
MS.COM.GEN.1000 | Commencement date | 0 | 0 | 01-Oct-25 A |  | 100% | 100%
MS.COM.GEN.1005 | Project Completion | 0 | 0 |  | 2027-07-25 | 0% | 0% | -116
KAFD00330-636-SBC-UP-261029.1.2Control Milestone |  | 230 | 230 | 2026-11-18 | 2027-07-06 | 0% | 0% | -97
MS.COM.GEN.1015 | Completion of Shop Drawings | 0 | 0 |  | 2026-11-18 | 0% | 0% | 133
MS.COM.GEN.1030 | Completion of Intermediate Pump Station Construction Works | 0 | 0 |  | 2027-01-26 | 0% | 0% | 64
MS.COM.GEN.1045 | Completion of Material Delivery | 0 | 0 |  | 2027-01-29 | 0% | 0% | 61
MS.COM.GEN.1025 | Completion of Mobilization Works | 0 | 0 |  | 2027-03-16 | 0% | 0% | 15
MS.COM.GEN.1035 | Completion of Collection system Construction Works | 0 | 0 |  | 2027-04-14 | 0% | 0% | -14
MS.COM.GEN.1040 | Completion of RO Plaint Construction Works | 0 | 0 |  | 2027-07-06 | 0% | 0% | -97
KAFD00330-636-SBC-UP-261029.2General (Preliminaries and Mobilization) |  | 547 | 153 | 01-Oct-25 A | 2027-03-31 | 13.38% | 55.88% | 0
KAFD00330-636-SBC-UP-261029.2.1Mobilization Works |  | 210 | 28 | 11-Jun-26 A | 2027-03-16 | 0% | 17.73% | 13
MO.GEN.D01.1005 | Site Access, Routes & Directive Signage | 10 | 6 | 11-Jun-26 A | 2027-02-14 | 0% | 41.64% | 13
MO.GEN.D01.1015 | Site Offices Furnitures | 12 | 10 | 11-Jun-26 A | 2027-02-18 | 0% | 14.01% | 13
MO.GEN.D01.1030 | Temporary Facilities and Devices for Offices | 20 | 19 | 11-Jun-26 A | 2027-03-02 | 0% | 6.97% | 13
MO.GEN.D01.1006 | Waste Disposal & Enviremental Protection | 15 | 8 | 11-Jun-26 A | 2027-02-16 | 0% | 46.02% | 13
MO.GEN.D01.1007 | Administrative Site Offices and Facilities | 30 | 28 | 11-Jun-26 A | 2027-03-16 | 0% | 12% | 13
MO.GEN.D01.1011 | Temporary Utilities Installation | 25 | 23 | 25-Jun-26 A | 2027-03-07 | 0% | 12% | 18
MO.GEN.D01.1008 | Site Laboratory | 12 | 10 | 25-Jun-26 A | 2027-02-18 | 0% | 15% | 31
MO.GEN.D01.1009 | Temporary roads and Signs | 10 | 6 | 25-Jun-26 A | 2027-02-14 | 0% | 46.02% | 35
KAFD00330-636-SBC-UP-261029.2.2General Requirements |  | 547 | 153 | 01-Oct-25 A | 2027-03-31 | 20.23% | 75.43% | 0
GN.GEN.D01.1010 | Preliminaries for contractors and administrative works | 547 | 153 | 01-Oct-25 A | 2027-03-31 | 23.03% | 72.03% | 0
GN.GEN.D01.1020 | Performance Security | 15 | 0 | 16-Apr-26 A | 27-May-26 A | 0% | 100%
GN.GEN.D01.1025 | Advance Payment Security | 20 | 0 | 16-Apr-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3Engineering |  | 298 | 19 | 01-Oct-25 A | 2026-11-18 | 45.05% | 95.71% | 98
KAFD00330-636-SBC-UP-261029.3.1RO Plant |  | 254 | 19 | 01-Oct-25 A | 2026-11-18 | 52.15% | 95.63% | 98
KAFD00330-636-SBC-UP-261029.3.1.1RO Plant Shop Drawing Submittal |  | 213 | 9 | 01-Oct-25 A | 2026-11-09 | 50.4% | 98.75% | 91
KAFD00330-636-SBC-UP-261029.3.1.1.1Earthworks Shop Drawing Submittal |  | 60 | 0 | 01-Oct-25 A | 26-Nov-25 A | 100% | 100%
EN.RO.D31.SDS.1215 | RO l Submission of Excavation Works shop drawing | 20 | 0 | 01-Oct-25 A | 20-Oct-25 A | 100% | 100%
EN.RO.D31.SDS.1220 | RO l Submission of Concrete Piles shop drawing | 20 | 0 | 05-Nov-25 A | 26-Nov-25 A | 100% | 100%
EN.RO.D31.SDS.1225 | RO l Submission of Prestressed anchors shop drawing | 20 | 0 | 20-Nov-25 A | 26-Nov-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.2Concrete Shop Drawing Submittal |  | 122 | 0 | 13-Nov-25 A | 29-Apr-26 A | 91.36% | 100%
EN.RO.D03.SDS.1000 | RO l Submission of Raft Foundation shop drawing | 12 | 0 | 13-Nov-25 A | 24-Dec-25 A | 100% | 100%
EN.RO.D03.SDS.1005 | RO l Submission of Tank walls shop drawing | 18 | 0 | 04-Dec-25 A | 21-Jan-26 A | 100% | 100%
EN.RO.D03.SDS.1050 | RO l Submission of Tank slab shop drawing | 8 | 0 | 01-Jan-26 A | 21-Jan-26 A | 100% | 100%
EN.RO.D03.SDS.1010 | RO l Submission of Columns shop drawing Gf | 6 | 0 | 12-Feb-26 A | 24-Feb-26 A | 100% | 100%
EN.RO.D03.SDS.1015 | RO l Submission of Columns shop drawing 1st | 6 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
EN.RO.D03.SDS.1020 | RO l Submission of Columns shop drawing 2nd | 6 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
EN.RO.D03.SDS.1030 | RO l Submission of Concrete Slab shop drawing GF | 8 | 0 | 19-Feb-26 A | 25-Feb-26 A | 37.5% | 100%
EN.RO.D03.SDS.1035 | RO l Submission of Concrete Slab shop drawing 1st | 8 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D03.SDS.1040 | RO l Submission of Concrete Slab shop drawing 2nd | 18 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D03.SDS.1045 | RO l Submission of Floor & Roof screed shop drawing | 18 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.RO.D03.SDS.1025 | RO l Submission of Slab on grade shop drawing | 10 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.3Masonry Shop Drawing Submittal |  | 21 | 0 | 22-Jan-26 A | 04-Feb-26 A | 0% | 100%
EN.RO.D04.SDS.1055 | RO l Submission of Masonary works shop drawing | 14 | 0 | 22-Jan-26 A | 28-Jan-26 A | 0% | 100%
EN.RO.D04.SDS.1060 | RO l Submission of Stone cladding shop drawing | 7 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.4Metal Shop Drawing Submittal |  | 14 | 0 | 30-Apr-26 A | 13-May-26 A | 0% | 100%
EN.RO.D05.SDS.1065 | RO l Submission of Structural steel works | 14 | 0 | 30-Apr-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.5Thermal Protection Shop Drawing Submittal |  | 38 | 0 | 15-Jan-26 A | 17-Jun-26 A | 0% | 100%
EN.RO.D07.SDS.1080 | RO l Submission of Concrete tiles shop drawing | 16 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.RO.D07.SDS.1075 | RO l Submission of Canopy aluminium cladding shop drawing | 16 | 0 | 07-May-26 A | 17-Jun-26 A | 0% | 100%
EN.RO.D07.SDS.1070 | RO l Submission of Aluminium panels cladding shop drawing | 12 | 0 | 21-May-26 A | 17-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.6Openings Shop Drawing Submittal |  | 12 | 0 | 12-Feb-26 A | 01-Jul-26 A | 0% | 100%
EN.RO.D08.SDS.1085 | RO l Submission of Steel doors shop drawing | 12 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.RO.D08.SDS.1090 | RO l Submission of Aluminum windows & Louvers shop drawing | 12 | 0 | 17-Mar-26 A | 01-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.7Finishes Shop Drawing Submittal |  | 30 | 0 | 15-Jan-26 A | 01-Jul-26 A | 0% | 100%
EN.RO.D09.SDS.1100 | RO l Submission of Floor Works shop drawing | 16 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.RO.D09.SDS.1095 | RO l Submission of Gypsum board Works shop drawing | 16 | 0 | 09-Feb-26 A | 01-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.8Elevator Shop Drawing Submittal |  | 10 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
EN.RO.D14.SDS.1105 | RO l Submission of Elevators shop drawing | 10 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.9Fire Supperssion Shop Drawing Submittal |  | 64 | 0 | 01-Jan-26 A | 29-Apr-26 A | 0% | 100%
EN.RO.D21.SDS.1115 | RO l Submission of Fire Suppression shop drawing GF | 10 | 0 | 01-Jan-26 A | 28-Jan-26 A | 0% | 100%
EN.RO.D21.SDS.1125 | RO l Submission of Fire Suppression shop drawing 2nd | 10 | 0 | 12-Mar-26 A | 18-Mar-26 A | 0% | 100%
EN.RO.D21.SDS.1120 | RO l Submission of Fire Suppression shop drawing 1st | 10 | 0 | 12-Mar-26 A | 18-Mar-26 A | 0% | 100%
EN.RO.D21.SDS.1110 | RO l Submission of Fire Suppression for Pump room shop drawing | 10 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.10Plumbing Shop Drawing Submittal |  | 39 | 0 | 29-Jan-26 A | 15-Mar-26 A | 0% | 100%
EN.RO.D22.SDS.1135 | RO l Submission of Domestic water piping shop drawing | 10 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
EN.RO.D22.SDS.1130 | RO l Submission of Vibration & Seismic controls For Plumbingshop drawing | 10 | 0 | 07-Feb-26 A | 11-Feb-26 A | 0% | 100%
EN.RO.D22.SDS.1140 | RO l Submission of Plumbing Valves shop drawing | 7 | 0 | 07-Feb-26 A | 11-Feb-26 A | 0% | 100%
EN.RO.D22.SDS.1145 | RO l Submission of Sanitary Pipes shop drawing | 12 | 0 | 12-Feb-26 A | 15-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.11HVAC System Shop Drawing Submittal |  | 36 | 0 | 12-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D23.SDS.1150 | RO l Submission of HVAC System shop drawing GF | 12 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.RO.D23.SDS.1155 | RO l Submission of HVAC System shop drawing 1st | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D23.SDS.1160 | RO l Submission of HVAC System shop drawing 2nd | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.12Electrical System Shop Drawing Submittal |  | 43 | 0 | 15-Jan-26 A | 13-May-26 A | 0% | 100%
EN.RO.D26.SDS.1175 | RO l Submission of Lightning & Earthing shop drawing | 6 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.RO.D26.SDS.1190 | RO l Submission of lighting system shop drawing | 9 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.RO.D26.SDS.1180 | RO l Submission of Power system shop drawing | 6 | 0 | 12-Mar-26 A | 18-Mar-26 A | 0% | 100%
EN.RO.D26.SDS.1185 | RO l Submission of Cable routing shop drawing | 12 | 0 | 26-Mar-26 A | 01-Apr-26 A | 0% | 100%
EN.RO.D26.SDS.1165 | RO l Submission of Panel board shop drawing | 10 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D26.SDS.1170 | RO l Submission of UPS System shop drawing | 10 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.13Low Current Shop Drawing Submittal |  | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D27.SDS.1195 | RO l Submission of Communication System shop drawing | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.14Security Shop Drawing Submittal |  | 42 | 0 | 16-Apr-26 A | 13-May-26 A | 0% | 100%
EN.RO.D28.SDS.1205 | RO l Submission of CCTV system shop drawing | 14 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D28.SDS.1210 | RO l Submission of Fire alarm system shop drawing | 14 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.RO.D28.SDS.1200 | RO l Submission of Access control shop drawing | 14 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.15Exterior Improvement Shop Drawing Submittal |  | 18 | 9 | 16-Apr-26 A | 2026-11-09 | 0% | 50% | 50
EN.RO.D32.SDS.1230 | RO l Submission of Precast concrete shop drawing | 18 | 9 | 16-Apr-26 A | 2026-11-09 | 0% | 50% | 50
KAFD00330-636-SBC-UP-261029.3.1.1.16Special System Shop Drawing Submittal |  | 50 | 0 | 16-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.RO.D33.SDS.1235 | RO l Submission of (BWRO) Plant shop drawing | 50 | 0 | 16-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.1.17SCADA Shop Drawing Submittal |  | 15 | 8 | 27-Aug-26 A | 2026-11-08 | 100% | 50% | 83
EN.RO.D40.SDS.1240 | RO l Submission of SCDA system shop drawing | 15 | 8 | 27-Aug-26 A | 2026-11-08 | 100% | 50% | 83
KAFD00330-636-SBC-UP-261029.3.1.2RO Plant Shop Drawing Approval |  | 178 | 14 | 22-Oct-25 A | 2026-11-18 | 53.89% | 92.51% | 69
KAFD00330-636-SBC-UP-261029.3.1.2.1Concrete Shop Drawing Approval |  | 110 | 3 | 18-Dec-25 A | 2026-11-03 | 86.99% | 99.68% | 44
EN.RO.D03.SDA.1000 | RO l Approval of Raft Foundation shop drawing | 14 | 0 | 18-Dec-25 A | 23-Feb-26 A | 100% | 100%
EN.RO.D03.SDA.1005 | RO l Approval of Tank walls shop drawing | 14 | 0 | 29-Jan-26 A | 25-Mar-26 A | 100% | 100%
EN.RO.D03.SDA.1050 | RO l Approval of Tank slab shop drawing | 14 | 0 | 29-Jan-26 A | 11-Mar-26 A | 57.14% | 100%
EN.RO.D03.SDA.1010 | RO l Approval of Columns shop drawing Gf | 14 | 0 | 09-Feb-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D03.SDA.1030 | RO l Approval of Concrete Slab shop drawing GF | 14 | 0 | 09-Feb-26 A | 03-Jun-26 A | 0% | 100%
EN.RO.D03.SDA.1015 | RO l Approval of Columns shop drawing 1st | 14 | 0 | 16-Feb-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D03.SDA.1020 | RO l Approval of Columns shop drawing 2nd | 14 | 0 | 05-Mar-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D03.SDA.1035 | RO l Approval of Concrete Slab shop drawing 1st | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
EN.RO.D03.SDA.1040 | RO l Approval of Concrete Slab shop drawing 2nd | 14 | 0 | 16-Apr-26 A | 17-Jun-26 A | 0% | 100%
EN.RO.D03.SDA.1045 | RO l Approval of Floor & Roof screed shop drawing | 14 | 0 | 30-Apr-26 A | 29-Jul-26 A | 0% | 100%
EN.RO.D03.SDA.1025 | RO l Approval of Slab on grade shop drawing | 14 | 3 | 10-Sep-26 A | 2026-11-03 | 100% | 80% | 14
KAFD00330-636-SBC-UP-261029.3.1.2.2Masonry Shop Drawing Approval |  | 20 | 7 | 30-Apr-26 A | 2026-11-09 | 0% | 73.5% | 74
EN.RO.D04.SDA.1060 | RO l Approval of Stone cladding shop drawing | 14 | 7 | 30-Apr-26 A | 2026-11-09 | 0% | 50% | 74
EN.RO.D04.SDA.1055 | RO l Approval of Masonary works shop drawing | 14 | 0 | 30-Apr-26 A | 01-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.3Metal Shop Drawing Approval |  | 14 | 0 | 28-May-26 A | 29-Jul-26 A | 0% | 100%
EN.RO.D05.SDA.1065 | RO l Approval of Structural steel works | 14 | 0 | 28-May-26 A | 29-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.4Thermal Protection Shop Drawing Submittal |  | 140 | 3 | 11-Jun-26 A | 2026-11-03 | 90.24% | 81.95% | 80
EN.RO.D07.SDA.1080 | RO l Approval of Concrete tiles shop drawing | 14 | 0 | 11-Jun-26 A | 17-Jun-26 A | 0% | 100%
EN.RO.D07.SDA.1070 | RO l Approval of Aluminium panels cladding shop drawing | 14 | 3 | 02-Jul-26 A | 2026-11-03 | 100% | 80% | 72
EN.RO.D07.SDA.1075 | RO l Approval of Canopy aluminium cladding shop drawing | 14 | 3 | 02-Jul-26 A | 2026-11-03 | 100% | 80% | 80
KAFD00330-636-SBC-UP-261029.3.1.2.5Openings Shop Drawing Approval |  | 58 | 7 | 07-May-26 A | 2026-11-09 | 5.75% | 91.95% | 68
EN.RO.D08.SDA.1085 | RO l Approval of Steel doors shop drawing | 14 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
EN.RO.D08.SDA.1090 | RO l Approval of Aluminum windows & Louvers shop drawing | 14 | 7 | 22-Oct-26 A | 2026-11-09 | 35.71% | 50% | 68
KAFD00330-636-SBC-UP-261029.3.1.2.6Finishes Shop Drawing Approval |  | 131 | 3 | 18-Jun-26 A | 2026-11-03 | 63.18% | 87.36% | 57
EN.RO.D09.SDA.1100 | RO l Approval of Floor Works shop drawing | 14 | 0 | 18-Jun-26 A | 24-Jun-26 A | 0% | 100%
EN.RO.D09.SDA.1095 | RO l Approval of Gypsum board Works shop drawing | 14 | 3 | 25-Jun-26 A | 2026-11-03 | 100% | 80% | 57
KAFD00330-636-SBC-UP-261029.3.1.2.7Elevator Shop Drawing Approval |  | 14 | 0 | 18-Jun-26 A | 01-Jul-26 A | 0% | 100%
EN.RO.D14.SDA.1105 | RO l Approval of Elevators shop drawing | 14 | 0 | 18-Jun-26 A | 01-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.8Fire Supperssion Shop Drawing Approval |  | 59 | 0 | 21-May-26 A | 15-Jul-26 A | 0% | 100%
EN.RO.D21.SDA.1110 | RO l Approval of Fire Suppression for Pump room shop drawing | 14 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
EN.RO.D21.SDA.1115 | RO l Approval of Fire Suppression shop drawing GF | 14 | 0 | 28-May-26 A | 15-Jul-26 A | 0% | 100%
EN.RO.D21.SDA.1120 | RO l Approval of Fire Suppression shop drawing 1st | 14 | 0 | 28-May-26 A | 15-Jul-26 A | 0% | 100%
EN.RO.D21.SDA.1125 | RO l Approval of Fire Suppression shop drawing 2nd | 14 | 0 | 28-May-26 A | 15-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.9Plumbing Shop Drawing Approval |  | 37 | 0 | 12-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D22.SDA.1145 | RO l Approval of Sanitary Pipes shop drawing | 14 | 0 | 12-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D22.SDA.1130 | RO l Approval of Vibration & Seismic controls For Plumbingshop drawing | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D22.SDA.1135 | RO l Approval of Domestic water piping shop drawing | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D22.SDA.1140 | RO l Approval of Plumbing Valves shop drawing | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.10HVAC System Shop Drawing Approval |  | 34 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D23.SDA.1150 | RO l Approval of HVAC System shop drawing GF | 14 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D23.SDA.1155 | RO l Approval of HVAC System shop drawing 1st | 14 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.RO.D23.SDA.1160 | RO l Approval of HVAC System shop drawing 2nd | 14 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.11Electrical System Shop Drawing Approval |  | 144 | 3 | 26-Feb-26 A | 2026-11-03 | 14.35% | 97.13% | 79
EN.RO.D26.SDA.1175 | RO l Approval of Lightning & Earthing shop drawing | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
EN.RO.D26.SDA.1180 | RO l Approval of Power system shop drawing | 14 | 0 | 16-Apr-26 A | 01-Jul-26 A | 0% | 100%
EN.RO.D26.SDA.1185 | RO l Approval of Cable routing shop drawing | 14 | 0 | 30-Apr-26 A | 27-May-26 A | 0% | 100%
EN.RO.D26.SDA.1190 | RO l Approval of lighting system shop drawing | 14 | 0 | 07-May-26 A | 20-May-26 A | 0% | 100%
EN.RO.D26.SDA.1170 | RO l Approval of UPS System shop drawing | 14 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
EN.RO.D26.SDA.1165 | RO l Approval of Panel board shop drawing | 14 | 3 | 09-Jul-26 A | 2026-11-03 | 100% | 80% | 50
KAFD00330-636-SBC-UP-261029.3.1.2.12Low Current Shop Drawing Approval |  | 14 | 4 | 13-Aug-26 A | 2026-11-04 | 100% | 70% | 56
EN.RO.D27.SDA.1195 | RO l Approval of Communication System shop drawing | 14 | 4 | 13-Aug-26 A | 2026-11-04 | 100% | 70% | 56
KAFD00330-636-SBC-UP-261029.3.1.2.13Security Shop Drawing Approval |  | 90 | 14 | 28-May-26 A | 2026-11-18 | 0% | 26.32% | 41
EN.RO.D28.SDA.1210 | RO l Approval of Fire alarm system shop drawing | 14 | 0 | 28-May-26 A | 15-Jul-26 A | 0% | 100%
EN.RO.D28.SDA.1200 | RO l Approval of Access control shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 41
EN.RO.D28.SDA.1205 | RO l Approval of CCTV system shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 41
KAFD00330-636-SBC-UP-261029.3.1.2.14Earthworks Shop Drawing Approval |  | 48 | 0 | 22-Oct-25 A | 24-Dec-25 A | 100% | 100%
EN.RO.D31.SDA.1215 | RO l Approval of Excavation Works shop drawing | 14 | 0 | 22-Oct-25 A | 18-Nov-25 A | 100% | 100%
EN.RO.D31.SDA.1220 | RO l Approval of Concrete Piles shop drawing | 14 | 0 | 20-Nov-25 A | 10-Dec-25 A | 100% | 100%
EN.RO.D31.SDA.1225 | RO l Approval of Prestressed anchors shop drawing | 14 | 0 | 18-Dec-25 A | 24-Dec-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.1.2.15Exterior Improvement Shop Drawing Approval |  | 14 | 7 | 07-May-26 A | 2026-11-09 | 0% | 50% | 41
EN.RO.D32.SDA.1230 | RO l Approval of Precast concrete shop drawing | 14 | 7 | 07-May-26 A | 2026-11-09 | 0% | 50% | 41
KAFD00330-636-SBC-UP-261029.3.1.2.16Special System Shop Drawing Approval |  | 14 | 3 | 21-May-26 A | 2026-11-03 | 0% | 80% | 19
EN.RO.D33.SDA.1235 | RO l Approval of (BWRO) Plant shop drawing | 14 | 3 | 21-May-26 A | 2026-11-03 | 0% | 80% | 19
KAFD00330-636-SBC-UP-261029.3.1.2.17SCADA Shop Drawing Approval |  | 14 | 11 | 10-Sep-26 A | 2026-11-15 | 100% | 20% | 69
EN.RO.D40.SDA.1240 | RO l Approval of SCDA system shop drawing | 14 | 11 | 10-Sep-26 A | 2026-11-15 | 100% | 20% | 69
KAFD00330-636-SBC-UP-261029.3.2Pump-Station |  | 268 | 19 | 05-Nov-25 A | 2026-11-18 | 25.26% | 92.92% | 69
KAFD00330-636-SBC-UP-261029.3.2.1Pump-Station Technical Submittal |  | 39 | 0 | 05-Nov-25 A | 26-Nov-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.1.1Pump-Station Technical Submittal |  | 18 | 0 | 05-Nov-25 A | 18-Nov-25 A | 100% | 100%
EN.PS.D02.SDS.1000 | IPS l Submission of Soil Investigations Technical Report | 18 | 0 | 05-Nov-25 A | 18-Nov-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.1.2Pump-Station Technical Approval |  | 14 | 0 | 20-Nov-25 A | 26-Nov-25 A | 100% | 100%
EN.PS.D02.SDA.1000 | IPS l Approval of Soil Investigations Technical Report | 14 | 0 | 20-Nov-25 A | 26-Nov-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2Pump-Station Shop Drawing |  | 268 | 19 | 04-Dec-25 A | 2026-11-18 | 24.95% | 92.89% | 69
KAFD00330-636-SBC-UP-261029.3.2.2.1Pump-Station Shop Drawing Submittal |  | 204 | 10 | 04-Dec-25 A | 2026-11-10 | 20.51% | 97.52% | 65
KAFD00330-636-SBC-UP-261029.3.2.2.1.1Concrete Shop Drawing Submittal |  | 16 | 0 | 04-Dec-25 A | 24-Dec-25 A | 100% | 100%
EN.PS.D03.SDS.1010 | IPS l Submission of Concrete Works Shop drawing | 16 | 0 | 04-Dec-25 A | 24-Dec-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.2Masonry Shop Drawing Submittal |  | 15 | 0 | 04-Dec-25 A | 28-Jan-26 A | 100% | 100%
EN.PS.D04.SDS.1015 | IPS l Submission of Masonry works Shop drawing | 15 | 0 | 04-Dec-25 A | 28-Jan-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.3Metal Shop Drawing Submittal |  | 12 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
EN.PS.D05.SDS.1020 | IPS l Submission of Trench covers Shop drawing | 12 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.4Thermal Protection Shop Drawing Submittal |  | 12 | 0 | 16-Feb-26 A | 02-Sep-26 A | 0% | 100%
EN.PS.D07.SDS.1025 | IPS l Submission of Aluminum cladding Shop drawing | 12 | 0 | 16-Feb-26 A | 02-Sep-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.5Openings Shop Drawing Submittal |  | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 16.67% | 100%
EN.PS.D08.SDS.1030 | IPS l Submission of Steel doors Shop drawing | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 16.67% | 100%
EN.PS.D08.SDS.1035 | IPS l Submission of Aluminium louvers Shop drawing | 12 | 0 | 26-Feb-26 A | 04-Mar-26 A | 16.67% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.6Special construction Shop Drawing Submittal |  | 10 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
EN.PS.D13.SDS.1040 | IPS l Submission of Aluminium Control booths Shop drawing | 10 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.7Fire Supperssion Shop Drawing Submittal |  | 15 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
EN.PS.D21.SDS.1045 | IPS l Submission of Fire Suppression Shop drawing | 15 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.8Plumbing Shop Drawing Submittal |  | 46 | 0 | 15-Jan-26 A | 22-Apr-26 A | 0.44% | 100%
EN.PS.D22.SDS.1050 | IPS l Submission of Electrical room plumbing Shop drawing | 10 | 0 | 15-Jan-26 A | 21-Jan-26 A | 20% | 100%
EN.PS.D22.SDS.1055 | IPS l Submission of Pump room piping & fitting Shop drawing | 18 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.PS.D22.SDS.1060 | IPS l Submission of Submersible sump pumps Shop drawing | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.9HVAC System Shop Drawing Submittal |  | 20 | 0 | 25-Dec-25 A | 21-Jan-26 A | 0% | 100%
EN.PS.D23.SDS.1065 | IPS l Submission of HVAC System shop drawing | 20 | 0 | 25-Dec-25 A | 21-Jan-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.10Electrical System Shop Drawing Submittal |  | 66 | 0 | 25-Dec-25 A | 29-Apr-26 A | 1.16% | 100%
EN.PS.D26.SDS.1090 | IPS l Submission of lighting system shop drawing | 18 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
EN.PS.D26.SDS.1080 | IPS l Submission of Lightning & Earthing shop drawing | 15 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
EN.PS.D26.SDS.1075 | IPS l Submission of Power system shop drawing | 12 | 0 | 16-Apr-26 A | 29-Apr-26 A | 16.67% | 100%
EN.PS.D26.SDS.1085 | IPS l Submission of Cable routing shop drawing | 16 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
EN.PS.D26.SDS.1070 | IPS l Submission of Panel board shop drawing | 20 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.11Low Current Shop Drawing Submittal |  | 20 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.PS.D27.SDS.1095 | IPS l Submission of Communication System shop drawing | 20 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.12Security Shop Drawing Submittal |  | 18 | 0 | 25-Dec-25 A | 29-Apr-26 A | 0% | 100%
EN.PS.D28.SDS.1110 | IPS l Submission of Fire alarm system shop drawing | 18 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
EN.PS.D28.SDS.1100 | IPS l Submission of Access control shop drawing | 18 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.PS.D28.SDS.1105 | IPS l Submission of CCTV system shop drawing | 18 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.13Earthworks Shop Drawing Submittal |  | 20 | 0 | 11-Dec-25 A | 17-Dec-25 A | 100% | 100%
EN.PS.D31.SDS.1115 | IPS l Submission of Reinforced piles Shop drawing | 20 | 0 | 11-Dec-25 A | 17-Dec-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.1.14External Improvement Shop Drawing Submittal |  | 48 | 10 | 15-Jan-26 A | 2026-11-10 | 0% | 73.09% | 65
EN.PS.D32.SDS.1120 | IPS l Submission of concrete paving Shop drawing | 16 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.PS.D32.SDS.1135 | IPS l Submission of Planting Shop drawing | 12 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.PS.D32.SDS.1125 | IPS l Submission of Sliding gates Shop drawing | 16 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.PS.D32.SDS.1130 | IPS l Submission of Precast concrete wall Shop drawing | 20 | 10 | 23-Apr-26 A | 2026-11-10 | 0% | 50% | 37
KAFD00330-636-SBC-UP-261029.3.2.2.1.15Special System Shop Drawing Submittal |  | 20 | 0 | 14-May-26 A | 03-Jun-26 A | 0% | 100%
EN.PS.D40.SDS.1140 | IPS l Submission of Process Control Systems Shop drawing | 20 | 0 | 14-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2Pump-Station Shop Drawing Approval |  | 187 | 14 | 25-Dec-25 A | 2026-11-18 | 29.39% | 88.27% | 49
KAFD00330-636-SBC-UP-261029.3.2.2.2.1Concrete Shop Drawing Approval |  | 14 | 0 | 08-Jan-26 A | 14-Jan-26 A | 100% | 100%
EN.PS.D03.SDA.1010 | IPS l Approval of Concrete Works Shop drawing | 14 | 0 | 08-Jan-26 A | 14-Jan-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.2Masonry Shop Drawing Approval |  | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 14.29% | 100%
EN.PS.D04.SDA.1015 | IPS l Approval of Masonry works Shop drawing | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 14.29% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.3Metal Shop Drawing Approval |  | 14 | 7 | 13-Aug-26 A | 2026-11-09 | 100% | 50% | 32
EN.PS.D05.SDA.1020 | IPS l Approval of Trench covers Shop drawing | 14 | 7 | 13-Aug-26 A | 2026-11-09 | 100% | 50% | 32
KAFD00330-636-SBC-UP-261029.3.2.2.2.4Thermal Protection Shop Drawing Approval |  | 14 | 4 | 01-Oct-26 A | 2026-11-04 | 100% | 80% | 15
EN.PS.D07.SDA.1025 | IPS l Approval of Aluminum cladding Shop drawing | 14 | 4 | 01-Oct-26 A | 2026-11-04 | 100% | 80% | 15
KAFD00330-636-SBC-UP-261029.3.2.2.2.5Openings Shop Drawing Approval |  | 58 | 14 | 27-Aug-26 A | 2026-11-18 | 46.29% | 46.29% | 43
EN.PS.D08.SDA.1035 | IPS l Approval of Aluminium louvers Shop drawing | 14 | 0 | 27-Aug-26 A | 02-Sep-26 A | 100% | 100%
EN.PS.D08.SDA.1030 | IPS l Approval of Steel doors Shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 35
KAFD00330-636-SBC-UP-261029.3.2.2.2.6Special construction Shop Drawing Approval |  | 14 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
EN.PS.D13.SDA.1040 | IPS l Approval of Aluminium Control booths Shop drawing | 14 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.7Fire Supperssion Shop Drawing Approval |  | 14 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
EN.PS.D21.SDA.1045 | IPS l Approval of Fire Suppression Shop drawing | 14 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.8Plumbing Shop Drawing Approval |  | 44 | 0 | 12-Feb-26 A | 20-May-26 A | 0% | 100%
EN.PS.D22.SDA.1050 | IPS l Approval of Electrical room plumbing Shop drawing | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.PS.D22.SDA.1055 | IPS l Approval of Pump room piping & fitting Shop drawing | 14 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
EN.PS.D22.SDA.1060 | IPS l Approval of Submersible sump pumps Shop drawing | 14 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.9HVAC System Shop Drawing Approval |  | 14 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.PS.D23.SDA.1065 | IPS l Approval of HVAC System shop drawing | 14 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.10Electrical System Shop Drawing Approvall |  | 139 | 3 | 25-Dec-25 A | 2026-11-03 | 24.65% | 93.49% | 56
EN.PS.D26.SDA.1090 | IPS l Approval of lighting system shop drawing | 14 | 0 | 25-Dec-25 A | 28-Jan-26 A | 0% | 100%
EN.PS.D26.SDA.1080 | IPS l Approval of Lightning & Earthing shop drawing | 14 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
EN.PS.D26.SDA.1085 | IPS l Approval of Cable routing shop drawing | 14 | 3 | 23-Apr-26 A | 2026-11-03 | 0% | 90% | 52
EN.PS.D26.SDA.1075 | IPS l Approval of Power system shop drawing | 14 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.PS.D26.SDA.1070 | IPS l Approval of Panel board shop drawing | 14 | 3 | 25-Jun-26 A | 2026-11-03 | 100% | 80% | 50
KAFD00330-636-SBC-UP-261029.3.2.2.2.11Low Current Shop Drawing Approval |  | 14 | 2 | 26-Feb-26 A | 2026-11-02 | 0% | 90% | 41
EN.PS.D27.SDA.1095 | IPS l Approval of Communication System shop drawing | 14 | 2 | 26-Feb-26 A | 2026-11-02 | 0% | 90% | 41
KAFD00330-636-SBC-UP-261029.3.2.2.2.12Security Shop Drawing Approval |  | 82 | 14 | 17-May-26 A | 2026-11-18 | 0% | 44.91% | 38
EN.PS.D28.SDA.1110 | IPS l Approval of Fire alarm system shop drawing | 14 | 0 | 17-May-26 A | 15-Jul-26 A | 0% | 100%
EN.PS.D28.SDA.1100 | IPS l Approval of Access control shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 2
EN.PS.D28.SDA.1105 | IPS l Approval of CCTV system shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 38
KAFD00330-636-SBC-UP-261029.3.2.2.2.13Earthworks Shop Drawing Approval |  | 14 | 0 | 01-Jan-26 A | 07-Jan-26 A | 100% | 100%
EN.PS.D31.SDA.1115 | IPS l Approval of Reinforced piles Shop drawing | 14 | 0 | 01-Jan-26 A | 07-Jan-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.3.2.2.2.14External Improvement Shop Drawing Approval |  | 155 | 14 | 14-May-26 A | 2026-11-18 | 23.31% | 63.33% | 48
EN.PS.D32.SDA.1130 | IPS l Approval of Precast concrete wall Shop drawing | 14 | 7 | 14-May-26 A | 2026-11-09 | 0% | 50% | 30
EN.PS.D32.SDA.1120 | IPS l Approval of concrete paving Shop drawing | 14 | 0 | 28-May-26 A | 24-Jun-26 A | 0% | 100%
EN.PS.D32.SDA.1135 | IPS l Approval of Planting Shop drawing | 14 | 0 | 23-Jul-26 A | 29-Jul-26 A | 100% | 100%
EN.PS.D32.SDA.1125 | IPS l Approval of Sliding gates Shop drawing | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 48
KAFD00330-636-SBC-UP-261029.3.2.2.2.15Special System Shop Drawing Approval |  | 14 | 3 | 28-May-26 A | 2026-11-03 | 0% | 80% | 52
EN.PS.D40.SDA.1140 | IPS l Approval of Process Control Systems Shop drawing | 14 | 3 | 28-May-26 A | 2026-11-03 | 0% | 80% | 52
KAFD00330-636-SBC-UP-261029.3.3Collection System |  | 134 | 4 | 25-Dec-25 A | 2026-11-03 | 0% | 97.08% | 90
KAFD00330-636-SBC-UP-261029.3.3.1Collection System Shop Drawing Submittal |  | 94 | 3 | 25-Dec-25 A | 2026-11-02 | 0% | 97.82% | 68
KAFD00330-636-SBC-UP-261029.3.3.1.1Plumbing Shop Drawing Submittal |  | 54 | 0 | 25-Dec-25 A | 13-May-26 A | 0% | 100%
EN.CL.D22.SDS.1000 | CLS l Submission of Submersible pump room shop drawing | 20 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
EN.CL.D33.SDS.1015 | CLS l Submission of Pressured network inside the tunnel shop drawing | 20 | 0 | 25-Dec-25 A | 31-Dec-25 A | 0% | 100%
EN.CL.D33.SDS.1005 | CLS l Submission of Gravity network shop drawing | 20 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
EN.CL.D33.SDS.1010 | CLS l Submission of Pressured network in trenches shop drawing | 10 | 0 | 15-Jan-26 A | 18-Feb-26 A | 0% | 100%
EN.CL.D33.SDS.1020 | CLS l Submission of Fabricated Channel shop drawing | 14 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.3.1.2Electrical System Shop Drawing Submittal |  | 40 | 3 | 12-Feb-26 A | 2026-11-02 | 0% | 92.33% | 68
EN.CL.D33.SDS.1030 | CLS l Submission of Fiber Optic network drawing | 20 | 3 | 12-Feb-26 A | 2026-11-02 | 0% | 90% | 41
EN.CL.D33.SDS.1025 | CLS l Submission of Remote terminal unit (RTU) shop drawing | 20 | 0 | 12-Feb-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.3.2Collection System Shop Drawing Approval |  | 75 | 3 | 12-Feb-26 A | 2026-11-03 | 0% | 96.34% | 64
KAFD00330-636-SBC-UP-261029.3.3.2.1Plumbing Shop Drawing Approval |  | 42 | 2 | 12-Feb-26 A | 2026-11-02 | 0% | 97.93% | 65
EN.CL.D33.SDA.1015 | CLS l Approval of Pressured network inside the tunnel shop drawing | 14 | 2 | 12-Feb-26 A | 2026-11-02 | 0% | 95% | -51
EN.CL.D33.SDA.1010 | CLS l Approval of Pressured network in trenches shop drawing | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
EN.CL.D22.SDA.1000 | CLS l Approval of Submersible pump room shop drawing | 14 | 0 | 12-Mar-26 A | 18-Mar-26 A | 0% | 100%
EN.CL.D33.SDA.1005 | CLS l Approval of Gravity network shop drawing | 14 | 0 | 12-Apr-26 A | 29-Apr-26 A | 0% | 100%
EN.CL.D33.SDA.1020 | CLS l Approval of Fabricated Channel shop drawing | 14 | 0 | 14-May-26 A | 17-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.3.3.2.2Electrical System Shop Drawing Approval |  | 30 | 3 | 12-Feb-26 A | 2026-11-03 | 0% | 92.33% | 56
EN.CL.D33.SDA.1030 | CLS l Approval of Fiber Optic network drawing | 14 | 3 | 12-Feb-26 A | 2026-11-03 | 0% | 90% | 34
EN.CL.D33.SDA.1025 | CLS l Approval of Remote terminal unit (RTU) shop drawing | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4Procurement |  | 426 | 92 | 12-Nov-25 A | 2027-01-29 | 8.58% | 68.28% | 61
KAFD00330-636-SBC-UP-261029.4.1RO Plant |  | 426 | 92 | 12-Nov-25 A | 2027-01-29 | 10.35% | 66.04% | 61
KAFD00330-636-SBC-UP-261029.4.1.1Short Lead Items |  | 378 | 67 | 12-Nov-25 A | 2027-01-04 | 40.06% | 63.12% | 86
KAFD00330-636-SBC-UP-261029.4.1.1.1RO Plant Material Submittal - Short Lead |  | 284 | 7 | 12-Nov-25 A | 2026-11-07 | 46.65% | 98.72% | 107
KAFD00330-636-SBC-UP-261029.4.1.1.1.1Structural Material Submittal |  | 98 | 0 | 12-Nov-25 A | 04-Mar-26 A | 67.14% | 100%
PR.RO.D31.MTS.1035 | RO l MT Submission for Concrete Piles & prestressed anchors | 14 | 0 | 12-Nov-25 A | 03-Dec-25 A | 100% | 100%
PR.RO.D07.MTS.1030 | RO l MT Submission for Thermal & Moisture insulation | 12 | 0 | 22-Jan-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.2Finishes Material Submittal |  | 246 | 7 | 16-Apr-26 A | 2026-11-07 | 35.28% | 88.92% | 104
PR.RO.D08.MTS.1050 | RO l MT Submission for Steel doors | 12 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.RO.D04.MTS.1045 | RO l MT Submission for Stone cladding | 12 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.RO.D04.MTS.1040 | RO l MT Submission for Masonary | 14 | 7 | 28-May-26 A | 2026-11-07 | 0% | 50% | 0
PR.RO.D09.MTS.1055 | RO l MT Submission for Gypsum board | 12 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.RO.D09.MTS.1060 | RO l MT Submission for Floor | 12 | 0 | 23-Jul-26 A | 29-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.3Fire Supperssion Material Submittal |  | 18 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
PR.RO.D21.MTS.1065 | RO l MT Submission for Fire Suppression piping & fitting | 18 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.4Plumbing Material Submittal |  | 38 | 0 | 01-Jan-26 A | 22-Apr-26 A | 0% | 100%
PR.RO.D22.MTS.1075 | RO l MT Submission for Sanitary pipes & fitting | 16 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
PR.RO.D22.MTS.1070 | RO l MT Submission for Water supply pipes & Valves | 20 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
PR.RO.D22.MTS.1080 | RO l MT Submission for Plumbing Fixtures | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.5HVAC System Material Submittal |  | 38 | 0 | 29-Jan-26 A | 22-Apr-26 A | 0% | 100%
PR.RO.D23.MTS.1085 | RO l MT Submission for HVAC piping & Valves | 20 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
PR.RO.D23.MTS.1090 | RO l MT Submission for HVAC Ducts | 18 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D23.MTS.1095 | RO l MT Submission for HVAC Accessories | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.6Electrical System Material Submittal |  | 258 | 0 | 26-Feb-26 A | 09-Sep-26 A | 41.94% | 100%
PR.RO.D26.MTS.1110 | RO l MT Submission for Cable routing matrial | 18 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.RO.D26.MTS.1105 | RO l MT Submission for Uninterruptible Power Supply (UPS) | 18 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D26.MTS.1115 | RO l MT Submission for Sochets & switches matrial | 18 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.RO.D26.MTS.1100 | RO l MT Submission for Distribution board | 20 | 0 | 03-Sep-26 A | 09-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.7Low Current Material Submittal |  | 48 | 0 | 15-Jan-26 A | 13-May-26 A | 0% | 100%
PR.RO.D27.MTS.1125 | RO l MT Submission for Communication Cables | 16 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
PR.RO.D27.MTS.1130 | RO l MT Submission for Data communication components | 12 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.RO.D27.MTS.1120 | RO l MT Submission for Communication equipment fitting | 20 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D27.MTS.1135 | RO l MT Submission for Telecommunication components | 12 | 0 | 23-Apr-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.8Security Material Submittal |  | 16 | 0 | 15-Jan-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D28.MTS.1150 | RO l MT Submission for Fire alarm components | 16 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
PR.RO.D28.MTS.1140 | RO l MT Submission for Access control components | 16 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D28.MTS.1145 | RO l MT Submission for CCTV system components | 16 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.1.9External Improvement Material Submittal |  | 32 | 0 | 30-Jul-26 A | 16-Sep-26 A | 100% | 100%
PR.RO.D32.MTS.1155 | RO l MT Submission for Precast concrete paving | 30 | 0 | 30-Jul-26 A | 05-Aug-26 A | 100% | 100%
PR.RO.D32.MTS.1160 | RO l MT Submission for Precast concrete wall | 30 | 0 | 10-Sep-26 A | 16-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2RO Plant Material Approval - Short Lead |  | 245 | 14 | 04-Dec-25 A | 2026-11-18 | 51.14% | 84.23% | 91
KAFD00330-636-SBC-UP-261029.4.1.1.2.1Structural Material Approval |  | 83 | 0 | 04-Dec-25 A | 29-Jul-26 A | 67.14% | 100%
PR.RO.D31.MTA.1035 | RO l MT Approval for Concrete Piles & prestressed anchors | 14 | 0 | 04-Dec-25 A | 21-Jan-26 A | 100% | 100%
PR.RO.D07.MTA.1030 | RO l MT Approval for Thermal & Moisture insulation | 14 | 0 | 12-Mar-26 A | 29-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2.2Finishes Material Approval |  | 178 | 14 | 07-May-26 A | 2026-11-18 | 49.09% | 43.46% | 91
PR.RO.D08.MTA.1050 | RO l MT Approval for Steel doors | 14 | 7 | 07-May-26 A | 2026-11-09 | 0% | 50% | 55
PR.RO.D09.MTA.1055 | RO l MT Approval for Gypsum board | 14 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.RO.D04.MTA.1040 | RO l MT Approval for Masonary | 14 | 7 | 23-Jul-26 A | 2026-11-09 | 100% | 50% | 0
PR.RO.D09.MTA.1060 | RO l MT Approval for Floor | 14 | 13 | 22-Oct-26 A | 2026-11-17 | 35.71% | 10% | 37
PR.RO.D04.MTA.1045 | RO l MT Approval for Stone cladding | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.1.1.2.3Fire Supperssion Material Approval |  | 14 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
PR.RO.D21.MTA.1065 | RO l MT Approval for Fire Suppression piping & fitting | 14 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2.4Plumbing Material Approval |  | 32 | 0 | 22-Jan-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D22.MTA.1070 | RO l MT Approval for Water supply pipes & Valves | 14 | 0 | 22-Jan-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D22.MTA.1075 | RO l MT Approval for Sanitary pipes & fitting | 14 | 0 | 22-Jan-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D22.MTA.1080 | RO l MT Approval for Plumbing Fixtures | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2.5HVAC System Material Approvall |  | 30 | 0 | 12-Feb-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MTA.1085 | RO l MT Approval for HVAC piping & Valves | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D23.MTA.1090 | RO l MT Approval for HVAC Ducts | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D23.MTA.1095 | RO l MT Approval for HVAC Accessories | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2.6Electrical System Material Approval |  | 193 | 11 | 26-Feb-26 A | 2026-11-15 | 81.13% | 72.74% | 94
PR.RO.D26.MTA.1110 | RO l MT Approval for Cable routing matrial | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.RO.D26.MTA.1105 | RO l MT Approval for Uninterruptible Power Supply (UPS) | 14 | 0 | 02-Jul-26 A | 26-Aug-26 A | 100% | 100%
PR.RO.D26.MTA.1115 | RO l MT Approval for Sochets & switches matrial | 14 | 0 | 02-Jul-26 A | 30-Sep-26 A | 100% | 100%
PR.RO.D26.MTA.1100 | RO l MT Approval for Distribution board | 14 | 11 | 24-Sep-26 A | 2026-11-15 | 100% | 20% | 94
KAFD00330-636-SBC-UP-261029.4.1.1.2.7Low Current Material Approval |  | 232 | 0 | 23-Apr-26 A | 08-Jul-26 A | 61.98% | 100%
PR.RO.D27.MTA.1125 | RO l MT Approval for Communication Cables | 14 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D27.MTA.1120 | RO l MT Approval for Communication equipment fitting | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D27.MTA.1135 | RO l MT Approval for Telecommunication components | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D27.MTA.1130 | RO l MT Approval for Data communication components | 14 | 0 | 02-Jul-26 A | 08-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.2.8Security Material Approval |  | 182 | 14 | 16-Apr-26 A | 2026-11-18 | 0% | 26.32% | 91
PR.RO.D28.MTA.1150 | RO l MT Approval for Fire alarm components | 14 | 0 | 16-Apr-26 A | 06-May-26 A | 0% | 100%
PR.RO.D28.MTA.1145 | RO l MT Approval for CCTV system components | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 8
PR.RO.D28.MTA.1140 | RO l MT Approval for Access control components | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.1.1.2.9External Improvement Material Approval |  | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
PR.RO.D32.MTA.1155 | RO l MT Approval for Precast concrete paving | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
PR.RO.D32.MTA.1160 | RO l MT Approval for Precast concrete wall | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.1.1.3RO Plant Material PO - Short Lead |  | 305 | 16 | 11-Dec-25 A | 2026-12-07 | 40.94% | 97.89% | 49
KAFD00330-636-SBC-UP-261029.4.1.1.3.1Structural Material PO |  | 95 | 0 | 11-Dec-25 A | 01-Apr-26 A | 67.14% | 100%
PR.RO.D31.MPO.1035 | RO l PO Placement for Concrete Piles & prestressed anchors | 10 | 0 | 11-Dec-25 A | 17-Dec-25 A | 100% | 100%
PR.RO.D07.MPO.1030 | RO l PO Placement for Thermal & Moisture insulation | 12 | 0 | 26-Feb-26 A | 01-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.2Finishes Material PO |  | 264 | 0 | 21-May-26 A | 28-Oct-26 A | 44.45% | 100%
PR.RO.D08.MPO.1050 | RO l PO Placement for Steel doors | 18 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D04.MPO.1045 | RO l PO Placement for Stone cladding | 12 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D09.MPO.1055 | RO l PO Placement for Gypsum board | 18 | 0 | 06-Aug-26 A | 12-Aug-26 A | 100% | 100%
PR.RO.D04.MPO.1040 | RO l PO Placement for Masonary | 12 | 0 | 03-Sep-26 A | 28-Oct-26 A | 100% | 100%
PR.RO.D09.MPO.1060 | RO l PO Placement for Floor | 18 | 0 | 22-Oct-26 A | 28-Oct-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.3Fire Supperssion Material PO |  | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D21.MPO.1065 | RO l PO Placement for Fire Suppression piping & fitting | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.4Plumbing Material PO |  | 42 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D22.MPO.1070 | RO l PO Placement for Water supply pipes & Valves | 18 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D22.MPO.1075 | RO l PO Placement for Sanitary pipes & fitting | 18 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D22.MPO.1080 | RO l PO Placement for Plumbing Fixtures | 20 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.5HVAC System Material PO |  | 40 | 0 | 28-May-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1085 | RO l PO Placement for HVAC piping & Valves | 20 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1090 | RO l PO Placement for HVAC Ducts | 20 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1095 | RO l PO Placement for HVAC Accessories | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.6Electrical System Material PO |  | 54 | 0 | 21-May-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D26.MPO.1100 | RO l PO Placement for Distribution board | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D26.MPO.1110 | RO l PO Placement for Cable routing matrial | 16 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D26.MPO.1115 | RO l PO Placement for Sochets & switches matrial | 16 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D26.MPO.1105 | RO l PO Placement for Uninterruptible Power Supply (UPS) | 16 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.7Low Current Material PO |  | 52 | 0 | 28-May-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D27.MPO.1125 | RO l PO Placement for Communication Cables | 18 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D27.MPO.1130 | RO l PO Placement for Data communication components | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D27.MPO.1120 | RO l PO Placement for Communication equipment fitting | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D27.MPO.1135 | RO l PO Placement for Telecommunication components | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.3.8Security Material PO |  | 219 | 16 | 28-May-26 A | 2026-12-07 | 0% | 54.21% | 23
PR.RO.D28.MPO.1150 | RO l PO Placement for Fire alarm components | 16 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D28.MPO.1140 | RO l PO Placement for Access control components | 16 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D28.MPO.1145 | RO l PO Placement for CCTV system components | 16 | 16 | 2026-11-19 | 2026-12-07 | 0% | 0% | 10
KAFD00330-636-SBC-UP-261029.4.1.1.3.9External Improvement Material PO |  | 56 | 0 | 28-May-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D32.MPO.1160 | RO l PO Placement for Precast concrete wall | 40 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D32.MPO.1155 | RO l PO Placement for Precast concrete paving | 25 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.4RO Plant Material Delivery and Fabrication - Short Lead |  | 115 | 67 | 05-Dec-25 A | 2027-01-04 | 36.82% | 42.07% | 50
KAFD00330-636-SBC-UP-261029.4.1.1.4.1Structural Material Delivery and Fabrication |  | 115 | 11 | 05-Dec-25 A | 2026-11-09 | 67.14% | 77% | 5
PR.RO.D07.MTD.1030 | RO l MT Delivery for Thermal & Moisture insulation | 16 | 11 | 05-Dec-25 A | 2026-11-09 | 0% | 30% | 5
PR.RO.D31.MTD.1035 | RO l MT Delivery for Concrete Piles & prestressed anchors | 14 | 0 | 04-Jan-26 A | 17-Jun-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.1.4.2Finishes Material Delivery and Fabrication |  | 37 | 37 | 2026-10-30 | 2026-12-05 | 0% | 0% | 79
PR.RO.D04.MTD.1045 | RO l MT Delivery for Stone cladding | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 96
PR.RO.D09.MTD.1055 | RO l MT Delivery for Gypsum board | 25 | 25 | 2026-10-31 | 2026-11-24 | 0% | 0% | 60
PR.RO.D04.MTD.1040 | RO l MT Delivery for Masonary | 30 | 30 | 2026-11-01 | 2026-11-30 | 0% | 0% | 0
PR.RO.D09.MTD.1060 | RO l MT Delivery for Floor | 35 | 35 | 2026-11-01 | 2026-12-05 | 0% | 0% | 51
PR.RO.D08.MTD.1050 | RO l MT Delivery for Steel doors | 25 | 25 | 2026-11-01 | 2026-11-25 | 0% | 0% | 77
KAFD00330-636-SBC-UP-261029.4.1.1.4.3Fire Supperssion Material Delivery and Fabrication |  | 25 | 24 | 22-Oct-26 A | 2026-11-23 | 24% | 5% | 29
PR.RO.D21.MTD.1065 | RO l MT Delivery for Fire Suppression piping & fitting | 25 | 24 | 22-Oct-26 A | 2026-11-23 | 24% | 5% | 29
KAFD00330-636-SBC-UP-261029.4.1.1.4.4Plumbing Material Delivery and Fabrication |  | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 88
PR.RO.D22.MTD.1075 | RO l MT Delivery for Sanitary pipes & fitting | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | -1
PR.RO.D22.MTD.1070 | RO l MT Delivery for Water supply pipes & Valves | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 46
PR.RO.D22.MTD.1080 | RO l MT Delivery for Plumbing Fixtures | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 88
KAFD00330-636-SBC-UP-261029.4.1.1.4.5HVAC System Material Delivery and Fabrication |  | 25 | 25 | 2026-10-31 | 2026-11-24 | 0% | 0% | 69
PR.RO.D23.MTD.1090 | RO l MT Delivery for HVAC Ducts | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 33
PR.RO.D23.MTD.1085 | RO l MT Delivery for HVAC piping & Valves | 25 | 25 | 2026-10-31 | 2026-11-24 | 0% | 0% | 40
PR.RO.D23.MTD.1095 | RO l MT Delivery for HVAC Accessories | 22 | 22 | 2026-10-31 | 2026-11-21 | 0% | 0% | 72
KAFD00330-636-SBC-UP-261029.4.1.1.4.6Electrical System Material Delivery and Fabrication |  | 26 | 26 | 2026-10-30 | 2026-11-24 | 0% | 0% | 91
PR.RO.D26.MTD.1100 | RO l MT Delivery for Distribution board | 26 | 26 | 2026-10-30 | 2026-11-24 | 0% | 0% | 63
PR.RO.D26.MTD.1105 | RO l MT Delivery for Uninterruptible Power Supply (UPS) | 22 | 22 | 2026-10-30 | 2026-11-20 | 0% | 0% | 95
PR.RO.D26.MTD.1110 | RO l MT Delivery for Cable routing matrial | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 45
PR.RO.D26.MTD.1115 | RO l MT Delivery for Sochets & switches matrial | 20 | 20 | 2026-10-31 | 2026-11-19 | 0% | 0% | 88
KAFD00330-636-SBC-UP-261029.4.1.1.4.7Low Current Material Delivery and Fabrication |  | 30 | 30 | 2026-10-31 | 2026-11-29 | 0% | 0% | 77
PR.RO.D27.MTD.1125 | RO l MT Delivery for Communication Cables | 30 | 30 | 2026-10-31 | 2026-11-29 | 0% | 0% | 54
PR.RO.D27.MTD.1120 | RO l MT Delivery for Communication equipment fitting | 28 | 28 | 2026-10-31 | 2026-11-27 | 0% | 0% | 61
PR.RO.D27.MTD.1135 | RO l MT Delivery for Telecommunication components | 25 | 25 | 2026-10-31 | 2026-11-24 | 0% | 0% | 76
PR.RO.D27.MTD.1130 | RO l MT Delivery for Data communication components | 27 | 27 | 2026-10-31 | 2026-11-26 | 0% | 0% | 80
KAFD00330-636-SBC-UP-261029.4.1.1.4.8Security Material Delivery and Fabrication |  | 73 | 67 | 22-Oct-26 A | 2027-01-04 | 6.07% | 18.42% | 12
PR.RO.D28.MTD.1150 | RO l MT Delivery for Fire alarm components | 26 | 8 | 22-Oct-26 A | 2026-11-07 | 23.08% | 70% | 65
PR.RO.D28.MTD.1140 | RO l MT Delivery for Access control components | 26 | 26 | 2026-10-30 | 2026-11-24 | 0% | 0% | 53
PR.RO.D28.MTD.1145 | RO l MT Delivery for CCTV system components | 28 | 28 | 2026-12-08 | 2027-01-04 | 0% | 0% | 12
KAFD00330-636-SBC-UP-261029.4.1.1.4.9External Improvement Material Delivery and Fabrication |  | 55 | 55 | 2026-10-30 | 2026-12-23 | 0% | 0% | 45
PR.RO.D32.MTD.1160 | RO l MT Delivery for Precast concrete wall | 55 | 55 | 2026-10-30 | 2026-12-23 | 0% | 0% | 13
PR.RO.D32.MTD.1155 | RO l MT Delivery for Precast concrete paving | 35 | 35 | 2026-10-30 | 2026-12-03 | 0% | 0% | 65
KAFD00330-636-SBC-UP-261029.4.1.2Long Lead Item |  | 426 | 92 | 11-Dec-25 A | 2027-01-29 | 5.38% | 66.53% | 61
KAFD00330-636-SBC-UP-261029.4.1.2.1RO Plant Material Submittal - Long Lead |  | 281 | 8 | 11-Dec-25 A | 2026-11-08 | 5.55% | 99.91% | 106
KAFD00330-636-SBC-UP-261029.4.1.2.1.1Finishes Material Submittal |  | 95 | 8 | 30-Apr-26 A | 2026-11-08 | 0% | 98.04% | 48
PR.RO.D05.MTS.1165 | RO l MT Submission for Structural steel | 35 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
PR.RO.D08.MTS.1175 | RO l MT Submission for Acoustic & Fire rated doors | 30 | 8 | 07-May-26 A | 2026-11-08 | 0% | 75% | 48
PR.RO.D07.MTS.1170 | RO l MT Submission for Aluminium cladding | 30 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.2Elevator Material Submittal |  | 22 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
PR.RO.D14.MTS.1180 | RO l MT Submission for Elevators | 22 | 0 | 15-Jan-26 A | 21-Jan-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.3Fire Supperssion Material Submittal |  | 84 | 0 | 22-Jan-26 A | 04-Feb-26 A | 0% | 100%
PR.RO.D21.MTS.1185 | RO l MT Submission for Fire Suppression equipment | 28 | 0 | 22-Jan-26 A | 28-Jan-26 A | 0% | 100%
PR.RO.D21.MTS.1190 | RO l MT Submission for Foam Water system | 28 | 0 | 22-Jan-26 A | 28-Jan-26 A | 0% | 100%
PR.RO.D21.MTS.1195 | RO l MT Submission for Clean Agent FK-5.1.12 System | 28 | 0 | 29-Jan-26 A | 04-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.4Plumbing Material Submittal |  | 60 | 0 | 12-Feb-26 A | 29-Apr-26 A | 0% | 100%
PR.RO.D22.MTS.1205 | RO l MT Submission for R&T Equipments & valves | 30 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D22.MTS.1200 | RO l MT Submission for Plumping equipment | 30 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.5HVAC System Material Submittal |  | 48 | 0 | 12-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.RO.D23.MTS.1215 | RO l MT Submission for Air Handlig Units | 28 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D23.MTS.1220 | RO l MT Submission for Split & Fan coil Units & Exhaust Fans | 24 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.RO.D23.MTS.1210 | RO l MT Submission for HVAC equipment | 24 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.6Electrical System Material Submittal |  | 266 | 0 | 26-Feb-26 A | 02-Sep-26 A | 29.86% | 100%
PR.RO.D26.MTS.1245 | RO l MT Submission for Lightning & Earthing | 18 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.RO.D26.MTS.1255 | RO l MT Submission for Lighting system | 21 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.RO.D26.MTS.1250 | RO l MT Submission for Low voltage electrical cables | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.RO.D26.MTS.1235 | RO l MT Submission for Diesel Generators | 21 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D26.MTS.1225 | RO l MT Submission for Meduim-Voltage switchgear | 24 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.RO.D26.MTS.1230 | RO l MT Submission for Meduim-Voltage Transformers | 24 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.RO.D26.MTS.1240 | RO l MT Submission for Main distribution board (MDB) | 28 | 0 | 27-Aug-26 A | 02-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.1.7Special System Material Submittal |  | 57 | 0 | 11-Dec-25 A | 01-Apr-26 A | 0% | 100%
PR.RO.D33.MTS.1260 | RO l MT Submission for Brackish Water Reverse Osmosis Plant | 37 | 0 | 11-Dec-25 A | 01-Apr-26 A | 0% | 100%
PR.RO.D40.MTS.1265 | RO l MT Submission for Process scada system and intrumentation | 30 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.2RO Plant Material Approval - Long Lead |  | 241 | 20 | 08-Jan-26 A | 2026-11-26 | 12.62% | 96.99% | 85
KAFD00330-636-SBC-UP-261029.4.1.2.2.1Finishes Material Approval |  | 146 | 20 | 07-May-26 A | 2026-11-26 | 0% | 86.31% | 85
PR.RO.D07.MTA.1170 | RO l MT Approval for Aluminium cladding | 14 | 3 | 07-May-26 A | 2026-11-03 | 0% | 90% | 40
PR.RO.D05.MTA.1165 | RO l MT Approval for Structural steel | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D08.MTA.1175 | RO l MT Approval for Acoustic & Fire rated doors | 14 | 14 | 2026-11-09 | 2026-11-26 | 0% | 0% | 85
KAFD00330-636-SBC-UP-261029.4.1.2.2.2Elevator Material Approval |  | 14 | 0 | 05-Mar-26 A | 11-Mar-26 A | 0% | 100%
PR.RO.D14.MTA.1180 | RO l MT Approval for Elevators | 14 | 0 | 05-Mar-26 A | 11-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.2.3Fire Supperssion Material Approval |  | 60 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.RO.D21.MTA.1185 | RO l MT Approval for Fire Suppression equipment | 14 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.RO.D21.MTA.1190 | RO l MT Approval for Foam Water system | 14 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.RO.D21.MTA.1195 | RO l MT Approval for Clean Agent FK-5.1.12 System | 14 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.2.4Plumbing Material Approval |  | 38 | 0 | 26-Feb-26 A | 30-Sep-26 A | 0% | 100%
PR.RO.D22.MTA.1205 | RO l MT Approval for R&T Equipments & valves | 14 | 0 | 26-Feb-26 A | 30-Sep-26 A | 0% | 100%
PR.RO.D22.MTA.1200 | RO l MT Approval for Plumping equipment | 14 | 0 | 23-Apr-26 A | 01-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.2.5HVAC System Material Approval |  | 34 | 0 | 19-Feb-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MTA.1215 | RO l MT Approval for Air Handlig Units | 14 | 0 | 19-Feb-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MTA.1220 | RO l MT Approval for Split & Fan coil Units & Exhaust Fans | 14 | 0 | 19-Feb-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MTA.1210 | RO l MT Approval for HVAC equipment | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.2.6Electrical System Material Approval |  | 229 | 11 | 16-Apr-26 A | 2026-11-15 | 67.88% | 87.11% | 94
PR.RO.D26.MTA.1245 | RO l MT Approval for Lightning & Earthing | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D26.MTA.1250 | RO l MT Approval for Low voltage electrical cables | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D26.MTA.1255 | RO l MT Approval for Lighting system | 14 | 0 | 16-Apr-26 A | 08-Jul-26 A | 0% | 100%
PR.RO.D26.MTA.1225 | RO l MT Approval for Meduim-Voltage switchgear | 14 | 5 | 02-Jul-26 A | 2026-11-05 | 100% | 70% | 20
PR.RO.D26.MTA.1230 | RO l MT Approval for Meduim-Voltage Transformers | 14 | 0 | 02-Jul-26 A | 30-Sep-26 A | 100% | 100%
PR.RO.D26.MTA.1235 | RO l MT Approval for Diesel Generators | 14 | 2 | 09-Jul-26 A | 2026-11-02 | 100% | 95% | 15
PR.RO.D26.MTA.1240 | RO l MT Approval for Main distribution board (MDB) | 14 | 11 | 24-Sep-26 A | 2026-11-15 | 100% | 20% | 94
KAFD00330-636-SBC-UP-261029.4.1.2.2.7Special System Material Approval |  | 30 | 0 | 08-Jan-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D33.MTA.1260 | RO l MT Approval for Brackish Water Reverse Osmosis Plant | 14 | 0 | 08-Jan-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D40.MTA.1265 | RO l MT Approval for Process scada system and intrumentation | 14 | 0 | 15-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3RO Plant Material PO - Long Lead |  | 318 | 0 | 18-Dec-25 A | 19-Aug-26 A | 5.53% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.1Finishes Material PO |  | 75 | 0 | 14-May-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D05.MPO.1165 | RO l PO Placement for Structural steel | 20 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
PR.RO.D07.MPO.1170 | RO l PO Placement for Aluminium cladding | 16 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D08.MPO.1175 | RO l PO Placement for Acoustic & Fire rated doors | 22 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.2Elevator Material PO |  | 24 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
PR.RO.D14.MPO.1180 | RO l PO Placement for Elevators | 24 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.3Fire Supperssion Material PO |  | 317 | 0 | 04-Jun-26 A | 01-Jul-26 A | 10.08% | 100%
PR.RO.D21.MPO.1185 | RO l PO Placement for Fire Suppression equipment | 24 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D21.MPO.1195 | RO l PO Placement for Clean Agent FK-5.1.12 System | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D21.MPO.1190 | RO l PO Placement for Foam Water system | 22 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.4Plumbing Material PO |  | 60 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D22.MPO.1200 | RO l PO Placement for Plumping equipment | 30 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D22.MPO.1205 | RO l PO Placement for R&T Equipments & valves | 30 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.5HVAC System Material PO |  | 49 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1210 | RO l PO Placement for HVAC equipment | 25 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1215 | RO l PO Placement for Air Handlig Units | 25 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.RO.D23.MPO.1220 | RO l PO Placement for Split & Fan coil Units & Exhaust Fans | 25 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.6Electrical System Material PO |  | 306 | 0 | 21-May-26 A | 19-Aug-26 A | 22.34% | 100%
PR.RO.D26.MPO.1255 | RO l PO Placement for Lighting system | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.RO.D26.MPO.1235 | RO l PO Placement for Diesel Generators | 25 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D26.MPO.1240 | RO l PO Placement for Main distribution board (MDB) | 28 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.RO.D26.MPO.1250 | RO l PO Placement for Low voltage electrical cables | 18 | 0 | 11-Jun-26 A | 17-Jun-26 A | 0% | 100%
PR.RO.D26.MPO.1245 | RO l PO Placement for Lightning & Earthing | 18 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
PR.RO.D26.MPO.1225 | RO l PO Placement for Meduim-Voltage switchgear | 20 | 0 | 13-Aug-26 A | 19-Aug-26 A | 100% | 100%
PR.RO.D26.MPO.1230 | RO l PO Placement for Meduim-Voltage Transformers | 28 | 0 | 13-Aug-26 A | 19-Aug-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.3.7Special System Material PO |  | 55 | 0 | 18-Dec-25 A | 10-Jun-26 A | 0% | 100%
PR.RO.D33.MPO.1260 | RO l PO Placement for Brackish Water Reverse Osmosis Plant | 55 | 0 | 18-Dec-25 A | 07-Jan-26 A | 0% | 100%
PR.RO.D40.MPO.1265 | RO l PO Placement for Process scada system and intrumentation | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.1.2.4RO Plant Material Delivery and Fabrication - Long Lead |  | 343 | 92 | 11-Jun-26 A | 2027-01-29 | 2.74% | 20.47% | 26
KAFD00330-636-SBC-UP-261029.4.1.2.4.1Finishes Material Delivery and Fabrication |  | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 36
PR.RO.D05.MTD.1165 | RO l MT Delivery for Structural steel | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 26
PR.RO.D08.MTD.1175 | RO l MT Delivery for Acoustic & Fire rated doors | 50 | 50 | 2026-10-30 | 2026-12-18 | 0% | 0% | 56
PR.RO.D07.MTD.1170 | RO l MT Delivery for Aluminium cladding | 50 | 50 | 2026-11-01 | 2026-12-20 | 0% | 0% | 54
KAFD00330-636-SBC-UP-261029.4.1.2.4.2Elevator Material Delivery and Fabrication |  | 65 | 65 | 2026-10-30 | 2027-01-02 | 0% | 0% | 46
PR.RO.D14.MTD.1180 | RO l MT Delivery for Elevators | 65 | 65 | 2026-10-30 | 2027-01-02 | 0% | 0% | 46
KAFD00330-636-SBC-UP-261029.4.1.2.4.3Fire Supperssion Material Delivery and Fabrication |  | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 39
PR.RO.D21.MTD.1185 | RO l MT Delivery for Fire Suppression equipment | 65 | 65 | 2026-10-30 | 2027-01-02 | 0% | 0% | 13
PR.RO.D21.MTD.1190 | RO l MT Delivery for Foam Water system | 65 | 65 | 2026-10-30 | 2027-01-02 | 0% | 0% | 36
PR.RO.D21.MTD.1195 | RO l MT Delivery for Clean Agent FK-5.1.12 System | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 39
KAFD00330-636-SBC-UP-261029.4.1.2.4.4Plumbing Material Delivery and Fabrication |  | 90 | 79 | 22-Oct-26 A | 2027-01-16 | 4.4% | 6.79% | 11
PR.RO.D22.MTD.1200 | RO l MT Delivery for Plumping equipment | 90 | 79 | 22-Oct-26 A | 2027-01-16 | 7.78% | 12% | 11
PR.RO.D22.MTD.1205 | RO l MT Delivery for R&T Equipments & valves | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 19
KAFD00330-636-SBC-UP-261029.4.1.2.4.5HVAC System Material Delivery and Fabrication |  | 92 | 50 | 17-Sep-26 A | 2026-12-18 | 27.91% | 40.93% | 47
PR.RO.D23.MTD.1215 | RO l MT Delivery for Air Handlig Units | 60 | 0 | 17-Sep-26 A | 28-Oct-26 A | 70% | 100%
PR.RO.D23.MTD.1220 | RO l MT Delivery for Split & Fan coil Units & Exhaust Fans | 50 | 33 | 22-Oct-26 A | 2026-12-01 | 14% | 35% | 57
PR.RO.D23.MTD.1210 | RO l MT Delivery for HVAC equipment | 50 | 50 | 2026-10-30 | 2026-12-18 | 0% | 0% | 25
KAFD00330-636-SBC-UP-261029.4.1.2.4.6Electrical System Material Delivery and Fabrication |  | 92 | 92 | 2026-10-30 | 2027-01-29 | 0% | 0% | 26
PR.RO.D26.MTD.1230 | RO l MT Delivery for Meduim-Voltage Transformers | 90 | 90 | 2026-10-30 | 2027-01-27 | 0% | 0% | 3
PR.RO.D26.MTD.1250 | RO l MT Delivery for Low voltage electrical cables | 40 | 40 | 2026-10-30 | 2026-12-08 | 0% | 0% | 35
PR.RO.D26.MTD.1245 | RO l MT Delivery for Lightning & Earthing | 40 | 40 | 2026-10-30 | 2026-12-08 | 0% | 0% | 66
PR.RO.D26.MTD.1255 | RO l MT Delivery for Lighting system | 40 | 40 | 2026-10-30 | 2026-12-08 | 0% | 0% | 71
PR.RO.D26.MTD.1240 | RO l MT Delivery for Main distribution board (MDB) | 35 | 35 | 2026-10-30 | 2026-12-03 | 0% | 0% | 75
PR.RO.D26.MTD.1235 | RO l MT Delivery for Diesel Generators | 90 | 90 | 2026-11-01 | 2027-01-29 | 0% | 0% | 21
PR.RO.D26.MTD.1225 | RO l MT Delivery for Meduim-Voltage switchgear | 90 | 90 | 2026-11-01 | 2027-01-29 | 0% | 0% | 26
KAFD00330-636-SBC-UP-261029.4.1.2.4.7Special System Material Delivery and Fabrication |  | 301 | 60 | 11-Jun-26 A | 2026-12-28 | 0% | 37.47% | 53
PR.RO.D33.MTD.1260 | RO l MT Delivery for Brackish Water Reverse Osmosis Plant | 91 | 54 | 11-Jun-26 A | 2026-12-22 | 0% | 41.12% | -22
PR.RO.D40.MTD.1265 | RO l MT Delivery for Process scada system and intrumentation | 60 | 60 | 2026-10-30 | 2026-12-28 | 0% | 0% | 53
KAFD00330-636-SBC-UP-261029.4.2Pump-Station |  | 347 | 80 | 29-Jan-26 A | 2027-01-17 | 9.66% | 62.64% | 73
KAFD00330-636-SBC-UP-261029.4.2.1Short Lead Items |  | 325 | 20 | 29-Jan-26 A | 2026-11-18 | 9.54% | 62.65% | 133
KAFD00330-636-SBC-UP-261029.4.2.1.1Pump-Station Material Submittal - Short Lead |  | 213 | 2 | 29-Jan-26 A | 2026-11-01 | 12.95% | 99.84% | 111
KAFD00330-636-SBC-UP-261029.4.2.1.1.1Structural Material Submittal |  | 30 | 0 | 29-Jan-26 A | 18-Feb-26 A | 15.77% | 100%
PR.PS.D31.MTS.1005 | IPS l MT Submission for Reinforced piles | 16 | 0 | 29-Jan-26 A | 18-Feb-26 A | 18.75% | 100%
PR.PS.D07.MTS.1000 | IPS l MT Submission for Thermal & Moisture insulation | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.1.2Finishes Material Submittal |  | 193 | 0 | 30-Apr-26 A | 28-Oct-26 A | 49.23% | 100%
PR.PS.D04.MTS.1010 | IPS l MT Submission for Masonry | 20 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
PR.PS.D07.MTS.1020 | IPS l MT Submission for Aluminum cladding | 18 | 0 | 28-May-26 A | 28-Oct-26 A | 0% | 100%
PR.PS.D13.MTS.1035 | IPS l MT Submission for Aluminium Control booths | 16 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.PS.D05.MTS.1015 | IPS l MT Submission for Trench covers | 12 | 0 | 02-Jul-26 A | 08-Jul-26 A | 100% | 100%
PR.PS.D07.MTS.1025 | IPS l MT Submission for Terrazzo Tiles | 16 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
PR.PS.D08.MTS.1030 | IPS l MT Submission for Aluminium louvers | 18 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.1.3Plumbing Material Submittal |  | 36 | 0 | 12-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D22.MTS.1040 | IPS l MT Submission for Plumbing valves | 18 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.PS.D22.MTS.1045 | IPS l MT Submission for Domestic Water Piping GRP | 18 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.1.4Low Current Material Submittal |  | 20 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.PS.D27.MTS.1050 | IPS l MT Submission for Communication System | 20 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.1.5Security Material Submittal |  | 18 | 0 | 16-Apr-26 A | 13-May-26 A | 0% | 100%
PR.PS.D28.MTS.1065 | IPS l MT Submission for Fire alarm system | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.PS.D28.MTS.1055 | IPS l MT Submission for Access control components | 18 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.PS.D28.MTS.1060 | IPS l MT Submission for CCTV system components | 18 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.1.6External Improvement Material Submittal |  | 24 | 2 | 22-Oct-26 A | 2026-11-01 | 17.99% | 98.2% | 111
PR.PS.D32.MTS.1070 | IPS l MT Submission for concrete paving | 12 | 2 | 22-Oct-26 A | 2026-11-01 | 50% | 95% | 111
PR.PS.D32.MTS.1075 | IPS l MT Submission for Planting | 12 | 0 | 22-Oct-26 A | 28-Oct-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.2Pump-Station Material Approval - Short Lead |  | 191 | 14 | 29-Jan-26 A | 2026-11-18 | 5.82% | 86.8% | 91
KAFD00330-636-SBC-UP-261029.4.2.1.2.1Structural Material Approval |  | 26 | 0 | 29-Jan-26 A | 29-Jul-26 A | 0% | 100%
PR.PS.D31.MTA.1005 | IPS l MT Approval for Reinforced piles | 14 | 0 | 29-Jan-26 A | 18-Feb-26 A | 0% | 100%
PR.PS.D07.MTA.1000 | IPS l MT Approval for Thermal & Moisture insulation | 14 | 0 | 09-Mar-26 A | 29-Jul-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.2.2Finishes Material Approval |  | 160 | 14 | 07-May-26 A | 2026-11-18 | 19.17% | 69.93% | 91
PR.PS.D04.MTA.1010 | IPS l MT Approval for Masonry | 14 | 0 | 07-May-26 A | 29-Jul-26 A | 0% | 100%
PR.PS.D13.MTA.1035 | IPS l MT Approval for Aluminium Control booths | 14 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
PR.PS.D08.MTA.1030 | IPS l MT Approval for Aluminium louvers | 14 | 0 | 03-Sep-26 A | 09-Sep-26 A | 100% | 100%
PR.PS.D07.MTA.1025 | IPS l MT Approval for Terrazzo Tiles | 14 | 0 | 24-Sep-26 A | 30-Sep-26 A | 100% | 100%
PR.PS.D07.MTA.1020 | IPS l MT Approval for Aluminum cladding | 14 | 0 | 22-Oct-26 A | 28-Oct-26 A | 0% | 100%
PR.PS.D05.MTA.1015 | IPS l MT Approval for Trench covers | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.2.1.2.3Plumbing Material Approval |  | 29 | 0 | 12-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D22.MTA.1040 | IPS l MT Approval for Plumbing valves | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.PS.D22.MTA.1045 | IPS l MT Approval for Domestic Water Piping GRP | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.2.4Low Current Material Approval |  | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D27.MTA.1050 | IPS l MT Approval for Communication System | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.2.5Security Material Approval |  | 114 | 14 | 16-Apr-26 A | 2026-11-18 | 0% | 44.91% | 91
PR.PS.D28.MTA.1065 | IPS l MT Approval for Fire alarm system | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D28.MTA.1055 | IPS l MT Approval for Access control components | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
PR.PS.D28.MTA.1060 | IPS l MT Approval for CCTV system components | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.2.1.2.6External Improvement Material Approval |  | 29 | 14 | 24-Sep-26 A | 2026-11-18 | 35.98% | 34.18% | 91
PR.PS.D32.MTA.1070 | IPS l MT Approval for concrete paving | 14 | 2 | 24-Sep-26 A | 2026-11-02 | 100% | 95% | 103
PR.PS.D32.MTA.1075 | IPS l MT Approval for Planting | 14 | 14 | 2026-11-01 | 2026-11-18 | 0% | 0% | 91
KAFD00330-636-SBC-UP-261029.4.2.1.3Pump-Station Material PO - Short Lead |  | 185 | 0 | 07-Feb-26 A | 28-Oct-26 A | 0.15% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.1Structural Material PO |  | 30 | 0 | 07-Feb-26 A | 29-Apr-26 A | 0% | 100%
PR.PS.D31.MPO.1005 | IPS l PO Placement for Reinforced piles | 15 | 0 | 07-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D07.MPO.1000 | IPS l PO Placement for Thermal & Moisture insulation | 15 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.2Finishes Material PO |  | 184 | 0 | 28-May-26 A | 28-Oct-26 A | 1.03% | 100%
PR.PS.D04.MPO.1010 | IPS l PO Placement for Masonry | 16 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D05.MPO.1015 | IPS l PO Placement for Trench covers | 15 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D07.MPO.1020 | IPS l PO Placement for Aluminum cladding | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D08.MPO.1030 | IPS l PO Placement for Aluminium louvers | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D13.MPO.1035 | IPS l PO Placement for Aluminium Control booths | 16 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D07.MPO.1025 | IPS l PO Placement for Terrazzo Tiles | 15 | 0 | 22-Oct-26 A | 28-Oct-26 A | 40% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.3Plumbing Material PO |  | 36 | 0 | 30-Apr-26 A | 20-May-26 A | 0% | 100%
PR.PS.D22.MPO.1045 | IPS l PO Placement for Domestic Water Piping GRP | 20 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
PR.PS.D22.MPO.1040 | IPS l PO Placement for Plumbing valves | 18 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.4Low Current Material PO |  | 20 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D27.MPO.1050 | IPS l PO Placement for Communication System | 20 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.5Security Material PO |  | 18 | 0 | 28-May-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D28.MPO.1065 | IPS l PO Placement for Fire alarm system | 18 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D28.MPO.1055 | IPS l PO Placement for Access control components | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D28.MPO.1060 | IPS l PO Placement for CCTV system components | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.3.6External Improvement Material PO |  | 144 | 0 | 11-Jun-26 A | 28-Oct-26 A | 0% | 100%
PR.PS.D32.MPO.1070 | IPS l PO Placement for concrete paving | 16 | 0 | 11-Jun-26 A | 17-Jun-26 A | 0% | 100%
PR.PS.D32.MPO.1075 | IPS l PO Placement for Planting | 16 | 0 | 22-Oct-26 A | 28-Oct-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.1.4Pump-Station Material Delivery and Fabrication - Short Lead |  | 175 | 20 | 02-Apr-26 A | 2026-11-18 | 12.73% | 39.98% | 72
KAFD00330-636-SBC-UP-261029.4.2.1.4.1Structural Material Delivery and Fabrication |  | 35 | 2 | 02-Apr-26 A | 2026-10-31 | 0% | 99.21% | 19
PR.PS.D31.MTD.1005 | IPS l MT Delivery for Reinforced piles | 20 | 0 | 02-Apr-26 A | 06-May-26 A | 0% | 100%
PR.PS.D07.MTD.1000 | IPS l MT Delivery for Thermal & Moisture insulation | 18 | 2 | 30-Apr-26 A | 2026-10-31 | 0% | 95% | 19
KAFD00330-636-SBC-UP-261029.4.2.1.4.2Finishes Material Delivery and Fabrication |  | 85 | 18 | 27-Aug-26 A | 2026-11-16 | 26.98% | 29.56% | 74
PR.PS.D04.MTD.1010 | IPS l MT Delivery for Masonry | 16 | 0 | 27-Aug-26 A | 22-Sep-26 A | 100% | 100%
PR.PS.D08.MTD.1030 | IPS l MT Delivery for Aluminium louvers | 20 | 0 | 03-Sep-26 A | 09-Sep-26 A | 100% | 100%
PR.PS.D13.MTD.1035 | IPS l MT Delivery for Aluminium Control booths | 15 | 0 | 24-Sep-26 A | 30-Sep-26 A | 100% | 100%
PR.PS.D07.MTD.1025 | IPS l MT Delivery for Terrazzo Tiles | 18 | 0 | 15-Oct-26 A | 21-Oct-26 A | 0% | 100%
PR.PS.D07.MTD.1020 | IPS l MT Delivery for Aluminum cladding | 18 | 18 | 2026-10-30 | 2026-11-16 | 0% | 0% | 9
PR.PS.D05.MTD.1015 | IPS l MT Delivery for Trench covers | 18 | 18 | 2026-10-30 | 2026-11-16 | 0% | 0% | 74
KAFD00330-636-SBC-UP-261029.4.2.1.4.3Plumbing Material Delivery and Fabrication |  | 112 | 20 | 21-May-26 A | 2026-11-18 | 0% | 19.06% | 42
PR.PS.D22.MTD.1045 | IPS l MT Delivery for Domestic Water Piping GRP | 16 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.PS.D22.MTD.1040 | IPS l MT Delivery for Plumbing valves | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 42
KAFD00330-636-SBC-UP-261029.4.2.1.4.4Low Current Material Delivery and Fabrication |  | 20 | 19 | 22-Oct-26 A | 2026-11-17 | 35% | 5% | 42
PR.PS.D27.MTD.1050 | IPS l MT Delivery for Communication System | 20 | 19 | 22-Oct-26 A | 2026-11-17 | 35% | 5% | 42
KAFD00330-636-SBC-UP-261029.4.2.1.4.5Security Material Delivery and Fabrication |  | 41 | 20 | 08-Oct-26 A | 2026-11-18 | 44.91% | 35.93% | 54
PR.PS.D28.MTD.1065 | IPS l MT Delivery for Fire alarm system | 20 | 4 | 08-Oct-26 A | 2026-11-02 | 100% | 80% | 22
PR.PS.D28.MTD.1055 | IPS l MT Delivery for Access control components | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 4
PR.PS.D28.MTD.1060 | IPS l MT Delivery for CCTV system components | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 54
KAFD00330-636-SBC-UP-261029.4.2.1.4.6External Improvement Material Delivery and Fabrication |  | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 68
PR.PS.D32.MTD.1070 | IPS l MT Delivery for concrete paving | 15 | 15 | 2026-10-30 | 2026-11-13 | 0% | 0% | 50
PR.PS.D32.MTD.1075 | IPS l MT Delivery for Planting | 20 | 20 | 2026-10-30 | 2026-11-18 | 0% | 0% | 68
KAFD00330-636-SBC-UP-261029.4.2.2Long Lead Item |  | 347 | 80 | 26-Feb-26 A | 2027-01-17 | 9.7% | 62.63% | 73
KAFD00330-636-SBC-UP-261029.4.2.2.1Pump-Station Material Submittal - Long Lead |  | 252 | 0 | 26-Feb-26 A | 15-Jul-26 A | 12.91% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.1.1Fire Supperssion Material Submittal |  | 20 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D21.MTS.1080 | IPS l MT Submission for Clean Agent FK-5.1.12 cylinders | 20 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.1.2Plumbing Material Submittal |  | 26 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D22.MTS.1085 | IPS l MT Submission for Submersible pumps | 26 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.1.3HVAC System Material Submittal |  | 24 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.PS.D23.MTS.1090 | IPS l MT Submission for HVAC System | 24 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.1.4Electrical System Material Submittal |  | 232 | 0 | 16-Apr-26 A | 15-Jul-26 A | 45.54% | 100%
PR.PS.D26.MTS.1100 | IPS l MT Submission for Low voltage electrical cables | 18 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.PS.D26.MTS.1105 | IPS l MT Submission for Lighting fixtures | 16 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.PS.D26.MTS.1095 | IPS l MT Submission for Panel boards | 20 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.1.5Special System Material Submittal |  | 20 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.PS.D40.MTS.1110 | IPS l MT Submission for SCADA | 20 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.2Pump-Station Material Approval - Long Lead |  | 169 | 11 | 26-Feb-26 A | 2026-11-16 | 12.91% | 87.35% | 94
KAFD00330-636-SBC-UP-261029.4.2.2.2.1Fire Supperssion Material Approval |  | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
PR.PS.D21.MTA.1080 | IPS l MT Approval for Clean Agent FK-5.1.12 cylinders | 14 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.2.2Plumbing Material Approval |  | 14 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
PR.PS.D22.MTA.1085 | IPS l MT Approval for Submersible pumps | 14 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.2.3HVAC System Material Approval |  | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D23.MTA.1090 | IPS l MT Approval for HVAC System | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.2.4Electrical System Material Approval |  | 152 | 11 | 16-Apr-26 A | 2026-11-16 | 45.54% | 55.37% | 94
PR.PS.D26.MTA.1100 | IPS l MT Approval for Low voltage electrical cables | 14 | 0 | 16-Apr-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D26.MTA.1105 | IPS l MT Approval for Lighting fixtures | 14 | 3 | 07-May-26 A | 2026-11-03 | 0% | 80% | 6
PR.PS.D26.MTA.1095 | IPS l MT Approval for Panel boards | 14 | 11 | 24-Sep-26 A | 2026-11-16 | 100% | 20% | 94
KAFD00330-636-SBC-UP-261029.4.2.2.2.5Special System Material Approval |  | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.PS.D40.MTA.1110 | IPS l MT Approval for SCADA | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3Pump-Station Material PO - Long Lead |  | 107 | 0 | 14-May-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3.1Fire Supperssion Material PO |  | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D21.MPO.1080 | IPS l PO Placement for Clean Agent FK-5.1.12 cylinders | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3.2Plumbing Material PO |  | 16 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
PR.PS.D22.MPO.1085 | IPS l PO Placement for Submersible pumps | 16 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3.3HVAC System Material PO |  | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D23.MPO.1090 | IPS l PO Placement for HVAC System | 20 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3.4Electrical System Material PO |  | 50 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D26.MPO.1095 | IPS l PO Placement for Panel boards | 18 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D26.MPO.1100 | IPS l PO Placement for Low voltage electrical cables | 15 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
PR.PS.D26.MPO.1105 | IPS l PO Placement for Lighting fixtures | 15 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.3.5Special System Material PO |  | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.PS.D40.MPO.1110 | IPS l PO Placement for SCADA | 20 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.2.2.4Pump-Station Material Delivery and Fabrication - Long Lead |  | 129 | 80 | 10-Sep-26 A | 2027-01-17 | 14.48% | 15.53% | 0
KAFD00330-636-SBC-UP-261029.4.2.2.4.1Fire Supperssion Material Delivery and Fabrication |  | 50 | 20 | 10-Sep-26 A | 2026-11-18 | 98% | 60% | 52
PR.PS.D21.MTD.1080 | IPS l MT Delivery for Clean Agent FK-5.1.12 cylinders | 50 | 20 | 10-Sep-26 A | 2026-11-18 | 98% | 60% | 52
KAFD00330-636-SBC-UP-261029.4.2.2.4.2Plumbing Material Delivery and Fabrication |  | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 9
PR.PS.D22.MTD.1085 | IPS l MT Delivery for Submersible pumps | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | 9
KAFD00330-636-SBC-UP-261029.4.2.2.4.3HVAC System Material Delivery and Fabrication |  | 70 | 7 | 01-Oct-26 A | 2026-11-05 | 40% | 90% | 69
PR.PS.D23.MTD.1090 | IPS l MT Delivery for HVAC System | 70 | 7 | 01-Oct-26 A | 2026-11-05 | 40% | 90% | 69
KAFD00330-636-SBC-UP-261029.4.2.2.4.4Electrical System Material Delivery and Fabrication |  | 72 | 72 | 2026-10-30 | 2027-01-09 | 0% | 0% | 8
PR.PS.D26.MTD.1095 | IPS l MT Delivery for Panel boards | 50 | 50 | 2026-10-30 | 2026-12-18 | 0% | 0% | 3
PR.PS.D26.MTD.1100 | IPS l MT Delivery for Low voltage electrical cables | 48 | 48 | 2026-10-30 | 2026-12-16 | 0% | 0% | 30
PR.PS.D26.MTD.1105 | IPS l MT Delivery for Lighting fixtures | 70 | 70 | 2026-11-01 | 2027-01-09 | 0% | 0% | 8
KAFD00330-636-SBC-UP-261029.4.2.2.4.5Special System Material Delivery and Fabrication |  | 80 | 80 | 2026-10-30 | 2027-01-17 | 0% | 0% | -1
PR.PS.D40.MTD.1110 | IPS l MT Delivery for SCADA | 80 | 80 | 2026-10-30 | 2027-01-17 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.4.3Collection System |  | 275 | 70 | 27-Nov-25 A | 2027-01-07 | 0.09% | 79.93% | 13
KAFD00330-636-SBC-UP-261029.4.3.1Short Lead Items |  | 111 | 0 | 18-Dec-25 A | 20-May-26 A | 6.8% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.1Collection System Material Submittal - Short Lead |  | 25 | 0 | 18-Dec-25 A | 24-Dec-25 A | 68% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.1.1Plumbing Material Submittal |  | 25 | 0 | 18-Dec-25 A | 24-Dec-25 A | 68% | 100%
PR.CL.D33.MTS.1000 | CLS l MT Submission for Precast Manholes | 25 | 0 | 18-Dec-25 A | 24-Dec-25 A | 68% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.2Collection System Material Approval - Short Lead |  | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.2.1Plumbing Material Approval |  | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
PR.CL.D33.MTA.1000 | CLS l MT Approval for Precast Manholes | 14 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.3Collection System Material PO - Short Lead |  | 20 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.3.1Plumbing Material PO |  | 20 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.CL.D33.MPO.1000 | CLS l PO Placement for Precast Manholes | 20 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.4Collection System Material Delivery and Fabrication - Short Lead |  | 40 | 0 | 02-Apr-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.1.4.1Plumbing Material Delivery & Fabrication |  | 40 | 0 | 02-Apr-26 A | 20-May-26 A | 0% | 100%
PR.CL.D33.MTD.1000 | CLS l MT Delivery for Precast Manholes | 40 | 0 | 02-Apr-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2Long Lead Item |  | 256 | 70 | 27-Nov-25 A | 2027-01-07 | 0% | 79.67% | 13
KAFD00330-636-SBC-UP-261029.4.3.2.1Collection System Material Submittal - Long Lead |  | 140 | 0 | 27-Nov-25 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.1.1Plumbing Material Submittal |  | 60 | 0 | 27-Nov-25 A | 22-Apr-26 A | 0% | 100%
PR.CL.D33.MTS.1015 | CLS l MT Submission for HDPE pipes | 20 | 0 | 27-Nov-25 A | 03-Dec-25 A | 0% | 100%
PR.CL.D33.MTS.1010 | CLS l MT Submission for GRP pipes | 20 | 0 | 18-Dec-25 A | 24-Dec-25 A | 0% | 100%
PR.CL.D33.MTS.1020 | CLS l MT Submission for General Duty valves | 20 | 0 | 01-Jan-26 A | 07-Jan-26 A | 0% | 100%
PR.CL.D22.MTS.1005 | CLS l MT Submission for Submersible pumps | 20 | 0 | 16-Apr-26 A | 22-Apr-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.1.2Electrical System Material Submittal |  | 80 | 0 | 02-Apr-26 A | 13-May-26 A | 0% | 100%
PR.CL.D33.MTS.1035 | CLS l MT Submission for Fiber optic | 25 | 0 | 02-Apr-26 A | 22-Apr-26 A | 0% | 100%
PR.CL.D33.MTS.1025 | CLS l MT Submission for Remote terminal unit (RTU) | 30 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
PR.CL.D33.MTS.1030 | CLS l MT Submission for Fiber Optic Cables | 25 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.2Collection System Material Approval - Long Lead |  | 113 | 0 | 11-Dec-25 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.2.1Plumbing Material Approval |  | 47 | 0 | 11-Dec-25 A | 20-May-26 A | 0% | 100%
PR.CL.D33.MTA.1015 | CLS l MT Approval for HDPE pipes | 14 | 0 | 11-Dec-25 A | 17-Dec-25 A | 0% | 100%
PR.CL.D33.MTA.1010 | CLS l MT Approval for GRP pipes | 14 | 0 | 18-Dec-25 A | 24-Dec-25 A | 0% | 100%
PR.CL.D22.MTA.1005 | CLS l MT Approval for Submersible pumps | 14 | 0 | 30-Apr-26 A | 06-May-26 A | 0% | 100%
PR.CL.D33.MTA.1020 | CLS l MT Approval for General Duty valves | 14 | 0 | 07-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.2.2Electrical System Material Approval |  | 59 | 0 | 05-Mar-26 A | 03-Jun-26 A | 0% | 100%
PR.CL.D33.MTA.1035 | CLS l MT Approval for Fiber optic | 14 | 0 | 05-Mar-26 A | 11-Mar-26 A | 0% | 100%
PR.CL.D33.MTA.1025 | CLS l MT Approval for Remote terminal unit (RTU) | 14 | 0 | 07-May-26 A | 03-Jun-26 A | 0% | 100%
PR.CL.D33.MTA.1030 | CLS l MT Approval for Fiber Optic Cables | 14 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.3Collection System Material PO - Long Lead |  | 154 | 0 | 19-Feb-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.3.1Plumbing Material PO |  | 59 | 0 | 19-Feb-26 A | 20-May-26 A | 0% | 100%
PR.CL.D33.MPO.1010 | CLS l PO Placement for GRP pipes | 20 | 0 | 19-Feb-26 A | 25-Feb-26 A | 0% | 100%
PR.CL.D33.MPO.1015 | CLS l PO Placement for HDPE pipes | 20 | 0 | 19-Feb-26 A | 11-Mar-26 A | 0% | 100%
PR.CL.D22.MPO.1005 | CLS l PO Placement for Submersible pumps | 20 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
PR.CL.D33.MPO.1020 | CLS l PO Placement for General Duty valves | 10 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.3.2Electrical System Material PO |  | 89 | 0 | 12-Mar-26 A | 27-May-26 A | 0% | 100%
PR.CL.D33.MPO.1035 | CLS l PO Placement for Fiber optic | 30 | 0 | 12-Mar-26 A | 25-Mar-26 A | 0% | 100%
PR.CL.D33.MPO.1025 | CLS l PO Placement for Remote terminal unit (RTU) | 35 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
PR.CL.D33.MPO.1030 | CLS l PO Placement for Fiber Optic Cables | 35 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.4.3.2.4Collection System Material Delivery and Fabrication - Long Lead |  | 256 | 70 | 05-Dec-25 A | 2027-01-07 | 0% | 56.66% | 13
KAFD00330-636-SBC-UP-261029.4.3.2.4.1Plumbing Material Delivery & Fabrication |  | 150 | 70 | 05-Dec-25 A | 2027-01-07 | 0% | 67.22% | -6
PR.CL.D33.MTD.1015 | CLS l MT Delivery for HDPE pipes | 40 | 0 | 05-Dec-25 A | 09-Sep-26 A | 0% | 100%
PR.CL.D33.MTD.1010 | CLS l MT Delivery for GRP pipes | 50 | 2 | 12-Mar-26 A | 2026-10-31 | 0% | 97% | 53
PR.CL.D22.MTD.1005 | CLS l MT Delivery for Submersible pumps | 70 | 70 | 2026-10-30 | 2027-01-07 | 0% | 0% | -55
PR.CL.D33.MTD.1020 | CLS l MT Delivery for General Duty valves | 30 | 30 | 2026-10-30 | 2026-11-28 | 0% | 0% | 34
KAFD00330-636-SBC-UP-261029.4.3.2.4.2Electrical System Material Delivery & Fabrication |  | 256 | 60 | 05-Dec-25 A | 2026-12-28 | 0% | 32.92% | 23
PR.CL.D33.MTD.1035 | CLS l MT Delivery for Fiber optic | 40 | 24 | 05-Dec-25 A | 2026-11-22 | 0% | 40% | 48
PR.CL.D33.MTD.1030 | CLS l MT Delivery for Fiber Optic Cables | 50 | 20 | 21-May-26 A | 2026-11-18 | 0% | 60% | 35
PR.CL.D33.MTD.1025 | CLS l MT Delivery for Remote terminal unit (RTU) | 60 | 60 | 2026-10-30 | 2026-12-28 | 0% | 0% | 23
KAFD00330-636-SBC-UP-261029.5Construction |  | 387 | 207 | 22-Oct-25 A | 2027-07-06 | 32.96% | 34.86% | -95
KAFD00330-636-SBC-UP-261029.5.1RO Plant |  | 294 | 207 | 22-Oct-25 A | 2027-07-06 | 35.69% | 34.82% | -95
KAFD00330-636-SBC-UP-261029.5.1.1Under Ground Floor |  | 232 | 149 | 05-Nov-25 A | 2027-04-26 | 56.56% | 55.18% | -45
KAFD00330-636-SBC-UP-261029.5.1.1.1Earthwork |  | 154 | 30 | 05-Nov-25 A | 2027-01-30 | 73.1% | 92.04% | 25
CO.RO.D31.0UG.1020 | RO l Excavation Works pre-piles part1 (Segment1,2,5) UG | 12 | 0 | 05-Nov-25 A | 10-Dec-25 A | 100% | 100%
CO.RO.D31.0UG.1560 | RO l Preparation and utilities relocation UG | 25 | 0 | 12-Nov-25 A | 26-Nov-25 A | 100% | 100%
CO.RO.D31.0UG.1025 | RO l Excavation Works pre-piles part2 (Segment3,4,6) UG | 10 | 0 | 27-Nov-25 A | 10-Jun-26 A | 100% | 100%
CO.RO.D31.0UG.1030 | RO l Concrete Piles works part 1 UG | 24 | 0 | 07-Dec-25 A | 18-Feb-26 A | 100% | 100%
CO.RO.D31.0UG.1035 | RO l Concrete Piles works part 2 UG | 21 | 0 | 06-Jan-26 A | 06-May-26 A | 100% | 100%
CO.RO.D31.0UG.1010 | RO l Temporary prestressed anchors works part 1 UG | 11 | 0 | 18-Jan-26 A | 17-Jun-26 A | 100% | 100%
CO.RO.D31.0UG.1040 | RO l Excavation Works post-piles part1 (Segment1,2,5) UG | 35 | 0 | 31-Jan-26 A | 01-Jul-26 A | 8.57% | 100%
CO.RO.D31.0UG.1015 | RO l Temporary prestressed anchors works part 2 UG | 11 | 0 | 19-Feb-26 A | 25-Feb-26 A | 36.36% | 100%
CO.RO.D31.0UG.1045 | RO l Excavation Works post-piles part2 (Segment3,4,6) UG | 38 | 0 | 14-Mar-26 A | 08-Jul-26 A | 0% | 100%
CO.RO.D31.0UG.1005 | RO l Under Foundation Probe Holes works UG | 3 | 0 | 23-Apr-26 A | 03-Jun-26 A | 0% | 100%
CO.RO.D31.0UG.1000 | RO l Groundwater Control System works UG | 30 | 30 | 2026-12-27 | 2027-01-30 | 0% | 0% | 25
KAFD00330-636-SBC-UP-261029.5.1.1.2Concrete Work |  | 171 | 88 | 23-Jul-26 A | 2027-02-09 | 54.84% | 48.19% | 4
CO.RO.D03.0UG.1060 | RO l Shuttering for Raft Foundation part 1 UG | 6 | 2 | 23-Jul-26 A | 2026-11-01 | 100% | 96% | -95
CO.RO.D03.0UG.1055 | RO l Plain Concrete works for foundation UG | 6 | 0 | 28-Jul-26 A | 29-Jul-26 A | 100% | 100%
CO.RO.D03.0UG.1065 | RO l Steel fixing & Pouring for Raft Foundation part 1 UG | 7 | 3 | 30-Jul-26 A | 2026-11-02 | 100% | 96% | -95
CO.RO.D03.0UG.1070 | RO l Shuttering for Raft Foundation part 2 UG | 6 | 0 | 13-Aug-26 A | 16-Sep-26 A | 100% | 100%
CO.RO.D03.0UG.1075 | RO l Steel fixing & Pouring for Raft Foundation part 2 UG | 7 | 0 | 13-Aug-26 A | 16-Sep-26 A | 100% | 100%
CO.RO.D03.0UG.1080 | RO l Shuttering & Pouring for Tank walls part 1 UG | 10 | 0 | 27-Aug-26 A | 07-Oct-26 A | 100% | 100%
CO.RO.D03.0UG.1085 | RO l Steel fixing for Tank walls part 1 UG | 8 | 0 | 27-Aug-26 A | 30-Sep-26 A | 100% | 100%
CO.RO.D03.0UG.1090 | RO l Shuttering & Pouring for Tank walls part 2 UG | 10 | 12 | 01-Oct-26 A | 2026-11-14 | 100% | 50% | -95
CO.RO.D03.0UG.1095 | RO l Steel fixing for Tank walls part 2 UG | 8 | 4 | 01-Oct-26 A | 2026-11-04 | 100% | 85% | -95
CO.RO.D03.0UG.1105 | RO l Steel fixing for Tank walls part 3 UG | 8 | 8 | 2026-11-15 | 2026-11-23 | 0% | 0% | -95
CO.RO.D03.0UG.1100 | RO l Shuttering & Pouring for Tank walls part 3 UG | 10 | 10 | 2026-11-24 | 2026-12-05 | 0% | 0% | -95
CO.RO.D03.0UG.1115 | RO l Steel fixing for Tank walls part 4 UG | 8 | 8 | 2026-12-06 | 2026-12-14 | 0% | 0% | -95
CO.RO.D03.0UG.1110 | RO l Shuttering & Pouring for Tank walls part 4 UG | 10 | 10 | 2026-12-15 | 2026-12-26 | 0% | 0% | -95
CO.RO.D03.0UG.1120 | RO l Shuttering for Tank slab part 1 UG | 9 | 9 | 2026-12-27 | 2027-01-05 | 0% | 0% | -95
CO.RO.D03.0UG.1145 | RO l Tank walls Deshuttering works UG | 14 | 14 | 2026-12-27 | 2027-01-11 | 0% | 0% | 29
CO.RO.D03.0UG.1130 | RO l Shuttering for Tank slab part 2 UG | 9 | 9 | 2027-01-06 | 2027-01-16 | 0% | 0% | -95
CO.RO.D03.0UG.1125 | RO l Steel fixing & Pouring Tank slab part 1 UG | 7 | 7 | 2027-01-06 | 2027-01-13 | 0% | 0% | -93
CO.RO.D03.0UG.1135 | RO l Steel fixing & Pouring Tank slab part 2 UG | 7 | 7 | 2027-01-17 | 2027-01-24 | 0% | 0% | -95
CO.RO.D03.0UG.1155 | RO l Tank slab Deshuttering works UG | 14 | 14 | 2027-01-25 | 2027-02-09 | 0% | 0% | 4
KAFD00330-636-SBC-UP-261029.5.1.1.3Metal Works |  | 5 | 5 | 2027-04-21 | 2027-04-26 | 0% | 0% | -47
CO.RO.D05.0UG.1185 | RO l Install of Metal Ladders UG | 5 | 5 | 2027-04-21 | 2027-04-26 | 0% | 0% | -47
KAFD00330-636-SBC-UP-261029.5.1.1.4Wood & Plastics |  | 4 | 4 | 2027-04-21 | 2027-04-25 | 0% | 0% | -44
CO.RO.D06.0UG.1195 | RO l Install of GRP ladder UG | 4 | 4 | 2027-04-21 | 2027-04-25 | 0% | 0% | -44
KAFD00330-636-SBC-UP-261029.5.1.1.5Thermal & Moisture Protection |  | 176 | 111 | 23-Jul-26 A | 2027-03-14 | 36.14% | 35.42% | -8
CO.RO.D07.0UG.1215 | RO l Install of Bottom of raft HDPE sheets UG | 6 | 2 | 23-Jul-26 A | 2026-11-02 | 100% | 98% | -95
CO.RO.D07.0UG.1220 | RO l Water Tank Membrene sheets waterproofing UG | 12 | 12 | 2027-01-12 | 2027-01-25 | 0% | 0% | 29
CO.RO.D07.0UG.1225 | RO l Water Tank Chemical waterproof coating UG | 12 | 12 | 2027-02-10 | 2027-02-24 | 0% | 0% | 4
CO.RO.D07.0UG.1210 | RO l Water Tank Slab Bituminous Coating UG | 4 | 4 | 2027-03-07 | 2027-03-14 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.1.6Plumbing |  | 32 | 32 | 2027-03-15 | 2027-04-20 | 0% | 0% | -40
CO.RO.D22.0UG.1440 | RO l Install of Sanitary Pipes UG | 4 | 4 | 2027-03-15 | 2027-03-18 | 0% | 0% | -95
CO.RO.D22.0UG.1445 | RO l Install of Domestic water pipes (R&T water pump station) UG | 5 | 5 | 2027-03-20 | 2027-03-24 | 0% | 0% | -40
CO.RO.D22.0UG.1450 | RO l Install of General Duty plumbing valves (R&T water pump station) UG | 6 | 6 | 2027-03-25 | 2027-03-31 | 0% | 0% | -40
CO.RO.D22.0UG.1460 | RO l Install of Domestic water filter (R&T water pump station) UG | 6 | 6 | 2027-04-01 | 2027-04-07 | 0% | 0% | -40
CO.RO.D22.0UG.1455 | RO l Install of water pumps (R&T water pump station) UG | 11 | 11 | 2027-04-08 | 2027-04-20 | 0% | 0% | -40
KAFD00330-636-SBC-UP-261029.5.1.1.7Electrical |  | 8 | 8 | 2027-03-15 | 2027-03-23 | 0% | 0% | -47
CO.RO.D26.0UG.1605 | RO l Install of Underground Cable ducts, manholes and trenches UG | 8 | 8 | 2027-03-15 | 2027-03-23 | 0% | 0% | -47
KAFD00330-636-SBC-UP-261029.5.1.2Ground Floor |  | 129 | 129 | 2027-01-25 | 2027-07-01 | 0% | 0% | -91
KAFD00330-636-SBC-UP-261029.5.1.2.1Concrete Work |  | 82 | 82 | 2027-01-25 | 2027-05-04 | 0% | 0% | -52
CO.RO.D03.0GF.1145 | RO l Steel fixing for Columns GF | 4 | 4 | 2027-01-25 | 2027-01-28 | 0% | 0% | -95
CO.RO.D03.0GF.1140 | RO l Shuttering & Pouring for Columns GF | 4 | 4 | 2027-01-30 | 2027-02-02 | 0% | 0% | -95
CO.RO.D03.0GF.1120 | RO l Shuttering for Slab GF | 7 | 7 | 2027-02-03 | 2027-02-10 | 0% | 0% | -95
CO.RO.D03.0GF.1125 | RO l Steel fixing & Pouring for Slab GF | 7 | 7 | 2027-02-11 | 2027-02-18 | 0% | 0% | -95
CO.RO.D03.0GF.1175 | RO l Deshuttering works for Slab GF | 12 | 12 | 2027-02-20 | 2027-03-06 | 0% | 0% | -95
CO.RO.D03.0GF.1150 | RO l Concete works for Slab on grade GF | 6 | 6 | 2027-03-20 | 2027-03-25 | 0% | 0% | -95
CO.RO.D03.0GF.1160 | RO l Concete works for Roof screed GF | 7 | 7 | 2027-04-10 | 2027-04-17 | 0% | 0% | -77
CO.RO.D03.0GF.1165 | RO l Concete works for Floor screed GF | 7 | 7 | 2027-04-13 | 2027-04-20 | 0% | 0% | -78
CO.RO.D03.0GF.1155 | RO l Install of Precast Shaft cover GF | 12 | 12 | 2027-04-21 | 2027-05-04 | 0% | 0% | -52
KAFD00330-636-SBC-UP-261029.5.1.2.2Masonry Works |  | 9 | 9 | 2027-03-27 | 2027-04-05 | 0% | 0% | -95
CO.RO.D04.0GF.1170 | RO l Masonry works GF | 9 | 9 | 2027-03-27 | 2027-04-05 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.2.3Metal Works |  | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -93
CO.RO.D05.0GF.1185 | RO l Install of Metal Ladders GF | 5 | 5 | 2027-06-10 | 2027-06-15 | 0% | 0% | -95
CO.RO.D05.0GF.1175 | RO l Install of Steel covers GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -93
CO.RO.D05.0GF.1180 | RO l Install of Handrail GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -93
KAFD00330-636-SBC-UP-261029.5.1.2.4Thermal And Moisture Protection |  | 50 | 50 | 2027-04-06 | 2027-06-06 | 0% | 0% | -77
CO.RO.D07.0GF.1570 | RO l Wet areas insulation works GF | 6 | 6 | 2027-04-06 | 2027-04-12 | 0% | 0% | -78
CO.RO.D07.0GF.1230 | RO l Rockwool insulation works GF | 6 | 6 | 2027-04-06 | 2027-04-12 | 0% | 0% | -33
CO.RO.D07.0GF.1235 | RO l Install of Concrete tiles GF | 6 | 6 | 2027-05-31 | 2027-06-06 | 0% | 0% | -77
KAFD00330-636-SBC-UP-261029.5.1.2.5Openings |  | 12 | 12 | 2027-06-10 | 2027-06-23 | 0% | 0% | -94
CO.RO.D08.0GF.1250 | RO l Install of Steel doors GF | 8 | 8 | 2027-06-10 | 2027-06-19 | 0% | 0% | -95
CO.RO.D08.0GF.1240 | RO l Install of Acoustic & Fire rated doors GF | 12 | 12 | 2027-06-10 | 2027-06-23 | 0% | 0% | -94
CO.RO.D08.0GF.1255 | RO l Install of Aluminum windows & Louvers GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -93
CO.RO.D08.0GF.1245 | RO l Install of Roller shutter doors GF | 8 | 8 | 2027-06-10 | 2027-06-19 | 0% | 0% | -90
KAFD00330-636-SBC-UP-261029.5.1.2.6Finishes |  | 53 | 53 | 2027-04-06 | 2027-06-09 | 0% | 0% | -76
CO.RO.D09.0GF.1310 | RO l Internal Plaster works GF | 10 | 10 | 2027-04-06 | 2027-04-17 | 0% | 0% | -95
CO.RO.D09.0GF.1300 | RO l Gypsum & cement board walls works GF | 8 | 8 | 2027-04-06 | 2027-04-14 | 0% | 0% | -58
CO.RO.D09.0GF.1280 | RO l Floor Ceramic tiles & Stones works GF | 6 | 6 | 2027-04-18 | 2027-04-24 | 0% | 0% | -66
CO.RO.D09.0GF.1305 | RO l Floor epoxy painting GF | 6 | 6 | 2027-04-21 | 2027-04-27 | 0% | 0% | -64
CO.RO.D09.0GF.1295 | RO l Wall epoxy painting GF | 5 | 5 | 2027-04-28 | 2027-05-03 | 0% | 0% | -47
CO.RO.D09.0GF.1275 | RO l Gypsum board ceiling works GF | 8 | 8 | 2027-05-23 | 2027-05-31 | 0% | 0% | -95
CO.RO.D09.0GF.1285 | RO l Wall Ceramic tiles works GF | 7 | 7 | 2027-05-23 | 2027-05-30 | 0% | 0% | -84
CO.RO.D09.0GF.1290 | RO l Wall & Ceiling painting works GF | 8 | 8 | 2027-06-01 | 2027-06-09 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.2.7Specialities |  | 15 | 15 | 2027-05-31 | 2027-06-16 | 0% | 0% | -82
CO.RO.D10.0GF.1340 | RO l Install of Toilet Accessories GF | 4 | 4 | 2027-05-31 | 2027-06-03 | 0% | 0% | -71
CO.RO.D10.0GF.1330 | RO l Install of Fire Extinguisher GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -82
CO.RO.D10.0GF.1335 | RO l Corner guards GF | 3 | 3 | 2027-06-10 | 2027-06-13 | 0% | 0% | -79
KAFD00330-636-SBC-UP-261029.5.1.2.8Special Construction |  | 6 | 6 | 2027-06-17 | 2027-06-23 | 0% | 0% | -88
CO.RO.D13.0GF.1350 | RO l Install of Aluminium Control booths GF | 6 | 6 | 2027-06-17 | 2027-06-23 | 0% | 0% | -88
KAFD00330-636-SBC-UP-261029.5.1.2.9Fire Supression |  | 41 | 41 | 2027-04-18 | 2027-06-07 | 0% | 0% | -78
CO.RO.D21.0GF.1415 | RO l Install of Fire Suppression standpipes GF | 10 | 10 | 2027-04-18 | 2027-04-28 | 0% | 0% | -95
CO.RO.D21.0GF.1390 | RO l Install of Vibration and Seismic controls GF | 10 | 10 | 2027-04-21 | 2027-05-02 | 0% | 0% | -78
CO.RO.D21.0GF.1365 | RO l Install of Fire Suppression valves GF | 10 | 10 | 2027-04-29 | 2027-05-10 | 0% | 0% | -88
CO.RO.D21.0GF.1400 | RO l Install of Cold Water Pipes GF | 12 | 12 | 2027-04-29 | 2027-05-12 | 0% | 0% | -59
CO.RO.D21.0GF.1370 | RO l Install of Fire Hose Cabinets GF | 7 | 7 | 2027-04-29 | 2027-05-06 | 0% | 0% | -54
CO.RO.D21.0GF.1360 | RO l Install of Siamese Connection GF | 6 | 6 | 2027-04-29 | 2027-05-05 | 0% | 0% | -53
CO.RO.D21.0GF.1425 | RO l Install of Electrical Fire Pump GF | 10 | 10 | 2027-05-03 | 2027-05-13 | 0% | 0% | -78
CO.RO.D21.0GF.1380 | RO l Install of Foam Bladder Tank GF | 4 | 4 | 2027-05-03 | 2027-05-06 | 0% | 0% | -68
CO.RO.D21.0GF.1405 | RO l Install of Recirculating Pumps GF | 14 | 14 | 2027-05-03 | 2027-05-22 | 0% | 0% | -64
CO.RO.D21.0GF.1375 | RO l Install of Foam Water fire extinguishing system GF | 14 | 14 | 2027-05-08 | 2027-05-26 | 0% | 0% | -68
CO.RO.D21.0GF.1385 | RO l Install of Clean Agent FK-5.1.12 System GF | 11 | 11 | 2027-05-11 | 2027-05-26 | 0% | 0% | -68
CO.RO.D21.0GF.1430 | RO l Install of Diesel Fire Pump GF | 10 | 10 | 2027-05-15 | 2027-05-29 | 0% | 0% | -78
CO.RO.D21.0GF.1435 | RO l Install of Diesel Fire Pump Pipes & Valves GF | 8 | 8 | 2027-05-30 | 2027-06-07 | 0% | 0% | -78
CO.RO.D21.0GF.1395 | RO l Install of Pressure Maintenance Fire Pump GF | 8 | 8 | 2027-05-30 | 2027-06-07 | 0% | 0% | -78
CO.RO.D21.0GF.1410 | RO l Install of Diesel Fire Pump fuel tank GF | 5 | 5 | 2027-05-30 | 2027-06-03 | 0% | 0% | -75
CO.RO.D21.0GF.1420 | RO l Install of Fire Suppersion Sprinkls GF | 6 | 6 | 2027-06-01 | 2027-06-07 | 0% | 0% | -78
KAFD00330-636-SBC-UP-261029.5.1.2.10Plumbing |  | 55 | 55 | 2027-04-06 | 2027-06-12 | 0% | 0% | -82
CO.RO.D22.0GF.1440 | RO l Install of Sanitary Pipes GF | 10 | 10 | 2027-04-06 | 2027-04-17 | 0% | 0% | -84
CO.RO.D22.0GF.1490 | RO l Install of Domestic water pipes GF | 10 | 10 | 2027-04-18 | 2027-04-28 | 0% | 0% | -84
CO.RO.D22.0GF.1480 | RO l Install of Sanitary drains & Cleanouts GF | 7 | 7 | 2027-04-18 | 2027-04-25 | 0% | 0% | -49
CO.RO.D22.0GF.1485 | RO l Install of Inspection Chamber GF | 5 | 5 | 2027-04-26 | 2027-05-01 | 0% | 0% | -49
CO.RO.D22.0GF.1475 | RO l Install of General Duty Plumbing Valves GF | 9 | 9 | 2027-04-29 | 2027-05-09 | 0% | 0% | -84
CO.RO.D22.0GF.1815 | RO l Install of Plumbing water meter GF | 6 | 6 | 2027-04-29 | 2027-05-05 | 0% | 0% | -53
CO.RO.D22.0GF.1470 | RO l Install of Plumbing pipes insulation GF | 8 | 8 | 2027-05-10 | 2027-05-22 | 0% | 0% | -84
CO.RO.D22.0GF.1465 | RO l Install of Plumbing Fixtures GF | 11 | 11 | 2027-05-31 | 2027-06-12 | 0% | 0% | -82
KAFD00330-636-SBC-UP-261029.5.1.2.11Heating, Ventilating And Air Conditioning |  | 50 | 50 | 2027-04-18 | 2027-06-17 | 0% | 0% | -87
CO.RO.D23.0GF.1590 | RO l Install of HVAC Metal ducts GF | 12 | 12 | 2027-04-18 | 2027-05-01 | 0% | 0% | -95
CO.RO.D23.0GF.1575 | RO l Install of Hydronic pipes GF | 10 | 10 | 2027-04-18 | 2027-04-28 | 0% | 0% | -85
CO.RO.D23.0GF.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works GF | 11 | 11 | 2027-04-18 | 2027-04-29 | 0% | 0% | -77
CO.RO.D23.0GF.1545 | RO l Install of Genetal duty HVAC valves GF | 12 | 12 | 2027-04-29 | 2027-05-12 | 0% | 0% | -69
CO.RO.D23.0GF.1555 | RO l Install of HVAC water treatment GF | 14 | 14 | 2027-05-01 | 2027-05-19 | 0% | 0% | -77
CO.RO.D23.0GF.1550 | RO l Install of HVAC system equipments GF | 10 | 10 | 2027-05-01 | 2027-05-11 | 0% | 0% | -73
CO.RO.D23.0GF.1560 | RO l Install of HVAC Flexible ducts GF | 7 | 7 | 2027-05-02 | 2027-05-09 | 0% | 0% | -95
CO.RO.D23.0GF.1535 | RO l Install of Condensate drain pipes GF | 7 | 7 | 2027-05-02 | 2027-05-09 | 0% | 0% | -87
CO.RO.D23.0GF.1530 | RO l Install of HVAC dampers GF | 7 | 7 | 2027-05-02 | 2027-05-09 | 0% | 0% | -83
CO.RO.D23.0GF.1580 | RO l Install of Ducts thermal insulation GF | 8 | 8 | 2027-05-10 | 2027-05-22 | 0% | 0% | -95
CO.RO.D23.0GF.1540 | RO l Install of Chilled water Pipes Insulation GF | 10 | 10 | 2027-05-13 | 2027-05-27 | 0% | 0% | -69
CO.RO.D23.0GF.1565 | RO l Install of Split & Fan coil Units GF | 12 | 12 | 2027-05-23 | 2027-06-05 | 0% | 0% | -91
CO.RO.D23.0GF.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles GF | 8 | 8 | 2027-06-01 | 2027-06-09 | 0% | 0% | -95
CO.RO.D23.0GF.1525 | RO l HVAC Monitoring and Controlling System GF | 7 | 7 | 2027-06-10 | 2027-06-17 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.2.12Electrical |  | 83 | 83 | 2027-03-24 | 2027-07-01 | 0% | 0% | -91
CO.RO.D26.0GF.1650 | RO l Install of Meduim-Vlotage Cables GF | 6 | 6 | 2027-03-24 | 2027-03-30 | 0% | 0% | -47
CO.RO.D26.0GF.1615 | RO l Install of Meduim-Voltage Transformers GF | 10 | 10 | 2027-03-31 | 2027-04-11 | 0% | 0% | -47
CO.RO.D26.0GF.1610 | RO l Install of Meduim-Voltage switchgear GF | 10 | 10 | 2027-03-31 | 2027-04-11 | 0% | 0% | -26
CO.RO.D26.0GF.1655 | RO l Install of Enclosed bus assemblies GF | 5 | 5 | 2027-04-12 | 2027-04-17 | 0% | 0% | -47
CO.RO.D26.0GF.1620 | RO l Install of Diesel Generators GF | 7 | 7 | 2027-04-12 | 2027-04-19 | 0% | 0% | -40
CO.RO.D26.0GF.1680 | RO l Install of Cable tray and trunk GF | 8 | 8 | 2027-04-18 | 2027-04-26 | 0% | 0% | -85
CO.RO.D26.0GF.1695 | RO l Install of Main distribution board (MDB) GF | 10 | 10 | 2027-04-18 | 2027-04-28 | 0% | 0% | -47
CO.RO.D26.0GF.1640 | RO l Install of Automatic Transfer Switches (ATS) GF | 7 | 7 | 2027-04-20 | 2027-04-27 | 0% | 0% | -40
CO.RO.D26.0GF.1690 | RO l Install of Low voltage electrical power conductors GF | 12 | 12 | 2027-04-27 | 2027-05-10 | 0% | 0% | -85
CO.RO.D26.0GF.1670 | RO l Install of Disconnecting Switches GF | 5 | 5 | 2027-04-29 | 2027-05-04 | 0% | 0% | -46
CO.RO.D26.0GF.1635 | RO l Install of Distribution and power panel boards GF | 9 | 9 | 2027-05-11 | 2027-05-24 | 0% | 0% | -85
CO.RO.D26.0GF.1685 | RO l Install of Low voltage electrical power Cables GF | 10 | 10 | 2027-05-25 | 2027-06-05 | 0% | 0% | -85
CO.RO.D26.0GF.1675 | RO l Install of Interior lighting GF | 7 | 7 | 2027-06-01 | 2027-06-08 | 0% | 0% | -81
CO.RO.D26.0GF.1630 | RO l Install of Motor control Centers (MCC) GF | 8 | 8 | 2027-06-06 | 2027-06-14 | 0% | 0% | -85
CO.RO.D26.0GF.1645 | RO l Install of Lightning & Earthing Protection Systems GF | 7 | 7 | 2027-06-06 | 2027-06-13 | 0% | 0% | -75
CO.RO.D26.0GF.1660 | RO l Install of Sochets & lighting switches GF | 9 | 9 | 2027-06-10 | 2027-06-20 | 0% | 0% | -91
CO.RO.D26.0GF.1625 | RO l Install of VFD with inlet air filters and MCPr GF | 7 | 7 | 2027-06-15 | 2027-06-22 | 0% | 0% | -85
CO.RO.D26.0GF.1665 | RO l Install of Network lighting control system GF | 10 | 10 | 2027-06-21 | 2027-07-01 | 0% | 0% | -91
KAFD00330-636-SBC-UP-261029.5.1.2.13Communication System |  | 48 | 48 | 2027-04-27 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.0GF.1730 | RO l Install of Communication Cables GF | 6 | 6 | 2027-04-27 | 2027-05-03 | 0% | 0% | -53
CO.RO.D27.0GF.1720 | RO l Install of Communication equipment room fitting GF | 8 | 8 | 2027-06-10 | 2027-06-19 | 0% | 0% | -95
CO.RO.D27.0GF.1735 | RO l Install of Telecommunication outlets/connector GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -88
CO.RO.D27.0GF.1715 | RO l Install of Network systems GF | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.0GF.1725 | RO l Install of Data communication components GF | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.0GF.1740 | RO l Install of Wireless data network components GF | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.0GF.1745 | RO l Install of IP Based telephony communication system GF | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.2.14Electronic Safety And Security |  | 56 | 56 | 2027-04-18 | 2027-06-24 | 0% | 0% | -95
CO.RO.D28.0GF.1775 | RO l Install of Fire alarm system 1st & 2nd Fix GF | 10 | 10 | 2027-04-18 | 2027-04-28 | 0% | 0% | -78
CO.RO.D28.0GF.1755 | RO l Install of Access control 1st & 2nd Fix GF | 6 | 6 | 2027-04-18 | 2027-04-24 | 0% | 0% | -74
CO.RO.D28.0GF.1765 | RO l Install of CCTV system 1st & 2nd Fix GF | 6 | 6 | 2027-04-18 | 2027-04-24 | 0% | 0% | -74
CO.RO.D28.0GF.1770 | RO l Install of CCTV system 3nd Fix GF | 6 | 6 | 2027-06-10 | 2027-06-16 | 0% | 0% | -95
CO.RO.D28.0GF.1760 | RO l Install of Access control 3nd Fix GF | 7 | 7 | 2027-06-10 | 2027-06-17 | 0% | 0% | -89
CO.RO.D28.0GF.1780 | RO l Install of Fire alarm system 3nd Fix GF | 7 | 7 | 2027-06-17 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.2.15Utilities |  | 71 | 71 | 2027-03-27 | 2027-06-20 | 0% | 0% | -95
CO.RO.D33.0GF.1805 | RO l Install of Brackish Water Reverse Osmosis Plant GF | 71 | 71 | 2027-03-27 | 2027-06-20 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.3First Floor |  | 111 | 111 | 2027-02-20 | 2027-07-06 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.3.1Concrete Work |  | 73 | 73 | 2027-02-20 | 2027-05-23 | 0% | 0% | -90
CO.RO.D03.1ST.1145 | RO l Steel fixing for Columns 1st | 6 | 6 | 2027-02-20 | 2027-02-27 | 0% | 0% | -95
CO.RO.D03.1ST.1140 | RO l Shuttering & Pouring for Columns 1st | 6 | 6 | 2027-02-28 | 2027-03-06 | 0% | 0% | -95
CO.RO.D03.1ST.1120 | RO l Shuttering for Slab 1st | 8 | 8 | 2027-03-07 | 2027-03-18 | 0% | 0% | -95
CO.RO.D03.1ST.1125 | RO l Steel fixing & Pouring for Slab 1st | 8 | 8 | 2027-03-20 | 2027-03-28 | 0% | 0% | -95
CO.RO.D03.1ST.1155 | RO l Deshuttering works for Slab 1st | 10 | 10 | 2027-03-29 | 2027-04-08 | 0% | 0% | -95
CO.RO.D03.1ST.1165 | RO l Concete works for Floor screed 1st | 7 | 7 | 2027-05-01 | 2027-05-08 | 0% | 0% | -80
CO.RO.D03.1ST.1160 | RO l Concete works for Roof screed 1st | 7 | 7 | 2027-05-12 | 2027-05-23 | 0% | 0% | -92
KAFD00330-636-SBC-UP-261029.5.1.3.2Masonry Works |  | 12 | 12 | 2027-04-10 | 2027-04-22 | 0% | 0% | -95
CO.RO.D04.1ST.1170 | RO l Masonry works 1st | 12 | 12 | 2027-04-10 | 2027-04-22 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.3.3Metal Works |  | 33 | 33 | 2027-05-12 | 2027-06-22 | 0% | 0% | -93
CO.RO.D05.1ST.1190 | RO l Structural steel works 1st | 8 | 8 | 2027-05-12 | 2027-05-24 | 0% | 0% | -80
CO.RO.D05.1ST.1185 | RO l Install of Metal Ladders 1st | 3 | 3 | 2027-06-16 | 2027-06-19 | 0% | 0% | -95
CO.RO.D05.1ST.1175 | RO l Install of Steel covers 1st | 5 | 5 | 2027-06-17 | 2027-06-22 | 0% | 0% | -93
CO.RO.D05.1ST.1180 | RO l Install of Handrail 1st | 5 | 5 | 2027-06-17 | 2027-06-22 | 0% | 0% | -93
KAFD00330-636-SBC-UP-261029.5.1.3.4Wood & Plastics |  | 4 | 4 | 2027-05-23 | 2027-05-26 | 0% | 0% | -68
CO.RO.D06.1ST.1200 | RO l Install of Pantry cabinet 1st | 4 | 4 | 2027-05-23 | 2027-05-26 | 0% | 0% | -68
KAFD00330-636-SBC-UP-261029.5.1.3.5Thermal And Moisture Protection |  | 35 | 35 | 2027-04-24 | 2027-06-06 | 0% | 0% | -77
CO.RO.D07.1ST.1565 | RO l Wet areas insulation works 1st | 6 | 6 | 2027-04-24 | 2027-04-29 | 0% | 0% | -80
CO.RO.D07.1ST.1230 | RO l Rockwool insulation works 1st | 5 | 5 | 2027-04-24 | 2027-04-28 | 0% | 0% | -47
CO.RO.D07.1ST.1260 | RO l Roofing insulation System works 1st | 6 | 6 | 2027-05-24 | 2027-05-30 | 0% | 0% | -77
CO.RO.D07.1ST.1265 | RO l Canopy aluminium panels cladding 1st | 11 | 11 | 2027-05-25 | 2027-06-06 | 0% | 0% | -77
CO.RO.D07.1ST.1235 | RO l Install of Concrete tiles 1st | 4 | 4 | 2027-05-31 | 2027-06-03 | 0% | 0% | -75
KAFD00330-636-SBC-UP-261029.5.1.3.6Openings |  | 9 | 9 | 2027-06-15 | 2027-06-24 | 0% | 0% | -95
CO.RO.D08.1ST.1240 | RO l Install of Acoustic & Fire rated doors 1st | 9 | 9 | 2027-06-15 | 2027-06-24 | 0% | 0% | -95
CO.RO.D08.1ST.1255 | RO l Install of Aluminum windows & Louvers 1st | 5 | 5 | 2027-06-17 | 2027-06-22 | 0% | 0% | -93
CO.RO.D08.1ST.1250 | RO l Install of Steel doors 1st | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.3.7Finishes |  | 46 | 46 | 2027-04-24 | 2027-06-19 | 0% | 0% | -84
CO.RO.D09.1ST.1310 | RO l Internal Plaster works 1st | 9 | 9 | 2027-04-24 | 2027-05-03 | 0% | 0% | -95
CO.RO.D09.1ST.1300 | RO l Gypsum & cement board walls works 1st | 6 | 6 | 2027-04-24 | 2027-04-29 | 0% | 0% | -44
CO.RO.D09.1ST.1280 | RO l Floor Ceramic tiles & Stones works 1st | 6 | 6 | 2027-05-09 | 2027-05-15 | 0% | 0% | -80
CO.RO.D09.1ST.1305 | RO l Floor epoxy painting 1st | 6 | 6 | 2027-05-09 | 2027-05-15 | 0% | 0% | -80
CO.RO.D09.1ST.1285 | RO l Wall Ceramic tiles works 1st | 6 | 6 | 2027-05-12 | 2027-05-22 | 0% | 0% | -68
CO.RO.D09.1ST.1295 | RO l Wall epoxy painting 1st | 3 | 3 | 2027-05-19 | 2027-05-22 | 0% | 0% | -60
CO.RO.D09.1ST.1275 | RO l Gypsum board ceiling works 1st | 10 | 10 | 2027-05-25 | 2027-06-05 | 0% | 0% | -95
CO.RO.D09.1ST.1290 | RO l Wall & Ceiling painting works 1st | 8 | 8 | 2027-06-06 | 2027-06-14 | 0% | 0% | -95
CO.RO.D09.1ST.1315 | RO l Carpet tiles works 1st | 4 | 4 | 2027-06-15 | 2027-06-19 | 0% | 0% | -84
KAFD00330-636-SBC-UP-261029.5.1.3.8Specialities |  | 29 | 29 | 2027-05-23 | 2027-06-24 | 0% | 0% | -89
CO.RO.D10.1ST.1340 | RO l Install of Toilet Accessories 1st | 5 | 5 | 2027-05-23 | 2027-05-27 | 0% | 0% | -65
CO.RO.D10.1ST.1335 | RO l Corner guards 1st | 3 | 3 | 2027-06-15 | 2027-06-17 | 0% | 0% | -83
CO.RO.D10.1ST.1330 | RO l Install of Fire Extinguisher 1st | 4 | 4 | 2027-06-21 | 2027-06-24 | 0% | 0% | -89
KAFD00330-636-SBC-UP-261029.5.1.3.9Furnishing |  | 4 | 4 | 2027-05-23 | 2027-05-26 | 0% | 0% | -64
CO.RO.D12.1ST.1345 | RO l Install of Vanity Counter 1st | 4 | 4 | 2027-05-23 | 2027-05-26 | 0% | 0% | -64
KAFD00330-636-SBC-UP-261029.5.1.3.10Fire Superssion |  | 42 | 42 | 2027-04-29 | 2027-06-20 | 0% | 0% | -89
CO.RO.D21.1ST.1415 | RO l Install of Fire Suppression standpipes 1st | 10 | 10 | 2027-04-29 | 2027-05-10 | 0% | 0% | -95
CO.RO.D21.1ST.1365 | RO l Install of Fire Suppression valves 1st | 9 | 9 | 2027-05-11 | 2027-05-24 | 0% | 0% | -95
CO.RO.D21.1ST.1385 | RO l Install of Clean Agent FK-5.1.12 System 1st | 11 | 11 | 2027-05-11 | 2027-05-26 | 0% | 0% | -68
CO.RO.D21.1ST.1420 | RO l Install of Fire Suppersion Sprinkls 1st | 6 | 6 | 2027-06-06 | 2027-06-12 | 0% | 0% | -82
CO.RO.D21.1ST.1370 | RO l Install of Fire Hose Cabinets 1st | 5 | 5 | 2027-06-15 | 2027-06-20 | 0% | 0% | -89
KAFD00330-636-SBC-UP-261029.5.1.3.11Plumbing |  | 26 | 26 | 2027-04-24 | 2027-05-26 | 0% | 0% | -68
CO.RO.D22.1ST.1440 | RO l Install of Sanitary Pipes 1st | 4 | 4 | 2027-04-24 | 2027-04-27 | 0% | 0% | -68
CO.RO.D22.1ST.1490 | RO l Install of Domestic water pipes 1st | 6 | 6 | 2027-04-28 | 2027-05-04 | 0% | 0% | -68
CO.RO.D22.1ST.1480 | RO l Install of Sanitary drains & Cleanouts 1st | 4 | 4 | 2027-04-28 | 2027-05-02 | 0% | 0% | -50
CO.RO.D22.1ST.1470 | RO l Install of Plumbing pipes insulation 1st | 6 | 6 | 2027-05-05 | 2027-05-11 | 0% | 0% | -68
CO.RO.D22.1ST.1475 | RO l Install of General Duty Plumbing Valves 1st | 5 | 5 | 2027-05-05 | 2027-05-10 | 0% | 0% | -67
CO.RO.D22.1ST.1465 | RO l Install of Plumbing Fixtures 1st | 4 | 4 | 2027-05-23 | 2027-05-26 | 0% | 0% | -68
KAFD00330-636-SBC-UP-261029.5.1.3.12Heating, Ventilating And Air Conditioning |  | 33 | 33 | 2027-05-04 | 2027-06-14 | 0% | 0% | -84
CO.RO.D23.1ST.1575 | RO l Install of Hydronic pipes 1st | 9 | 9 | 2027-05-04 | 2027-05-13 | 0% | 0% | -95
CO.RO.D23.1ST.1590 | RO l Install of HVAC Metal ducts 1st | 8 | 8 | 2027-05-04 | 2027-05-12 | 0% | 0% | -95
CO.RO.D23.1ST.1535 | RO l Install of Condensate drain pipes 1st | 5 | 5 | 2027-05-04 | 2027-05-09 | 0% | 0% | -85
CO.RO.D23.1ST.1580 | RO l Install of Ducts thermal insulation 1st | 7 | 7 | 2027-05-13 | 2027-05-24 | 0% | 0% | -95
CO.RO.D23.1ST.1530 | RO l Install of HVAC dampers 1st | 4 | 4 | 2027-05-13 | 2027-05-20 | 0% | 0% | -81
CO.RO.D23.1ST.1600 | RO l Install of Exhaust Fans 1st | 6 | 6 | 2027-05-13 | 2027-05-23 | 0% | 0% | -79
CO.RO.D23.1ST.1560 | RO l Install of HVAC Flexible ducts 1st | 5 | 5 | 2027-05-13 | 2027-05-22 | 0% | 0% | -64
CO.RO.D23.1ST.1540 | RO l Install of Chilled water Pipes Insulation 1st | 6 | 6 | 2027-05-15 | 2027-05-24 | 0% | 0% | -95
CO.RO.D23.1ST.1565 | RO l Install of Split & Fan coil Units 1st | 7 | 7 | 2027-05-15 | 2027-05-25 | 0% | 0% | -81
CO.RO.D23.1ST.1545 | RO l Install of Genetal duty HVAC valves 1st | 5 | 5 | 2027-05-15 | 2027-05-23 | 0% | 0% | -65
CO.RO.D23.1ST.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles 1st | 4 | 4 | 2027-05-22 | 2027-05-25 | 0% | 0% | -81
CO.RO.D23.1ST.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works 1st | 6 | 6 | 2027-05-24 | 2027-05-30 | 0% | 0% | -92
CO.RO.D23.1ST.1595 | RO l Install of Air Handlig Units 1st | 7 | 7 | 2027-05-31 | 2027-06-07 | 0% | 0% | -92
CO.RO.D23.1ST.1525 | RO l HVAC Monitoring and Controlling System 1st | 6 | 6 | 2027-06-08 | 2027-06-14 | 0% | 0% | -92
KAFD00330-636-SBC-UP-261029.5.1.3.13Electrical |  | 52 | 52 | 2027-05-04 | 2027-07-06 | 0% | 0% | -95
CO.RO.D26.1ST.1680 | RO l Install of Cable tray and trunk 1st | 7 | 7 | 2027-05-04 | 2027-05-11 | 0% | 0% | -90
CO.RO.D26.1ST.1635 | RO l Install of Distribution and power panel boards 1st | 10 | 10 | 2027-05-12 | 2027-05-26 | 0% | 0% | -68
CO.RO.D26.1ST.1690 | RO l Install of Low voltage electrical power conductors 1st | 8 | 8 | 2027-05-12 | 2027-05-24 | 0% | 0% | -66
CO.RO.D26.1ST.1685 | RO l Install of Low voltage electrical power Cables 1st | 8 | 8 | 2027-05-12 | 2027-05-24 | 0% | 0% | -66
CO.RO.D26.1ST.1645 | RO l Install of Lightning & Earthing Protection Systems 1st | 5 | 5 | 2027-05-25 | 2027-05-30 | 0% | 0% | -63
CO.RO.D26.1ST.1670 | RO l Install of Disconnecting Switches 1st | 6 | 6 | 2027-05-27 | 2027-06-02 | 0% | 0% | -68
CO.RO.D26.1ST.1660 | RO l Install of Sochets & lighting switches 1st | 6 | 6 | 2027-06-15 | 2027-06-21 | 0% | 0% | -95
CO.RO.D26.1ST.1675 | RO l Install of Interior lighting 1st | 7 | 7 | 2027-06-15 | 2027-06-22 | 0% | 0% | -89
CO.RO.D26.1ST.1700 | RO l Install of Uninterruptible Power Supply (UPS) 1st | 5 | 5 | 2027-06-22 | 2027-06-27 | 0% | 0% | -95
CO.RO.D26.1ST.1705 | RO l Install of Power Factor Corrections Capacitors 1st | 7 | 7 | 2027-06-22 | 2027-06-29 | 0% | 0% | -95
CO.RO.D26.1ST.1665 | RO l Install of Network lighting control system 1st | 6 | 6 | 2027-06-30 | 2027-07-06 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.3.14Communication System |  | 33 | 33 | 2027-05-12 | 2027-06-22 | 0% | 0% | -93
CO.RO.D27.1ST.1730 | RO l Install of Communication Cables 1st | 5 | 5 | 2027-05-12 | 2027-05-20 | 0% | 0% | -90
CO.RO.D27.1ST.1720 | RO l Install of Communication equipment room fitting 1st | 10 | 10 | 2027-05-22 | 2027-06-01 | 0% | 0% | -90
CO.RO.D27.1ST.1745 | RO l Install of IP Based telephony communication system 1st | 8 | 8 | 2027-05-22 | 2027-05-30 | 0% | 0% | -80
CO.RO.D27.1ST.1740 | RO l Install of Wireless data network components 1st | 7 | 7 | 2027-05-22 | 2027-05-29 | 0% | 0% | -72
CO.RO.D27.1ST.1750 | RO l Install of Computers & Related Peripherals 1st | 7 | 7 | 2027-06-02 | 2027-06-09 | 0% | 0% | -90
CO.RO.D27.1ST.1715 | RO l Install of Network systems 1st | 8 | 8 | 2027-06-10 | 2027-06-19 | 0% | 0% | -90
CO.RO.D27.1ST.1725 | RO l Install of Data communication components 1st | 7 | 7 | 2027-06-15 | 2027-06-22 | 0% | 0% | -93
CO.RO.D27.1ST.1735 | RO l Install of Telecommunication outlets/connector 1st | 7 | 7 | 2027-06-15 | 2027-06-22 | 0% | 0% | -93
KAFD00330-636-SBC-UP-261029.5.1.3.15Electronic Safety And Security |  | 42 | 42 | 2027-05-04 | 2027-06-24 | 0% | 0% | -93
CO.RO.D28.1ST.1775 | RO l Install of Fire alarm system 1st & 2nd Fix 1st | 10 | 10 | 2027-05-04 | 2027-05-15 | 0% | 0% | -61
CO.RO.D28.1ST.1755 | RO l Install of Access control 1st & 2nd Fix 1st | 6 | 6 | 2027-05-04 | 2027-05-10 | 0% | 0% | -57
CO.RO.D28.1ST.1765 | RO l Install of CCTV system 1st & 2nd Fix 1st | 6 | 6 | 2027-05-04 | 2027-05-10 | 0% | 0% | -57
CO.RO.D28.1ST.1770 | RO l Install of CCTV system 3nd Fix 1st | 9 | 9 | 2027-06-15 | 2027-06-24 | 0% | 0% | -95
CO.RO.D28.1ST.1780 | RO l Install of Fire alarm system 3nd Fix 1st | 9 | 9 | 2027-06-15 | 2027-06-24 | 0% | 0% | -95
CO.RO.D28.1ST.1760 | RO l Install of Access control 3nd Fix 1st | 9 | 9 | 2027-06-15 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4Second Floor |  | 78 | 78 | 2027-03-29 | 2027-06-30 | 0% | 0% | -90
KAFD00330-636-SBC-UP-261029.5.1.4.1Existing Condition |  | 53 | 53 | 2027-03-29 | 2027-06-01 | 0% | 0% | -95
CO.RO.D03.2ND.1145 | RO l Steel fixing for Columns 2nd | 6 | 6 | 2027-03-29 | 2027-04-04 | 0% | 0% | -95
CO.RO.D03.2ND.1140 | RO l Shuttering & Pouring for Columns 2nd | 6 | 6 | 2027-04-05 | 2027-04-11 | 0% | 0% | -95
CO.RO.D03.2ND.1120 | RO l Shuttering for Slab 2nd | 7 | 7 | 2027-04-12 | 2027-04-19 | 0% | 0% | -95
CO.RO.D03.2ND.1125 | RO l Steel fixing & Pouring for Slab 2nd | 7 | 7 | 2027-04-20 | 2027-04-27 | 0% | 0% | -95
CO.RO.D03.2ND.1155 | RO l Deshuttering works for Slab 2nd | 12 | 12 | 2027-04-28 | 2027-05-11 | 0% | 0% | -95
CO.RO.D03.2ND.1160 | RO l Concete works for Roof screed 2nd | 7 | 7 | 2027-05-12 | 2027-05-23 | 0% | 0% | -92
CO.RO.D03.2ND.1165 | RO l Concete works for Floor screed 2nd | 7 | 7 | 2027-05-25 | 2027-06-01 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.2Masonry Works |  | 8 | 8 | 2027-05-12 | 2027-05-24 | 0% | 0% | -95
CO.RO.D04.2ND.1170 | RO l Masonry works 2nd | 8 | 8 | 2027-05-12 | 2027-05-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.3Metal Works |  | 27 | 27 | 2027-05-25 | 2027-06-24 | 0% | 0% | -95
CO.RO.D05.2ND.1190 | RO l Structural steel works 2nd | 10 | 10 | 2027-05-25 | 2027-06-05 | 0% | 0% | -80
CO.RO.D05.2ND.1191 | RO l overhead crane | 10 | 10 | 2027-05-25 | 2027-06-05 | 0% | 0% | -80
CO.RO.D05.2ND.1185 | RO l Install of Metal Ladders 2nd | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
CO.RO.D05.2ND.1180 | RO l Install of Handrail 2nd | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
CO.RO.D05.2ND.1175 | RO l Install of Steel covers 2nd | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.4Thermal And Moisture Protection |  | 19 | 19 | 2027-05-24 | 2027-06-14 | 0% | 0% | -80
CO.RO.D07.2ND.1260 | RO l Roofing insulation System works 2nd | 5 | 5 | 2027-05-24 | 2027-05-29 | 0% | 0% | -70
CO.RO.D07.2ND.1230 | RO l Rockwool insulation works 2nd | 5 | 5 | 2027-05-25 | 2027-05-30 | 0% | 0% | -71
CO.RO.D07.2ND.1235 | RO l Install of Concrete tiles 2nd | 4 | 4 | 2027-05-30 | 2027-06-02 | 0% | 0% | -70
CO.RO.D07.2ND.1265 | RO l Canopy aluminium panels cladding 2nd | 8 | 8 | 2027-06-06 | 2027-06-14 | 0% | 0% | -80
KAFD00330-636-SBC-UP-261029.5.1.4.5Openings |  | 6 | 6 | 2027-06-15 | 2027-06-21 | 0% | 0% | -92
CO.RO.D08.2ND.1240 | RO l Install of Acoustic & Fire rated doors 2nd | 6 | 6 | 2027-06-15 | 2027-06-21 | 0% | 0% | -92
CO.RO.D08.2ND.1255 | RO l Install of Aluminum windows & Louvers 2nd | 4 | 4 | 2027-06-15 | 2027-06-19 | 0% | 0% | -90
CO.RO.D08.2ND.1250 | RO l Install of Steel doors 2nd | 2 | 2 | 2027-06-15 | 2027-06-16 | 0% | 0% | -88
KAFD00330-636-SBC-UP-261029.5.1.4.6Finishes |  | 17 | 17 | 2027-05-25 | 2027-06-13 | 0% | 0% | -79
CO.RO.D09.2ND.1310 | RO l Internal Plaster works 2nd | 4 | 4 | 2027-05-25 | 2027-05-29 | 0% | 0% | -95
CO.RO.D09.2ND.1280 | RO l Floor Ceramic tiles & Stones works 2nd | 6 | 6 | 2027-06-02 | 2027-06-08 | 0% | 0% | -95
CO.RO.D09.2ND.1305 | RO l Floor epoxy painting 2nd | 5 | 5 | 2027-06-02 | 2027-06-07 | 0% | 0% | -77
CO.RO.D09.2ND.1275 | RO l Gypsum board ceiling works 2nd | 4 | 4 | 2027-06-05 | 2027-06-08 | 0% | 0% | -95
CO.RO.D09.2ND.1295 | RO l Wall epoxy painting 1st | 3 | 3 | 2027-06-08 | 2027-06-10 | 0% | 0% | -77
CO.RO.D09.2ND.1290 | RO l Wall & Ceiling painting works 2nd | 4 | 4 | 2027-06-09 | 2027-06-13 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.7Specialities |  | 4 | 4 | 2027-06-14 | 2027-06-17 | 0% | 0% | -83
CO.RO.D10.2ND.1335 | RO l Corner guards 2nd | 4 | 4 | 2027-06-14 | 2027-06-17 | 0% | 0% | -83
CO.RO.D10.2ND.1330 | RO l Install of Fire Extinguisher 2nd | 4 | 4 | 2027-06-14 | 2027-06-17 | 0% | 0% | -83
KAFD00330-636-SBC-UP-261029.5.1.4.8Fire Superssion |  | 25 | 25 | 2027-05-30 | 2027-06-27 | 0% | 0% | -95
CO.RO.D21.2ND.1415 | RO l Install of Fire Suppression standpipes 2nd | 5 | 5 | 2027-05-30 | 2027-06-03 | 0% | 0% | -95
CO.RO.D21.2ND.1365 | RO l Install of Fire Suppression valves 2nd | 5 | 5 | 2027-06-05 | 2027-06-09 | 0% | 0% | -95
CO.RO.D21.2ND.1420 | RO l Install of Fire Suppersion Sprinkls 2nd | 7 | 7 | 2027-06-09 | 2027-06-16 | 0% | 0% | -95
CO.RO.D21.2ND.1370 | RO l Install of Fire Hose Cabinets 2nd | 3 | 3 | 2027-06-10 | 2027-06-13 | 0% | 0% | -83
CO.RO.D21.2ND.1385 | RO l Install of Clean Agent FK-5.1.12 System 2nd | 9 | 9 | 2027-06-17 | 2027-06-27 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.9Plumbing |  | 27 | 27 | 2027-05-24 | 2027-06-23 | 0% | 0% | -92
CO.RO.D22.2ND.1520 | RO l Install of Vibration & Seismic controls For Plumbing 2nd | 8 | 8 | 2027-05-24 | 2027-06-01 | 0% | 0% | -92
CO.RO.D22.2ND.1440 | RO l Install of Sanitary Pipes 2nd | 5 | 5 | 2027-05-25 | 2027-05-30 | 0% | 0% | -83
CO.RO.D22.2ND.1490 | RO l Install of Domestic water pipes 2nd | 6 | 6 | 2027-05-31 | 2027-06-06 | 0% | 0% | -83
CO.RO.D22.2ND.1480 | RO l Install of Sanitary drains & Cleanouts 2nd | 3 | 3 | 2027-05-31 | 2027-06-02 | 0% | 0% | -74
CO.RO.D22.2ND.1500 | RO l Install of Domestic Water Packaged Booster Pumpsr 2nd | 6 | 6 | 2027-06-02 | 2027-06-08 | 0% | 0% | -92
CO.RO.D22.2ND.1475 | RO l Install of General Duty Plumbing Valves 2nd | 6 | 6 | 2027-06-07 | 2027-06-13 | 0% | 0% | -83
CO.RO.D22.2ND.1495 | RO l Install of Electrical water heater 2nd | 4 | 4 | 2027-06-07 | 2027-06-10 | 0% | 0% | -81
CO.RO.D22.2ND.1470 | RO l Install of Plumbing pipes insulation 2nd | 4 | 4 | 2027-06-07 | 2027-06-10 | 0% | 0% | -81
CO.RO.D22.2ND.1505 | RO l Install of Circulating Pumps 2nd | 6 | 6 | 2027-06-09 | 2027-06-15 | 0% | 0% | -92
CO.RO.D22.2ND.1510 | RO l Install of GRP water tank 2nd | 3 | 3 | 2027-06-16 | 2027-06-19 | 0% | 0% | -92
CO.RO.D22.2ND.1515 | RO l Install of Water Filters 2nd | 4 | 4 | 2027-06-20 | 2027-06-23 | 0% | 0% | -92
KAFD00330-636-SBC-UP-261029.5.1.4.10Heating, Ventilating And Air Conditioning |  | 30 | 30 | 2027-05-24 | 2027-06-27 | 0% | 0% | -95
CO.RO.D23.2ND.1585 | RO l Vibration & Seismic controls For HVAC Piping & Pump works 2nd | 7 | 7 | 2027-05-24 | 2027-05-31 | 0% | 0% | -89
CO.RO.D23.2ND.1575 | RO l Install of Hydronic pipes 2nd | 5 | 5 | 2027-05-30 | 2027-06-03 | 0% | 0% | -95
CO.RO.D23.2ND.1535 | RO l Install of Condensate drain pipes 2nd | 5 | 5 | 2027-05-30 | 2027-06-03 | 0% | 0% | -95
CO.RO.D23.2ND.1590 | RO l Install of HVAC Metal ducts 2nd | 7 | 7 | 2027-05-30 | 2027-06-06 | 0% | 0% | -95
CO.RO.D23.2ND.1595 | RO l Install of Air Handlig Units 2nd | 10 | 10 | 2027-06-01 | 2027-06-12 | 0% | 0% | -89
CO.RO.D23.2ND.1545 | RO l Install of Genetal duty HVAC valves 2nd | 7 | 7 | 2027-06-05 | 2027-06-12 | 0% | 0% | -95
CO.RO.D23.2ND.1540 | RO l Install of Chilled water Pipes Insulation 2nd | 4 | 4 | 2027-06-05 | 2027-06-08 | 0% | 0% | -79
CO.RO.D23.2ND.1560 | RO l Install of HVAC Flexible ducts 2nd | 5 | 5 | 2027-06-07 | 2027-06-12 | 0% | 0% | -95
CO.RO.D23.2ND.1600 | RO l Install of Exhaust Fans 2nd | 4 | 4 | 2027-06-07 | 2027-06-10 | 0% | 0% | -88
CO.RO.D23.2ND.1570 | RO l Install of HVAC Diffusers, Resgisters and Grilles 1st | 4 | 4 | 2027-06-09 | 2027-06-13 | 0% | 0% | -90
CO.RO.D23.2ND.1565 | RO l Install of Split & Fan coil Units 2nd | 6 | 6 | 2027-06-13 | 2027-06-19 | 0% | 0% | -95
CO.RO.D23.2ND.1530 | RO l Install of HVAC dampers 2nd | 4 | 4 | 2027-06-13 | 2027-06-16 | 0% | 0% | -86
CO.RO.D23.2ND.1580 | RO l Install of Ducts thermal insulation 2nd | 3 | 3 | 2027-06-13 | 2027-06-15 | 0% | 0% | -85
CO.RO.D23.2ND.1525 | RO l HVAC Monitoring and Controlling System 2nd | 7 | 7 | 2027-06-20 | 2027-06-27 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.11Electrical |  | 28 | 28 | 2027-05-30 | 2027-06-30 | 0% | 0% | -90
CO.RO.D26.2ND.1680 | RO l Install of Cable tray and trunk 2nd | 6 | 6 | 2027-05-30 | 2027-06-05 | 0% | 0% | -95
CO.RO.D26.2ND.1690 | RO l Install of Low voltage electrical power conductors 2nd | 5 | 5 | 2027-06-06 | 2027-06-10 | 0% | 0% | -95
CO.RO.D26.2ND.1685 | RO l Install of Low voltage electrical power Cables 2nd | 5 | 5 | 2027-06-06 | 2027-06-10 | 0% | 0% | -95
CO.RO.D26.2ND.1645 | RO l Install of Lightning & Earthing Protection Systems 2nd | 5 | 5 | 2027-06-12 | 2027-06-16 | 0% | 0% | -95
CO.RO.D26.2ND.1670 | RO l Install of Disconnecting Switches 2nd | 6 | 6 | 2027-06-12 | 2027-06-17 | 0% | 0% | -81
CO.RO.D26.2ND.1660 | RO l Install of Sochets & lighting switches 2nd | 6 | 6 | 2027-06-14 | 2027-06-20 | 0% | 0% | -86
CO.RO.D26.2ND.1675 | RO l Install of Interior lighting 2nd | 6 | 6 | 2027-06-14 | 2027-06-20 | 0% | 0% | -86
CO.RO.D26.2ND.1665 | RO l Install of Network lighting control system 2nd | 5 | 5 | 2027-06-26 | 2027-06-30 | 0% | 0% | -90
KAFD00330-636-SBC-UP-261029.5.1.4.12Communication System |  | 17 | 17 | 2027-06-06 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.2ND.1730 | RO l Install of Communication Cables 2nd | 7 | 7 | 2027-06-06 | 2027-06-13 | 0% | 0% | -95
CO.RO.D27.2ND.1720 | RO l Install of Communication equipment room fitting 2nd | 6 | 6 | 2027-06-14 | 2027-06-20 | 0% | 0% | -95
CO.RO.D27.2ND.1725 | RO l Install of Data communication components 2nd | 6 | 6 | 2027-06-14 | 2027-06-20 | 0% | 0% | -95
CO.RO.D27.2ND.1740 | RO l Install of Wireless data network components 2nd | 7 | 7 | 2027-06-14 | 2027-06-21 | 0% | 0% | -92
CO.RO.D27.2ND.1745 | RO l Install of IP Based telephony communication system 2nd | 5 | 5 | 2027-06-14 | 2027-06-19 | 0% | 0% | -90
CO.RO.D27.2ND.1715 | RO l Install of Network systems 2nd | 4 | 4 | 2027-06-21 | 2027-06-24 | 0% | 0% | -95
CO.RO.D27.2ND.1735 | RO l Install of Telecommunication outlets/connector 2nd | 4 | 4 | 2027-06-21 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.4.13Electronic Safety And Security |  | 23 | 23 | 2027-05-30 | 2027-06-24 | 0% | 0% | -95
CO.RO.D28.2ND.1755 | RO l Install of Access control 1st & 2nd Fix 2nd | 6 | 6 | 2027-05-30 | 2027-06-05 | 0% | 0% | -88
CO.RO.D28.2ND.1765 | RO l Install of CCTV system 1st & 2nd Fix 2nd | 6 | 6 | 2027-05-30 | 2027-06-05 | 0% | 0% | -88
CO.RO.D28.2ND.1775 | RO l Install of Fire alarm system 1st & 2nd Fix 2nd | 10 | 10 | 2027-05-30 | 2027-06-09 | 0% | 0% | -87
CO.RO.D28.2ND.1760 | RO l Install of Access control 3nd Fix 2nd | 5 | 5 | 2027-06-14 | 2027-06-19 | 0% | 0% | -95
CO.RO.D28.2ND.1770 | RO l Install of CCTV system 3nd Fix 2nd | 5 | 5 | 2027-06-14 | 2027-06-19 | 0% | 0% | -95
CO.RO.D28.2ND.1780 | RO l Install of Fire alarm system 3nd Fix 1st | 5 | 5 | 2027-06-20 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.5External Work |  | 286 | 69 | 22-Oct-25 A | 2027-06-27 | 3.62% | 3.62% | -87
KAFD00330-636-SBC-UP-261029.5.1.5.1Earthworks |  | 12 | 0 | 22-Oct-25 A | 04-Nov-25 A | 100% | 100%
CO.RO.D31.0EX.1050 | RO l Site clearing wrosk EX | 12 | 0 | 22-Oct-25 A | 04-Nov-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.1.5.2Masonary works |  | 6 | 6 | 2027-05-12 | 2027-05-22 | 0% | 0% | -64
CO.RO.D04.0EX.1205 | RO l Stone cladding EX | 6 | 6 | 2027-05-12 | 2027-05-22 | 0% | 0% | -64
KAFD00330-636-SBC-UP-261029.5.1.5.3Thermal And Moisture Protection |  | 12 | 12 | 2027-06-03 | 2027-06-16 | 0% | 0% | -88
CO.RO.D07.0EX.1270 | RO l aluminium panels cladding EX | 12 | 12 | 2027-06-03 | 2027-06-16 | 0% | 0% | -88
KAFD00330-636-SBC-UP-261029.5.1.5.4Finishes |  | 32 | 32 | 2027-04-24 | 2027-06-02 | 0% | 0% | -88
CO.RO.D09.0EX.1320 | RO l Plaster works EX | 16 | 16 | 2027-04-24 | 2027-05-11 | 0% | 0% | -88
CO.RO.D09.0EX.1325 | RO l painting works EX | 16 | 16 | 2027-05-12 | 2027-06-02 | 0% | 0% | -88
KAFD00330-636-SBC-UP-261029.5.1.5.5Conveying System |  | 9 | 9 | 2027-06-17 | 2027-06-27 | 0% | 0% | -95
CO.RO.D14.0GN.1355 | RO l Elevators GN | 9 | 9 | 2027-06-17 | 2027-06-27 | 0% | 0% | -95
CO.RO.D14.0GN.1356 | RO l Submersibl Pump for Elevator GN | 9 | 9 | 2027-06-17 | 2027-06-27 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.1.5.6Electrical |  | 14 | 14 | 2027-06-03 | 2027-06-19 | 0% | 0% | -80
CO.RO.D26.0EX.1710 | RO l Install of Exterior lighting EX | 14 | 14 | 2027-06-03 | 2027-06-19 | 0% | 0% | -80
KAFD00330-636-SBC-UP-261029.5.1.5.7Exterior Improvement |  | 46 | 46 | 2027-04-05 | 2027-05-31 | 0% | 0% | -72
CO.RO.D32.0EX.1790 | RO l Install of Precast concrete wall EX | 17 | 17 | 2027-04-05 | 2027-04-24 | 0% | 0% | -72
CO.RO.D32.0EX.1791 | RO l Wayfinding works EX | 10 | 10 | 2027-04-25 | 2027-05-05 | 0% | 0% | -72
CO.RO.D32.0EX.1800 | RO l Precast concrete paving works EX | 11 | 11 | 2027-05-06 | 2027-05-22 | 0% | 0% | -72
CO.RO.D32.0EX.1795 | RO l Road works EX | 17 | 17 | 2027-05-06 | 2027-05-29 | 0% | 0% | -70
CO.RO.D32.0EX.1785 | RO l Install of Sliding gates EX | 8 | 8 | 2027-05-06 | 2027-05-15 | 0% | 0% | -61
CO.RO.D32.0EX.1801 | RO l Car Park shade EX | 8 | 8 | 2027-05-23 | 2027-05-31 | 0% | 0% | -72
KAFD00330-636-SBC-UP-261029.5.1.5.8Process Scada System And Instrumentation |  | 6 | 6 | 2027-06-19 | 2027-06-24 | 0% | 0% | -95
CO.RO.D40.0GN.1810 | RO l Process scada system and intrumentation GN | 6 | 6 | 2027-06-19 | 2027-06-24 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.5.2Pump-Station |  | 286 | 76 | 04-Dec-25 A | 2027-01-26 | 19.8% | 39.76% | 4
KAFD00330-636-SBC-UP-261029.5.2.1Electrical Room |  | 241 | 76 | 05-Dec-25 A | 2027-01-26 | 13.43% | 20.76% | 4
KAFD00330-636-SBC-UP-261029.5.2.1.1Existing Condition |  | 12 | 0 | 01-Jan-26 A | 07-Jan-26 A | 100% | 100%
CO.PS.D02.ELC.1000 | IPS l Geotechnical Investigations works | 12 | 0 | 01-Jan-26 A | 07-Jan-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.2.1.2Earthwork |  | 116 | 0 | 05-Dec-25 A | 03-Jun-26 A | 2.13% | 100%
CO.PS.D31.ELC.1015 | IPS l Excavation Works | 12 | 0 | 05-Dec-25 A | 03-Jun-26 A | 0% | 100%
CO.PS.D31.ELC.1010 | IPS l Site clearing works | 8 | 0 | 11-Dec-25 A | 11-Mar-26 A | 12.5% | 100%
CO.PS.D31.ELC.1020 | IPS l Piles rainforced concrete works | 17 | 0 | 22-Jan-26 A | 22-Apr-26 A | 0% | 100%
CO.PS.D31.ELC.1005 | IPS l Under Foundation Probe Holes works | 11 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
KAFD00330-636-SBC-UP-261029.5.2.1.3Concrete Work |  | 236 | 0 | 28-May-26 A | 16-Sep-26 A | 76.09% | 100%
CO.PS.D03.ELC.1030 | IPS l Plain Concrete works for foundation | 5 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
CO.PS.D03.ELC.1040 | IPS l Concrete works for Isolated footings | 14 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
CO.PS.D03.ELC.1045 | IPS l Concrete works for Columns neck & Ground beams | 6 | 0 | 11-Jun-26 A | 17-Jun-26 A | 0% | 100%
CO.PS.D03.ELC.1050 | IPS l Concrete works for Columns | 7 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
CO.PS.D03.ELC.1055 | IPS l Concrete works for Slabs | 12 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
CO.PS.D03.ELC.1035 | IPS l Concrete works for Slab on grade | 5 | 0 | 09-Jul-26 A | 15-Jul-26 A | 100% | 100%
CO.PS.D03.ELC.1065 | IPS l Deshuttering works for Slabs | 14 | 0 | 13-Aug-26 A | 19-Aug-26 A | 100% | 100%
CO.PS.D03.ELC.1060 | IPS l Concrete works for Roof screed | 4 | 0 | 10-Sep-26 A | 16-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.2.1.4Masonry Works |  | 6 | 0 | 30-Jul-26 A | 16-Sep-26 A | 100% | 100%
CO.PS.D04.ELC.1170 | IPS l Masonry works | 6 | 0 | 30-Jul-26 A | 16-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.2.1.5Metal Works |  | 2 | 2 | 2026-11-28 | 2026-11-29 | 0% | 0% | 54
CO.PS.D05.ELC.1185 | IPS l Install of Metal ladder | 2 | 2 | 2026-11-28 | 2026-11-29 | 0% | 0% | 54
KAFD00330-636-SBC-UP-261029.5.2.1.6Thermal And Moisture Protection |  | 241 | 14 | 04-Jun-26 A | 2026-12-08 | 24.86% | 31.48% | 32
CO.PS.D07.ELC.1210 | IPS l Foundation Waterproofing works | 4 | 0 | 04-Jun-26 A | 10-Jun-26 A | 0% | 100%
CO.PS.D07.ELC.1215 | IPS l Install of HDPE Waterproofing Sheets | 2 | 0 | 02-Jul-26 A | 22-Sep-26 A | 100% | 100%
CO.PS.D07.ELC.1260 | IPS l Roofing System works | 7 | 0 | 01-Oct-26 A | 21-Oct-26 A | 100% | 100%
CO.PS.D07.ELC.1235 | IPS l Terrazzo Tiles works | 4 | 0 | 15-Oct-26 A | 28-Oct-26 A | 0% | 100%
CO.PS.D07.ELC.1265 | IPS l Install of aluminum cladding | 14 | 14 | 2026-11-23 | 2026-12-08 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.5.2.1.7Openings |  | 4 | 4 | 2026-11-23 | 2026-11-26 | 0% | 0% | 49
CO.PS.D08.ELC.1250 | IPS l Install of Steel doors | 4 | 4 | 2026-11-23 | 2026-11-26 | 0% | 0% | 39
CO.PS.D08.ELC.1255 | IPS l Install of Aluminium louvers | 4 | 4 | 2026-11-23 | 2026-11-26 | 0% | 0% | 49
KAFD00330-636-SBC-UP-261029.5.2.1.8Finishes |  | 31 | 7 | 17-Sep-26 A | 2026-11-22 | 39.96% | 60.24% | 3
CO.PS.D09.ELC.1310 | IPS l Plaster works | 7 | 0 | 17-Sep-26 A | 30-Sep-26 A | 100% | 100%
CO.PS.D09.ELC.1290 | IPS l Painting works | 10 | 6 | 01-Oct-26 A | 2026-11-22 | 0% | 45% | 3
CO.PS.D09.ELC.1305 | IPS l Floor Epoxy Painting works | 7 | 7 | 2026-11-15 | 2026-11-22 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.5.2.1.9Specialties |  | 3 | 3 | 2026-11-23 | 2026-11-25 | 0% | 0% | 52
CO.PS.D10.ELC.1330 | IPS l Install of Fire Extinguisher | 3 | 3 | 2026-11-23 | 2026-11-25 | 0% | 0% | 52
KAFD00330-636-SBC-UP-261029.5.2.1.10Fire Suppression |  | 12 | 12 | 2026-11-23 | 2026-12-06 | 0% | 0% | 41
CO.PS.D21.ELC.1385 | IPS l Install of Clean Agent FK-5.1.12 cylinders | 12 | 12 | 2026-11-23 | 2026-12-06 | 0% | 0% | 41
KAFD00330-636-SBC-UP-261029.5.2.1.11Plumbing |  | 4 | 4 | 2026-11-19 | 2026-11-23 | 0% | 0% | 59
CO.PS.D22.ELC.1475 | IPS l Install of Plumbing pipes & valves | 4 | 4 | 2026-11-19 | 2026-11-23 | 0% | 0% | 59
KAFD00330-636-SBC-UP-261029.5.2.1.12Heating, Ventilating And Air Conditioning |  | 10 | 10 | 2026-11-23 | 2026-12-03 | 0% | 0% | 45
CO.PS.D23.ELC.1590 | IPS l Install of HVAC Field Instrumentation | 6 | 6 | 2026-11-23 | 2026-11-29 | 0% | 0% | 45
CO.PS.D23.ELC.1565 | IPS l Install of Split units | 4 | 4 | 2026-11-30 | 2026-12-03 | 0% | 0% | 45
KAFD00330-636-SBC-UP-261029.5.2.1.13Electrical |  | 87 | 71 | 17-Sep-26 A | 2027-01-21 | 10.68% | 9.19% | 3
CO.PS.D26.ELC.1675 | IPS l Install of Lighting fixtures | 4 | 7 | 17-Sep-26 A | 2027-01-09 | 0% | 20% | 7
CO.PS.D26.ELC.1645 | IPS l Install of Grounding and Bonding for Electrical Systems | 4 | 4 | 17-Sep-26 A | 2026-12-21 | 0% | 10% | 30
CO.PS.D26.ELC.1660 | IPS l Install of Switches & Socket outlets | 4 | 4 | 17-Sep-26 A | 2026-11-22 | 0% | 20% | 55
CO.PS.D26.ELC.1680 | IPS l Underground cable duct, manholes and trench works | 3 | 2 | 01-Oct-26 A | 2026-11-02 | 100% | 70% | 38
CO.PS.D26.ELC.1655 | IPS l Coordination for connection of electrical supply | 4 | 4 | 2026-11-03 | 2026-11-07 | 0% | 0% | 38
CO.PS.D26.ELC.1685 | IPS l Install of Low voltage cables & conductors | 4 | 4 | 2026-12-17 | 2026-12-21 | 0% | 0% | 25
CO.PS.D26.ELC.1670 | IPS l Install of Power Factor Corrections Capacitors | 11 | 11 | 2026-12-19 | 2026-12-30 | 0% | 0% | 3
CO.PS.D26.ELC.1695 | IPS l Install of Main distribution board (MDB) | 8 | 8 | 2026-12-31 | 2027-01-09 | 0% | 0% | 3
CO.PS.D26.ELC.1635 | IPS l Install of Distribution and power panel boards | 6 | 6 | 2027-01-10 | 2027-01-16 | 0% | 0% | 3
CO.PS.D26.ELC.1630 | IPS l Install of Motor control Centers (MCC) | 5 | 5 | 2027-01-17 | 2027-01-21 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.5.2.1.14Communication System |  | 23 | 23 | 2026-11-23 | 2026-12-19 | 0% | 0% | 32
CO.PS.D27.ELC.1720 | IPS l Install of Communication equipment room fitting | 4 | 4 | 2026-11-23 | 2026-11-26 | 0% | 0% | 32
CO.PS.D27.ELC.1725 | IPS l Install of Data communication components | 4 | 4 | 2026-11-28 | 2026-12-01 | 0% | 0% | 32
CO.PS.D27.ELC.1740 | IPS l Install of Wireless data network components | 5 | 5 | 2026-12-02 | 2026-12-07 | 0% | 0% | 32
CO.PS.D27.ELC.1745 | IPS l Install of IP Based telephony communication system | 4 | 4 | 2026-12-08 | 2026-12-12 | 0% | 0% | 32
CO.PS.D27.ELC.1715 | IPS l Install of Network Systems | 6 | 6 | 2026-12-13 | 2026-12-19 | 0% | 0% | 32
KAFD00330-636-SBC-UP-261029.5.2.1.15Electronic Safety And Security |  | 57 | 38 | 17-Sep-26 A | 2026-12-13 | 36.15% | 9.04% | 37
CO.PS.D28.ELC.1755 | IPS l Install of Access control 1st & 2nd Fix | 5 | 4 | 17-Sep-26 A | 2026-11-18 | 100% | 25% | 3
CO.PS.D28.ELC.1775 | IPS l Install of Fire alarm system 1st & 2nd Fix | 8 | 6 | 17-Sep-26 A | 2026-11-05 | 100% | 25% | 16
CO.PS.D28.ELC.1765 | IPS l Install of CCTV system 1st & 2nd Fix | 5 | 5 | 2026-11-19 | 2026-11-24 | 0% | 0% | 53
CO.PS.D28.ELC.1780 | IPS l Install of Fire alarm system 3nd Fix | 8 | 8 | 2026-11-23 | 2026-12-01 | 0% | 0% | 37
CO.PS.D28.ELC.1760 | IPS l Install of Access control 3nd Fix | 4 | 4 | 2026-11-28 | 2026-12-01 | 0% | 0% | 39
CO.PS.D28.ELC.1770 | IPS l Install of CCTV system 3nd Fix | 4 | 4 | 2026-12-09 | 2026-12-13 | 0% | 0% | 29
KAFD00330-636-SBC-UP-261029.5.2.1.16Process Scada System And Instrumentation |  | 8 | 8 | 2027-01-18 | 2027-01-26 | 0% | 0% | -1
CO.PS.D40.ELC.1810 | IPS l Process Control Systems | 8 | 8 | 2027-01-18 | 2027-01-26 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.5.2.2Pump Room |  | 286 | 68 | 04-Dec-25 A | 2027-01-17 | 31.13% | 68.48% | 12
KAFD00330-636-SBC-UP-261029.5.2.2.1Existing Condition |  | 12 | 0 | 04-Dec-25 A | 10-Dec-25 A | 100% | 100%
CO.PS.D02.PUM.1000 | IPS l Geotechnical Investigations works | 12 | 0 | 04-Dec-25 A | 10-Dec-25 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.2.2.2EARTHWORK |  | 196 | 1 | 08-Jan-26 A | 2026-10-31 | 58.12% | 94.43% | 58
CO.PS.D31.PUM.1010 | IPS l Site clearing works | 10 | 0 | 08-Jan-26 A | 18-Feb-26 A | 100% | 100%
CO.PS.D31.PUM.1015 | IPS l Excavation Works | 10 | 0 | 23-Apr-26 A | 29-Apr-26 A | 0% | 100%
CO.PS.D31.PUM.1020 | IPS l Piles rainforced concrete works | 14 | 0 | 23-Apr-26 A | 06-May-26 A | 0% | 100%
CO.PS.D31.PUM.1005 | IPS l Under Foundation Probe Holes works | 4 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
CO.PS.D31.PUM.1025 | IPS l Groundwater Control System works | 10 | 1 | 25-Jun-26 A | 2026-10-31 | 100% | 90% | 58
KAFD00330-636-SBC-UP-261029.5.2.2.3Concrete Work |  | 243 | 3 | 07-May-26 A | 2026-11-02 | 11.87% | 99.28% | 63
CO.PS.D03.PUM.1070 | IPS l Plain Concrete works for foundation stage (1) | 4 | 0 | 07-May-26 A | 13-May-26 A | 0% | 100%
CO.PS.D03.PUM.1080 | IPS l Concrete works for Foundation stage (1) | 7 | 0 | 07-May-26 A | 20-May-26 A | 0% | 100%
CO.PS.D03.PUM.1090 | IPS l Concrete works for Basement walls stage (1) | 14 | 0 | 14-May-26 A | 27-May-26 A | 0% | 100%
CO.PS.D03.PUM.1075 | IPS l Plain Concrete works for foundation stage (2) | 4 | 0 | 21-May-26 A | 27-May-26 A | 0% | 100%
CO.PS.D03.PUM.1095 | IPS l Concrete works for Basement walls stage (2) | 14 | 0 | 28-May-26 A | 01-Jul-26 A | 0% | 100%
CO.PS.D03.PUM.1085 | IPS l Concrete works for Foundation stage (2) | 7 | 0 | 28-May-26 A | 03-Jun-26 A | 0% | 100%
CO.PS.D03.PUM.1055 | IPS l Concrete works for Slabs | 10 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
CO.PS.D03.PUM.1065 | IPS l Concrete works for Floors screed works | 7 | 3 | 17-Sep-26 A | 2026-11-02 | 100% | 70% | 63
CO.PS.D03.PUM.1105 | IPS l Deshuttering works for Slabs | 14 | 0 | 17-Sep-26 A | 22-Sep-26 A | 100% | 100%
KAFD00330-636-SBC-UP-261029.5.2.2.4Metal Works |  | 4 | 4 | 2026-11-03 | 2026-11-07 | 0% | 0% | 73
CO.PS.D05.PUM.1175 | IPS l Install of Trench covers | 4 | 4 | 2026-11-03 | 2026-11-07 | 0% | 0% | 73
KAFD00330-636-SBC-UP-261029.5.2.2.5Wood & Plastics |  | 4 | 4 | 2026-11-03 | 2026-11-07 | 0% | 0% | 73
CO.PS.D06.PUM.1195 | IPS l Install of GRB ladders | 4 | 4 | 2026-11-03 | 2026-11-07 | 0% | 0% | 73
KAFD00330-636-SBC-UP-261029.5.2.2.6Thermal & Moisture Protection |  | 139 | 7 | 07-May-26 A | 2026-11-07 | 12.79% | 91.05% | 59
CO.PS.D07.PUM.1215 | IPS l Install of HDPE Waterproofing Sheets stage (1) | 5 | 0 | 07-May-26 A | 20-May-26 A | 0% | 100%
CO.PS.D07.PUM.1225 | IPS l Install of HDPE Waterproofing Sheets stage (2) | 5 | 0 | 28-May-26 A | 01-Jul-26 A | 0% | 100%
CO.PS.D07.PUM.1220 | IPS l Basement wall Waterproofing works | 10 | 7 | 08-Oct-26 A | 2026-11-07 | 100% | 30% | 59
KAFD00330-636-SBC-UP-261029.5.2.2.7Plumbing |  | 162 | 68 | 11-Jun-26 A | 2027-01-17 | 0% | 5.46% | 7
CO.PS.D22.PUM.1490 | IPS l Install of GRP Domestic Water Pipes | 6 | 4 | 11-Jun-26 A | 2026-11-03 | 0% | 30% | 49
CO.PS.D22.PUM.1475 | IPS l Install of General Duty Plumbing Valves | 8 | 8 | 2026-11-19 | 2026-11-28 | 0% | 0% | 36
CO.PS.D22.PUM.1815 | IPS l Install of Flow meter | 6 | 6 | 2026-11-29 | 2026-12-05 | 0% | 0% | 36
CO.PS.D22.PUM.1505 | IPS l Install of Submersible sump pumps | 8 | 8 | 2027-01-09 | 2027-01-17 | 0% | 0% | 7
KAFD00330-636-SBC-UP-261029.5.2.2.8Heating, Ventilation & Air Conditioning |  | 4 | 4 | 2026-11-07 | 2026-11-10 | 0% | 0% | 65
CO.PS.D23.PUM.1600 | IPS l Install of Exhaust Fans | 4 | 4 | 2026-11-07 | 2026-11-10 | 0% | 0% | 65
KAFD00330-636-SBC-UP-261029.5.2.2.9Electrical |  | 23 | 23 | 2026-12-22 | 2027-01-17 | 0% | 0% | 7
CO.PS.D26.PUM.1685 | IPS l Install of Low voltage cables & conductors | 5 | 5 | 2026-12-22 | 2026-12-27 | 0% | 0% | 25
CO.PS.D26.PUM.1695 | IPS l Install of Lighting fixtures | 7 | 7 | 2027-01-10 | 2027-01-17 | 0% | 0% | 7
KAFD00330-636-SBC-UP-261029.5.2.2.10Electronic Safety & Security |  | 98 | 38 | 02-Jul-26 A | 2026-12-13 | 60% | 18% | 37
CO.PS.D28.PUM.1775 | IPS l Install of Fire alarm system 1st & 2nd Fix | 10 | 7 | 02-Jul-26 A | 2026-11-07 | 100% | 30% | 68
CO.PS.D28.PUM.1780 | IPS l Install of Fire alarm system 3nd Fix | 10 | 10 | 2026-12-02 | 2026-12-13 | 0% | 0% | 37
KAFD00330-636-SBC-UP-261029.5.2.3Pump-Station ( External Works ) |  | 33 | 33 | 2026-12-09 | 2027-01-16 | 0% | 0% | 13
KAFD00330-636-SBC-UP-261029.5.2.3.1Special Constrction |  | 8 | 8 | 2026-12-09 | 2026-12-17 | 0% | 0% | 3
CO.PS.D13.0EX.1270 | IPS l Install of Aluminium Control booths | 8 | 8 | 2026-12-09 | 2026-12-17 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.5.2.3.2Exterior Improvement |  | 25 | 25 | 2026-12-19 | 2027-01-16 | 0% | 0% | 13
CO.PS.D32.0EX.1790 | IPS l Install of Precast concrete wall | 10 | 10 | 2026-12-19 | 2026-12-29 | 0% | 0% | 3
CO.PS.D32.0EX.1800 | IPS l Pre-cast concrete paving works | 4 | 4 | 2026-12-30 | 2027-01-03 | 0% | 0% | 3
CO.PS.D32.0EX.1785 | IPS l Install of Sliding gates | 5 | 5 | 2026-12-30 | 2027-01-04 | 0% | 0% | 23
CO.PS.D32.0EX.1805 | IPS l Install of Precast concrete curb | 6 | 6 | 2027-01-04 | 2027-01-10 | 0% | 0% | 13
CO.PS.D32.0EX.1820 | IPS l Planting works | 5 | 5 | 2027-01-11 | 2027-01-16 | 0% | 0% | 13
KAFD00330-636-SBC-UP-261029.5.3Collection System |  | 382 | 139 | 05-Dec-25 A | 2027-04-14 | 6.62% | 33.12% | -34
KAFD00330-636-SBC-UP-261029.5.3.1Plumbing |  | 382 | 139 | 05-Dec-25 A | 2027-04-14 | 1.13% | 31.98% | -34
KAFD00330-636-SBC-UP-261029.5.3.1.1Pumps inside Parcels |  | 325 | 128 | 18-Dec-25 A | 2027-04-01 | 6.77% | 20.68% | -23
CO.CL.D22.0EX.1120 | CLS l Civil works For Pump room P5.02 | 7 | 3 | 18-Dec-25 A | 2026-11-02 | 0% | 90% | -4
CO.CL.D22.0EX.1135 | CLS l Civil works For Pump room P5.04 | 7 | 3 | 18-Dec-25 A | 2026-11-02 | 0% | 90% | 33
CO.CL.D22.0EX.1105 | CLS l Pump room Electrical connection P2.09 | 6 | 5 | 25-Dec-25 A | 2027-03-06 | 0% | 20% | -13
CO.CL.D22.0EX.1100 | CLS l Pump room Electrical connection P5.05 | 6 | 5 | 25-Dec-25 A | 2027-02-24 | 0% | 20% | -5
CO.CL.D22.0EX.1095 | CLS l Pump room Electrical connection P5.04 | 6 | 5 | 25-Dec-25 A | 2027-02-14 | 0% | 20% | 3
CO.CL.D22.0EX.1080 | CLS l Pump room Electrical connection P5.02 | 6 | 5 | 01-Jan-26 A | 2027-01-17 | 0% | 20% | 27
CO.CL.D22.0EX.1070 | CLS l Pump room MEC Piping& fitting P4.11 | 10 | 3 | 22-Jan-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1075 | CLS l Pump room MEC Piping& fitting P3.09 | 10 | 3 | 07-Feb-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1115 | CLS l Pump room Electrical connection P3.09 | 6 | 5 | 07-Feb-26 A | 2027-03-18 | 0% | 20% | -21
CO.CL.D22.0EX.1110 | CLS l Pump room Electrical connection P4.11 | 6 | 5 | 07-Feb-26 A | 2027-03-06 | 0% | 20% | -13
CO.CL.D22.0EX.1090 | CLS l Pump room Electrical connection P5.03 | 6 | 5 | 07-Feb-26 A | 2027-02-04 | 0% | 20% | 11
CO.CL.D22.0EX.1145 | CLS l Civil works For Pump room P2.09 | 7 | 3 | 07-Feb-26 A | 2026-11-02 | 0% | 90% | 33
CO.CL.D22.0EX.1040 | CLS l Pump room MEC Piping& fitting P5.02 | 10 | 3 | 14-Feb-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1050 | CLS l Pump room MEC Piping& fitting P5.03 | 10 | 3 | 10-Mar-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1055 | CLS l Pump room MEC Piping& fitting P5.04 | 10 | 3 | 25-Mar-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1060 | CLS l Pump room MEC Piping& fitting P5.05 | 10 | 3 | 06-Apr-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1065 | CLS l Pump room MEC Piping& fitting P2.09 | 10 | 3 | 16-Apr-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1045 | CLS l Pump room MEC Piping& fitting P2.15 | 10 | 3 | 30-Apr-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1078 | CLS l Pump room MEC Piping& fitting P5.01 | 10 | 3 | 07-May-26 A | 2026-11-02 | 0% | 85% | -71
CO.CL.D22.0EX.1076 | CLS l Pump room MEC Piping& fitting P1.11 | 10 | 3 | 07-May-26 A | 2026-11-02 | 0% | 85% | -61
CO.CL.D22.0EX.1077 | CLS l Pump room MEC Piping& fitting P3.10 | 10 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 85% | -61
CO.CL.D22.0EX.1125 | CLS l Civil works For Pump room P2.15 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 3
CO.CL.D22.0EX.1130 | CLS l Civil works For Pump room P5.03 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 10
CO.CL.D22.0EX.1140 | CLS l Civil works For Pump room P5.05 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 33
CO.CL.D22.0EX.1150 | CLS l Civil works For Pump room P4.11 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 33
CO.CL.D22.0EX.1083 | CLS l Civil works For Pump room P5.01 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 33
CO.CL.D22.0EX.1086 | CLS l Civil works For Pump room P3.11 | 7 | 3 | 25-Jun-26 A | 2026-11-14 | 100% | 90% | 40
CO.CL.D22.0EX.1084 | CLS l Civil works For Pump room P5.06 | 7 | 3 | 25-Jun-26 A | 2026-11-02 | 100% | 90% | 43
CO.CL.D22.0EX.1081 | CLS l Civil works For Pump room P1.11 | 7 | 0 | 25-Jun-26 A | 01-Jul-26 A | 100% | 100%
CO.CL.D22.0EX.1079 | CLS l Pump room MEC Piping& fitting P5.06 | 10 | 3 | 02-Jul-26 A | 2026-11-02 | 100% | 85% | -71
CO.CL.D22.0EX.1074 | CLS l Pump room Electrical connection P5.01 | 6 | 5 | 02-Jul-26 A | 2027-03-25 | 0% | 20% | -33
CO.CL.D22.0EX.1037 | CLS l Pump room Electrical connection P3.11 | 6 | 5 | 02-Jul-26 A | 2027-04-01 | 0% | 20% | -33
CO.CL.D22.0EX.1072 | CLS l Pump room Electrical connection P1.11 | 6 | 5 | 02-Jul-26 A | 2027-03-18 | 0% | 20% | -21
CO.CL.D22.0EX.1085 | CLS l Pump room Electrical connection P2.15 | 6 | 5 | 02-Jul-26 A | 2027-01-26 | 100% | 20% | 19
CO.CL.D22.0EX.1155 | CLS l Civil works For Pump room P3.09 | 7 | 3 | 02-Jul-26 A | 2026-11-14 | 100% | 90% | 29
CO.CL.D22.0EX.1082 | CLS l Civil works For Pump room P3.10 | 7 | 3 | 02-Jul-26 A | 2026-11-14 | 100% | 90% | 92
CO.CL.D22.0EX.1071 | CLS l Pump room MEC Piping& fitting P3.11 | 10 | 10 | 2026-11-03 | 2026-11-14 | 0% | 0% | -71
CO.CL.D22.0EX.1021 | CLS l Valve works For Piping P5.02 | 7 | 7 | 2026-11-03 | 2026-11-10 | 0% | 0% | -4
CO.CL.D22.0EX.1022 | CLS l Valve works For Piping P2.15 | 7 | 7 | 2026-11-11 | 2026-11-18 | 0% | 0% | -4
CO.CL.D22.0EX.1027 | CLS l Valve works For Piping P2.09 | 7 | 7 | 2026-11-11 | 2026-11-18 | 0% | 0% | 29
CO.CL.D22.0EX.1023 | CLS l Valve works For Piping P5.03 | 7 | 7 | 2026-11-19 | 2026-11-26 | 0% | 0% | -4
CO.CL.D22.0EX.1034 | CLS l Valve works For Piping P5.06 | 7 | 7 | 2026-11-19 | 2026-11-26 | 0% | 0% | 29
CO.CL.D22.0EX.1024 | CLS l Valve works For Piping P5.04 | 7 | 7 | 2026-11-19 | 2026-11-26 | 0% | 0% | 67
CO.CL.D22.0EX.1031 | CLS l Valve works For Piping P1.11 | 7 | 7 | 2026-11-19 | 2026-11-26 | 0% | 0% | 67
CO.CL.D22.0EX.1028 | CLS l Valve works For Piping P4.11 | 7 | 7 | 2026-11-19 | 2026-11-26 | 0% | 0% | 81
CO.CL.D22.0EX.1041 | CLS l Valve works For Piping P3.11 | 7 | 7 | 2026-11-28 | 2026-12-05 | 0% | 0% | 29
CO.CL.D22.0EX.1026 | CLS l Valve works For Piping P5.05 | 7 | 7 | 2026-11-28 | 2026-12-05 | 0% | 0% | 67
CO.CL.D22.0EX.1032 | CLS l Valve works For Piping P3.10 | 7 | 7 | 2026-11-28 | 2026-12-05 | 0% | 0% | 67
CO.CL.D22.0EX.1029 | CLS l Valve works For Piping P3.09 | 7 | 7 | 2026-12-06 | 2026-12-13 | 0% | 0% | 67
CO.CL.D22.0EX.1033 | CLS l Valve works For Piping P5.01 | 7 | 7 | 2026-12-06 | 2026-12-13 | 0% | 0% | 67
CO.CL.D22.0EX.1000 | CLS l Install of Submersible pumps P2.15 | 8 | 8 | 2027-01-09 | 2027-01-17 | 0% | 0% | -48
CO.CL.D22.0EX.1005 | CLS l Install of Submersible pumps P5.03 | 8 | 8 | 2027-01-18 | 2027-01-26 | 0% | 0% | -48
CO.CL.D22.0EX.1010 | CLS l Install of Submersible pumps P2.09 | 8 | 8 | 2027-01-27 | 2027-02-04 | 0% | 0% | -48
CO.CL.D22.0EX.1015 | CLS l Install of Submersible pumps P4.11 | 8 | 8 | 2027-02-06 | 2027-02-14 | 0% | 0% | -48
CO.CL.D22.0EX.1020 | CLS l Install of Submersible pumps P1.11 | 8 | 8 | 2027-02-15 | 2027-02-24 | 0% | 0% | -48
CO.CL.D22.0EX.1025 | CLS l Install of Submersible pumps P3.10 | 8 | 8 | 2027-02-25 | 2027-03-06 | 0% | 0% | -48
CO.CL.D22.0EX.1035 | CLS l Install of Submersible pumps P5.06 | 8 | 8 | 2027-03-07 | 2027-03-18 | 0% | 0% | -48
CO.CL.D22.0EX.1073 | CLS l Pump room Electrical connection P3.10 | 6 | 6 | 2027-03-20 | 2027-03-25 | 0% | 0% | -33
CO.CL.D22.0EX.1036 | CLS l Pump room Electrical connection P5.06 | 6 | 6 | 2027-03-27 | 2027-04-01 | 0% | 0% | -33
KAFD00330-636-SBC-UP-261029.5.3.1.2Gravity Network Piping |  | 106 | 3 | 19-Mar-26 A | 2026-11-02 | 0% | 94.71% | 65
CO.CL.D33.0EX.1160 | CLS l Excavation works for GRP pipes and manholes part 1 | 10 | 0 | 19-Mar-26 A | 01-Apr-26 A | 0% | 100%
CO.CL.D33.0EX.1180 | CLS l Install of GRP pipes between manholes part 1 | 15 | 0 | 07-May-26 A | 20-May-26 A | 0% | 100%
CO.CL.D33.0EX.1165 | CLS l Backfilling works for GRP pipes and manholes part 1 | 14 | 0 | 14-May-26 A | 03-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1195 | CLS l Install of Precast Manholes part 1 | 14 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
CO.CL.D33.0EX.1190 | CLS l Install of Precast Manholes part 2 | 14 | 3 | 21-May-26 A | 2026-11-02 | 0% | 90% | 65
CO.CL.D33.0EX.1175 | CLS l Excavation works for GRP pipes and manholes part 2 | 10 | 3 | 21-May-26 A | 2026-11-02 | 0% | 95% | 65
CO.CL.D33.0EX.1185 | CLS l Install of GRP pipes between manholes part 2 | 15 | 3 | 28-May-26 A | 2026-11-02 | 0% | 90% | 65
CO.CL.D33.0EX.1170 | CLS l Backfilling works for GRP pipes and manholes part 2 | 14 | 3 | 04-Jun-26 A | 2026-11-02 | 0% | 80% | 65
KAFD00330-636-SBC-UP-261029.5.3.1.3Piping Between 5 Parcels and Manholes |  | 255 | 39 | 05-Dec-25 A | 2026-12-14 | 0% | 80.5% | 29
CO.CL.D33.0EX.1240 | CLS l Excavation works for HDPE pipes P3.10 | 10 | 0 | 05-Dec-25 A | 03-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1235 | CLS l Excavation works for HDPE pipes P5.02 | 10 | 0 | 05-Dec-25 A | 03-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1200 | CLS l Install of HDPE pipes P5.01 | 12 | 0 | 12-Feb-26 A | 17-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1225 | CLS l Excavation works for HDPE pipes P5.01 | 10 | 0 | 12-Feb-26 A | 18-Feb-26 A | 0% | 100%
CO.CL.D33.0EX.1205 | CLS l Install of HDPE pipes P3.09 | 12 | 0 | 26-Feb-26 A | 20-May-26 A | 0% | 100%
CO.CL.D33.0EX.1230 | CLS l Excavation works for HDPE pipes P3.09 | 10 | 0 | 26-Feb-26 A | 04-Mar-26 A | 0% | 100%
CO.CL.D33.0EX.1260 | CLS l Backfilling works for HDPE pipes P5.02 | 14 | 3 | 14-May-26 A | 2026-11-02 | 0% | 95% | 51
CO.CL.D33.0EX.1255 | CLS l Backfilling works for HDPE pipes P3.09 | 14 | 0 | 14-May-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1210 | CLS l Install of HDPE pipes P5.02 | 12 | 0 | 14-May-26 A | 01-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1250 | CLS l Backfilling works for HDPE pipes P5.01 | 14 | 0 | 14-May-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1201 | CLS l Break chamber works for HDPE pipes P5.01 | 12 | 0 | 14-May-26 A | 16-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1202 | CLS l Break chamber works for HDPE pipes P3.09 | 12 | 0 | 14-May-26 A | 16-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1203 | CLS l Break chamber works for HDPE pipes P5.02 | 12 | 0 | 14-May-26 A | 16-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1215 | CLS l Install of HDPE pipes P3.10 | 12 | 3 | 28-May-26 A | 2026-11-02 | 0% | 90% | 51
CO.CL.D33.0EX.1204 | CLS l Break chamber works for HDPE pipes P3.10 | 12 | 3 | 28-May-26 A | 2026-11-02 | 0% | 95% | 51
CO.CL.D33.0EX.1220 | CLS l Install of HDPE pipes P3.11 | 12 | 3 | 11-Jun-26 A | 2026-11-02 | 0% | 90% | 51
CO.CL.D33.0EX.1265 | CLS l Backfilling works for HDPE pipes P3.10 | 14 | 3 | 11-Jun-26 A | 2026-11-02 | 0% | 90% | 51
CO.CL.D33.0EX.1206 | CLS l Break chamber works for HDPE pipes P3.11 | 12 | 3 | 11-Jun-26 A | 2026-11-02 | 0% | 90% | 51
CO.CL.D33.0EX.1270 | CLS l Backfilling works for HDPE pipes P3.11 | 14 | 3 | 11-Jun-26 A | 2026-11-02 | 0% | 90% | 65
CO.CL.D33.0EX.1245 | CLS l Excavation works for HDPE pipes P3.11 | 10 | 0 | 11-Jun-26 A | 16-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1275 | CLS l Install of General Duty valves | 14 | 14 | 2026-11-29 | 2026-12-14 | 0% | 0% | 29
KAFD00330-636-SBC-UP-261029.5.3.1.4Piping Between 4 Parcels and Pump station& 4 Parecl to RO |  | 326 | 39 | 14-May-26 A | 2026-12-14 | 4.43% | 87.76% | 29
CO.CL.D33.0EX.1280 | CLS l Install of HDPE pipes P5.03 | 12 | 0 | 14-May-26 A | 15-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1300 | CLS l Excavation works for HDPE pipes P5.03 | 10 | 0 | 14-May-26 A | 20-May-26 A | 0% | 100%
CO.CL.D33.0EX.1304 | CLS l Excavation works for HDPE pipes P4.11 | 14 | 0 | 21-May-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1309 | CLS l Install of HDPE pipes P4.11 | 14 | 0 | 21-May-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1296 | CLS l Break chamber for HDPE pipes P5.03 | 12 | 3 | 28-May-26 A | 2026-11-02 | 0% | 95% | 51
CO.CL.D33.0EX.1305 | CLS l Excavation works for HDPE pipes P5.04 | 10 | 0 | 28-May-26 A | 10-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1285 | CLS l Install of HDPE pipes P5.04 | 12 | 0 | 04-Jun-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1320 | CLS l Backfilling works for HDPE pipes P5.03 | 14 | 3 | 11-Jun-26 A | 2026-11-02 | 0% | 95% | 54
CO.CL.D33.0EX.1310 | CLS l Excavation works for HDPE pipes P5.05 | 10 | 0 | 11-Jun-26 A | 24-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1290 | CLS l Install of HDPE pipes P5.05 | 12 | 0 | 11-Jun-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1325 | CLS l Backfilling works for HDPE pipes P5.04 | 14 | 3 | 18-Jun-26 A | 2026-11-02 | 0% | 95% | 54
CO.CL.D33.0EX.1330 | CLS l Backfilling works for HDPE pipes P5.05 | 14 | 3 | 18-Jun-26 A | 2026-11-02 | 0% | 95% | 54
CO.CL.D33.0EX.1335 | CLS l Backfilling works for HDPE pipes P5.06 | 14 | 3 | 18-Jun-26 A | 2026-11-02 | 0% | 95% | 65
CO.CL.D33.0EX.1306 | CLS l Install of HDPE pipes P2.09 | 14 | 3 | 18-Jun-26 A | 2026-11-02 | 0% | 95% | 65
CO.CL.D33.0EX.1295 | CLS l Install of HDPE pipes P5.06 | 12 | 0 | 18-Jun-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1315 | CLS l Excavation works for HDPE pipes P5.06 | 10 | 0 | 18-Jun-26 A | 24-Jun-26 A | 0% | 100%
CO.CL.D33.0EX.1301 | CLS l Excavation works for HDPE pipes P2.09 | 14 | 0 | 18-Jun-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1302 | CLS l Excavation works for HDPE pipes P2.15 | 14 | 0 | 18-Jun-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1303 | CLS l Excavation works for HDPE pipes P1.11 | 14 | 0 | 18-Jun-26 A | 08-Jul-26 A | 0% | 100%
CO.CL.D33.0EX.1307 | CLS l Install of HDPE pipes P2.15 | 14 | 0 | 18-Jun-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1308 | CLS l Install of HDPE pipes P1.11 | 14 | 0 | 18-Jun-26 A | 09-Sep-26 A | 0% | 100%
CO.CL.D33.0EX.1311 | CLS l Backfilling works for HDPE pipes P2.09 | 14 | 3 | 02-Jul-26 A | 2026-11-02 | 100% | 95% | 65
CO.CL.D33.0EX.1312 | CLS l Backfilling works for HDPE pipes P2.15 | 14 | 3 | 02-Jul-26 A | 2026-11-02 | 100% | 95% | 65
CO.CL.D33.0EX.1313 | CLS l Backfilling works for HDPE pipes P1.11 | 14 | 3 | 02-Jul-26 A | 2026-11-02 | 100% | 95% | 65
CO.CL.D33.0EX.1314 | CLS l Backfilling works for HDPE pipes P4.11 | 14 | 3 | 02-Jul-26 A | 2026-11-02 | 100% | 95% | 65
CO.CL.D33.0EX.1340 | CLS l Install of General Duty valves | 14 | 14 | 2026-11-29 | 2026-12-14 | 0% | 0% | 29
KAFD00330-636-SBC-UP-261029.5.3.1.5Piping Inside Tunnels |  | 126 | 126 | 2026-11-15 | 2027-04-14 | 0% | 0% | -71
CO.CL.D33.0EX.1350 | CLS l Install of HDPE pipes inside tunnels part 1 (9 Parcel) | 25 | 25 | 2026-11-15 | 2026-12-13 | 0% | 0% | -71
CO.CL.D33.0EX.1355 | CLS l Install of HDPE pipes inside tunnels part 2 (P1.11) | 20 | 20 | 2026-12-14 | 2027-01-05 | 0% | 0% | -71
CO.CL.D33.0EX.1360 | CLS l Install of HDPE pipes inside tunnels part 3 (P2.09) | 20 | 20 | 2027-01-06 | 2027-01-28 | 0% | 0% | -71
CO.CL.D33.0EX.1365 | CLS l Install of HDPE pipes inside tunnels part 4 (P2.15) | 20 | 20 | 2027-01-30 | 2027-02-21 | 0% | 0% | -71
CO.CL.D33.0EX.1370 | CLS l Install of HDPE pipes inside tunnels part 5 (P4.11) | 20 | 20 | 2027-02-23 | 2027-03-21 | 0% | 0% | -71
CO.CL.D33.0EX.1345 | CLS l Install of GRP pipes inside tunnels | 21 | 21 | 2027-03-22 | 2027-04-14 | 0% | 0% | -71
CO.CL.D33.0EX.1390 | CLS l Install of General Duty valves | 21 | 21 | 2027-03-22 | 2027-04-14 | 0% | 0% | -71
KAFD00330-636-SBC-UP-261029.5.3.1.6Fabricated Drainage Channel |  | 32 | 32 | 2026-11-03 | 2026-12-09 | 0% | 0% | 70
CO.CL.D33.0EX.1395 | CLS l Excavation works for Fabricated Channel | 8 | 8 | 2026-11-03 | 2026-11-11 | 0% | 0% | 70
CO.CL.D33.0EX.1400 | CLS l Concrete Works for Fabricated Channel | 8 | 8 | 2026-11-12 | 2026-11-21 | 0% | 0% | 70
CO.CL.D33.0EX.1410 | CLS l Protection works for Fabricated Channel | 8 | 8 | 2026-11-22 | 2026-11-30 | 0% | 0% | 70
CO.CL.D33.0EX.1405 | CLS l Backfilling works for Fabricated Channel | 8 | 8 | 2026-12-01 | 2026-12-09 | 0% | 0% | 70
KAFD00330-636-SBC-UP-261029.5.3.1.7Connecting Works to Existing Networks |  | 40 | 37 | 03-Sep-26 A | 2027-02-24 | 0% | 40% | -5
CO.CL.D33.0EX.1435 | CLS l Connecting Works to Existing Networks part 5 (P4.11) | 8 | 5 | 03-Sep-26 A | 2027-02-24 | 0% | 40% | -5
CO.CL.D33.0EX.1430 | CLS l Connecting Works to Existing Networks part 4 (P2.15) | 8 | 5 | 03-Sep-26 A | 2027-02-14 | 0% | 40% | 3
CO.CL.D33.0EX.1425 | CLS l Connecting Works to Existing Networks part 3 (P2.09) | 8 | 5 | 03-Sep-26 A | 2027-02-04 | 0% | 40% | 11
CO.CL.D33.0EX.1420 | CLS l Connecting Works to Existing Networks part 2 (P1.11) | 8 | 5 | 03-Sep-26 A | 2027-01-26 | 0% | 40% | 19
CO.CL.D33.0EX.1415 | CLS l Connecting Works to Existing Networks part 1 (9 Parcel) | 8 | 5 | 03-Sep-26 A | 2027-01-17 | 0% | 40% | 27
KAFD00330-636-SBC-UP-261029.5.3.2Electrical |  | 37 | 37 | 2026-12-29 | 2027-02-09 | 0% | 0% | 7
KAFD00330-636-SBC-UP-261029.5.3.2.1Remote terminal unit (RTU) |  | 37 | 37 | 2026-12-29 | 2027-02-09 | 0% | 0% | 7
CO.CL.D33.0EX.1470 | CLS l Remote terminal unit connection works part 1 | 6 | 6 | 2026-12-29 | 2027-01-04 | 0% | 0% | 20
CO.CL.D33.0EX.1460 | CLS l Remote terminal unit connection works part 2 | 6 | 6 | 2027-01-05 | 2027-01-11 | 0% | 0% | 20
CO.CL.D33.0EX.1465 | CLS l Remote terminal unit connection works part 3 | 6 | 6 | 2027-01-12 | 2027-01-18 | 0% | 0% | 20
CO.CL.D33.0EX.1475 | CLS l Remote terminal unit connection works part 4 | 6 | 6 | 2027-01-19 | 2027-01-25 | 0% | 0% | 20
CO.CL.D33.0EX.1455 | CLS l Install of Remote terminal unit panel | 8 | 8 | 2027-02-01 | 2027-02-09 | 0% | 0% | 7
KAFD00330-636-SBC-UP-261029.5.3.3Communication System |  | 232 | 46 | 18-Jun-26 A | 2027-01-31 | 27.21% | 42.75% | 7
KAFD00330-636-SBC-UP-261029.5.3.3.1Fiber Optic Cable Network |  | 232 | 46 | 18-Jun-26 A | 2027-01-31 | 27.21% | 42.75% | 7
CO.CL.D33.0EX.1480 | CLS l Install of Fiber optic conduits part 1 (9 Parcel) | 11 | 4 | 18-Jun-26 A | 2026-12-13 | 0% | 60% | 7
CO.CL.D33.0EX.1485 | CLS l Install of Fiber optic conduits part 2 (P1.11) | 11 | 6 | 18-Jun-26 A | 2026-12-15 | 0% | 50% | 7
CO.CL.D33.0EX.1490 | CLS l Install of Fiber optic conduits part 3 (P2.09) | 11 | 6 | 25-Jun-26 A | 2026-12-15 | 100% | 50% | 7
CO.CL.D33.0EX.1495 | CLS l Install of Fiber optic conduits part 4 (P2.15) | 11 | 6 | 02-Jul-26 A | 2026-12-15 | 100% | 50% | 7
CO.CL.D33.0EX.1500 | CLS l Install of Fiber optic conduits part 5 (P4.11) | 11 | 6 | 02-Jul-26 A | 2026-12-15 | 100% | 50% | 7
CO.CL.D33.0EX.1520 | CLS l Install of Fiber optic Cables part 1 (9 Parcel) | 8 | 8 | 2026-12-16 | 2026-12-24 | 0% | 0% | 7
CO.CL.D33.0EX.1525 | CLS l Install of Fiber optic Cables part 2 (P1.11) | 8 | 8 | 2026-12-26 | 2027-01-03 | 0% | 0% | 7
CO.CL.D33.0EX.1530 | CLS l Install of Fiber optic Cables part 3 (P2.09) | 8 | 8 | 2027-01-04 | 2027-01-12 | 0% | 0% | 7
CO.CL.D33.0EX.1535 | CLS l Install of Fiber optic Cables part 4 (P2.15) | 8 | 8 | 2027-01-13 | 2027-01-21 | 0% | 0% | 7
CO.CL.D33.0EX.1540 | CLS l Install of Fiber optic Cables part 5 (P4.11) | 8 | 8 | 2027-01-23 | 2027-01-31 | 0% | 0% | 7
KAFD00330-636-SBC-UP-261029.6Testing & Commissioning |  | 190 | 190 | 2026-11-26 | 2027-07-13 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.6.1RO Plant |  | 38 | 38 | 2027-05-31 | 2027-07-13 | 0% | 0% | -95
TC.RO.D07.GEN.1000 | RO l Testing & Termination for Thermal & Moisture insulation works | 7 | 7 | 2027-05-31 | 2027-06-07 | 0% | 0% | -71
TC.RO.D33.GEN.1050 | RO l Testing & Termination for Brackish Water Reverse Osmosis Plant | 20 | 20 | 2027-06-21 | 2027-07-13 | 0% | 0% | -95
TC.RO.D22.GEN.1015 | RO l Testing & Termination for Plumbing Works | 8 | 8 | 2027-06-24 | 2027-07-03 | 0% | 0% | -92
TC.RO.D27.GEN.1040 | RO l Testing & Termination for Communication System | 6 | 6 | 2027-06-26 | 2027-07-01 | 0% | 0% | -93
TC.RO.D28.GEN.1045 | RO l Testing & Termination for Access control CCTV system | 6 | 6 | 2027-06-26 | 2027-07-01 | 0% | 0% | -93
TC.RO.D40.GEN.1055 | RO l Testing & Termination for Process scada system and intrumentation | 6 | 6 | 2027-06-26 | 2027-07-01 | 0% | 0% | -85
TC.RO.D23.GEN.1020 | RO l Testing & Termination for HVAC Piping | 8 | 8 | 2027-06-28 | 2027-07-06 | 0% | 0% | -95
TC.RO.D21.GEN.1010 | RO l Testing & Termination for Fire Suppression | 8 | 8 | 2027-06-28 | 2027-07-06 | 0% | 0% | -95
TC.RO.D26.GEN.1030 | RO l Testing & Termination for MDB & UPS | 7 | 7 | 2027-06-28 | 2027-07-05 | 0% | 0% | -95
TC.RO.D14.GEN.1005 | RO l Testing & Termination for Elevator | 8 | 8 | 2027-06-28 | 2027-07-06 | 0% | 0% | -95
TC.RO.D26.GEN.1025 | RO l Testing & Termination for Meduim Voltage & Diesel Generators | 8 | 8 | 2027-06-30 | 2027-07-08 | 0% | 0% | -91
TC.RO.D26.GEN.1035 | RO l Testing & Termination for Lightning System and Low current | 6 | 6 | 2027-07-07 | 2027-07-13 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.6.2Pump-Station |  | 63 | 63 | 2026-11-26 | 2027-02-07 | 0% | 0% | -1
TC.PS.D10.GEN.1060 | IPS l Testing & Termination for Fire Extinguisher | 10 | 10 | 2026-11-26 | 2026-12-07 | 0% | 0% | 52
TC.PS.D23.GEN.1070 | IPS l Testing & Termination for HVAC System | 10 | 10 | 2026-12-05 | 2026-12-15 | 0% | 0% | 45
TC.PS.D21.GEN.1075 | IPS l Testing & Termination for Fire Suppression | 10 | 10 | 2026-12-07 | 2026-12-17 | 0% | 0% | 43
TC.PS.D28.GEN.1085 | IPS l Testing & Termination for Electronic Safety and Security | 10 | 10 | 2026-12-14 | 2026-12-24 | 0% | 0% | 37
TC.PS.D27.GEN.1080 | IPS l Testing & Termination for Communication System | 10 | 10 | 2026-12-20 | 2026-12-30 | 0% | 0% | 32
TC.PS.D22.GEN.1065 | IPS l Testing & Termination for Plumbing Works | 10 | 10 | 2027-01-18 | 2027-01-28 | 0% | 0% | 7
TC.PS.D26.GEN.1075 | IPS l Testing & Termination for Electrical Works | 10 | 10 | 2027-01-23 | 2027-02-02 | 0% | 0% | 3
TC.PS.D40.GEN.1085 | IPS l Testing & Termination for Process scada system and intrumentation | 10 | 10 | 2027-01-27 | 2027-02-07 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.6.3Collection System |  | 69 | 69 | 2027-02-01 | 2027-04-26 | 0% | 0% | -44
TC.CL.D33.GEN.1115 | CLS l Testing & Termination for Fiber Optic Cables and Conduits | 10 | 10 | 2027-02-01 | 2027-02-11 | 0% | 0% | 15
TC.CL.D33.GEN.1110 | CLS l Testing & Termination for Remote terminal unit (RTU) | 10 | 10 | 2027-02-10 | 2027-02-21 | 0% | 0% | 7
TC.CL.D33.GEN.1120 | CLS l Testing & Termination for Connecting Works to Existing Networks | 10 | 10 | 2027-02-25 | 2027-03-08 | 0% | 0% | -5
TC.CL.D22.GEN.1090 | CLS l Testing & Termination for Submersible pumps | 10 | 10 | 2027-04-15 | 2027-04-26 | 0% | 0% | -44
TC.CL.D33.GEN.1095 | CLS l Testing & Termination for GRP pipes | 10 | 10 | 2027-04-15 | 2027-04-26 | 0% | 0% | -44
TC.CL.D33.GEN.1100 | CLS l Testing & Termination for HDPE pipes | 10 | 10 | 2027-04-15 | 2027-04-26 | 0% | 0% | -44
TC.CL.D33.GEN.1105 | CLS l Testing & Termination for Valves Work | 10 | 10 | 2027-04-15 | 2027-04-26 | 0% | 0% | -44
KAFD00330-636-SBC-UP-261029.7Hand-Over |  | 245 | 245 | 2026-11-23 | 2027-07-25 | 0% | 0% | -116
KAFD00330-636-SBC-UP-261029.7.1RO Plant |  | 62 | 62 | 2027-05-25 | 2027-07-25 | 0% | 0% | -116
KAFD00330-636-SBC-UP-261029.7.1.1RO Plant As-Built Drawings |  | 62 | 62 | 2027-05-25 | 2027-07-25 | 0% | 0% | -116
KAFD00330-636-SBC-UP-261029.7.1.1.1RO Plant As-Built Drawing Submittal |  | 36 | 36 | 2027-05-25 | 2027-07-05 | 0% | 0% | -95
HO.RO.0GN.ADS.1005 | RO l As-built drawings Submission for Masonry Works | 7 | 7 | 2027-05-25 | 2027-06-01 | 0% | 0% | -66
HO.RO.0GN.ADS.1015 | RO l As-built drawings Submission for Wood and Plastics | 7 | 7 | 2027-05-27 | 2027-06-03 | 0% | 0% | -68
HO.RO.0GN.ADS.1055 | RO l As-built drawings Submission for Earth Work | 7 | 7 | 2027-05-30 | 2027-06-06 | 0% | 0% | -70
HO.RO.0GN.ADS.1060 | RO l As-built drawings Submission for Exterior Improvement | 7 | 7 | 2027-06-01 | 2027-06-08 | 0% | 0% | -72
HO.RO.0GN.ADS.1000 | RO l As-built drawings Submission for Concrete Works | 7 | 7 | 2027-06-02 | 2027-06-09 | 0% | 0% | -73
HO.RO.0GN.ADS.1020 | RO l As-built drawings Submission for Thermal and Moisture Protection | 7 | 7 | 2027-06-07 | 2027-06-14 | 0% | 0% | -77
HO.RO.0GN.ADS.1065 | RO l As-built drawings Submission for Utilities | 7 | 7 | 2027-06-21 | 2027-06-28 | 0% | 0% | -89
HO.RO.0GN.ADS.1035 | RO l As-built drawings Submission for Plumbing Works | 7 | 7 | 2027-06-24 | 2027-07-01 | 0% | 0% | -92
HO.RO.0GN.ADS.1010 | RO l As-built drawings Submission for Metal Works | 7 | 7 | 2027-06-26 | 2027-07-03 | 0% | 0% | -95
HO.RO.0GN.ADS.1025 | RO l As-built drawings Submission for Doors and Windows | 7 | 7 | 2027-06-26 | 2027-07-03 | 0% | 0% | -95
HO.RO.0GN.ADS.1070 | RO l As-built drawings Submission for Process scada system | 7 | 7 | 2027-06-26 | 2027-07-03 | 0% | 0% | -95
HO.RO.0GN.ADS.1045 | RO l As-built drawings Submission for Communication System | 7 | 7 | 2027-06-26 | 2027-07-03 | 0% | 0% | -95
HO.RO.0GN.ADS.1050 | RO l As-built drawings Submission for Electronic Safety and Security | 7 | 7 | 2027-06-26 | 2027-07-03 | 0% | 0% | -95
HO.RO.0GN.ADS.1030 | RO l As-built drawings Submission for Fire Fighting | 7 | 7 | 2027-06-28 | 2027-07-05 | 0% | 0% | -95
HO.RO.0GN.ADS.1040 | RO l As-built drawings Submission for HVAC System | 7 | 7 | 2027-06-28 | 2027-07-05 | 0% | 0% | -95
HO.RO.0GN.ADS.1080 | RO l As-built drawings Submission for Elevators | 7 | 7 | 2027-06-28 | 2027-07-05 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.7.1.1.2RO Plant As-Built Drawing Approval |  | 38 | 38 | 2027-06-02 | 2027-07-25 | 0% | 0% | -79
HO.RO.0GN.ADA.1005 | RO l As-built drawings Approval for Masonry Works | 14 | 14 | 2027-06-02 | 2027-06-21 | 0% | 0% | -55
HO.RO.0GN.ADA.1015 | RO l As-built drawings Approval for Wood and Plastics | 14 | 14 | 2027-06-06 | 2027-06-23 | 0% | 0% | -57
HO.RO.0GN.ADA.1055 | RO l As-built drawings Approval for Earth Work | 14 | 14 | 2027-06-07 | 2027-06-24 | 0% | 0% | -58
HO.RO.0GN.ADA.1060 | RO l As-built drawings Approval for Exterior Improvement | 14 | 14 | 2027-06-09 | 2027-06-28 | 0% | 0% | -60
HO.RO.0GN.ADA.1000 | RO l As-built drawings Approval for Concrete Works | 14 | 14 | 2027-06-10 | 2027-06-29 | 0% | 0% | -61
HO.RO.0GN.ADA.1020 | RO l As-built drawings Approval for Thermal and Moisture Protection | 14 | 14 | 2027-06-15 | 2027-07-04 | 0% | 0% | -64
HO.RO.0GN.ADA.1065 | RO l As-built drawings Approval for Utilities | 14 | 14 | 2027-06-29 | 2027-07-18 | 0% | 0% | -74
HO.RO.0GN.ADA.1010 | RO l As-built drawings Approval for Metal Works | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -78
HO.RO.0GN.ADA.1025 | RO l As-built drawings Approval for Doors and Windows | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -78
HO.RO.0GN.ADA.1070 | RO l As-built drawings Approval for Process scada system | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -78
HO.RO.0GN.ADA.1045 | RO l As-built drawings Approval for Communication System | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -78
HO.RO.0GN.ADA.1050 | RO l As-built drawings Approval for Electronic Safety and Security | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -78
HO.RO.0GN.ADA.1035 | RO l As-built drawings Approval for Plumbing Works | 14 | 14 | 2027-07-04 | 2027-07-21 | 0% | 0% | -77
HO.RO.0GN.ADA.1030 | RO l As-built drawings Approval for Fire Fighting | 14 | 14 | 2027-07-06 | 2027-07-25 | 0% | 0% | -79
HO.RO.0GN.ADA.1040 | RO l As-built drawings Approval for HVAC System | 14 | 14 | 2027-07-06 | 2027-07-25 | 0% | 0% | -79
HO.RO.0GN.ADA.1080 | RO l As-built drawings Approval for Elevators | 14 | 14 | 2027-07-06 | 2027-07-25 | 0% | 0% | -79
KAFD00330-636-SBC-UP-261029.7.1.2RO Plant Snagging& Desnagging |  | 29 | 29 | 2027-06-03 | 2027-07-06 | 0% | 0% | -89
HO.RO.0GN.SNG.1085 | RO l Snagging & desnagging for Furnishings Work | 10 | 10 | 2027-06-03 | 2027-06-14 | 0% | 0% | -70
HO.RO.0GN.SNG.1075 | RO l Snagging & desnagging for Finishing Works | 10 | 10 | 2027-06-20 | 2027-06-30 | 0% | 0% | -84
HO.RO.0GN.SNG.1090 | RO l Snagging & desnagging for Aluminium Control booths | 10 | 10 | 2027-06-24 | 2027-07-05 | 0% | 0% | -88
HO.RO.0GN.SNG.1080 | RO l Snagging & desnagging for Specialtes Work | 10 | 10 | 2027-06-26 | 2027-07-06 | 0% | 0% | -89
KAFD00330-636-SBC-UP-261029.7.1.3RO Plant Manual and Maintenance |  | 8 | 8 | 2027-07-14 | 2027-07-22 | 0% | 0% | -95
HO.RO.0GN.0OM.1095 | RO l Operation and Maintenance Manuals | 8 | 8 | 2027-07-14 | 2027-07-22 | 0% | 0% | -95
KAFD00330-636-SBC-UP-261029.7.1.4RO Plant Demobilization |  | 9 | 9 | 2027-07-07 | 2027-07-17 | 0% | 0% | -89
HO.RO.0GN.0DM.1100 | RO l Demobilization works | 9 | 9 | 2027-07-07 | 2027-07-17 | 0% | 0% | -89
KAFD00330-636-SBC-UP-261029.7.1.5RO Plant TOC |  | 1 | 1 | 2027-07-25 | 2027-07-25 | 0% | 0% | -79
HO.RO.0GN.TOC.1105 | RO l Completion of TOC (Take Over Certificate) | 1 | 1 | 2027-07-25 | 2027-07-25 | 0% | 0% | -79
KAFD00330-636-SBC-UP-261029.7.1.6RO Plant CDC and CDA |  | 19 | 19 | 2027-06-28 | 2027-07-22 | 0% | 0% | -78
HO.RO.0GN.CDC.1120 | RO l Civil Defense Certificate | 5 | 5 | 2027-06-28 | 2027-07-04 | 0% | 0% | -78
HO.RO.0GN.CDA.1130 | RO l Civil Defense Approval | 14 | 14 | 2027-07-05 | 2027-07-22 | 0% | 0% | -78
KAFD00330-636-SBC-UP-261029.7.2Pump-Station |  | 130 | 130 | 2026-11-23 | 2027-04-01 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.7.2.1Pump Station As-Built Drawings |  | 83 | 83 | 2026-12-05 | 2027-02-25 | 0% | 0% | 4
KAFD00330-636-SBC-UP-261029.7.2.1.1Pump Station As-Built Drawings Submittal |  | 54 | 54 | 2026-12-05 | 2027-02-04 | 0% | 0% | 3
HO.PS.0GN.ADS.1045 | IPS l As-built drawings Submission for HVAC System | 7 | 7 | 2026-12-05 | 2026-12-12 | 0% | 0% | 50
HO.PS.0GN.ADS.1035 | IPS l As-built drawings Submission for Fire Fighting | 7 | 7 | 2026-12-07 | 2026-12-14 | 0% | 0% | 41
HO.PS.0GN.ADS.1055 | IPS l As-built drawings Submission for Electronic Safety and Security | 7 | 7 | 2026-12-14 | 2026-12-21 | 0% | 0% | 42
HO.PS.0GN.ADS.1050 | IPS l As-built drawings Submission for Communication System | 7 | 7 | 2026-12-20 | 2026-12-27 | 0% | 0% | 37
HO.PS.0GN.ADS.1060 | IPS l As-built drawings Submission for Electronic Earth Work | 7 | 7 | 2027-01-04 | 2027-01-11 | 0% | 0% | 3
HO.PS.0GN.ADS.1000 | IPS l As-built drawings Submission for Existing Condition | 7 | 7 | 2027-01-04 | 2027-01-11 | 0% | 0% | 3
HO.PS.0GN.ADS.1025 | IPS l As-built drawings Submission for Thermal and Moisture Protection | 7 | 7 | 2027-01-12 | 2027-01-19 | 0% | 0% | 3
HO.PS.0GN.ADS.1005 | IPS l As-built drawings Submission for Concrete Works | 7 | 7 | 2027-01-12 | 2027-01-19 | 0% | 0% | 3
HO.PS.0GN.ADS.1065 | IPS l As-built drawings Submission for Exterior Improvement | 7 | 7 | 2027-01-17 | 2027-01-24 | 0% | 0% | 13
HO.PS.0GN.ADS.1040 | IPS l As-built drawings Submission for Plumbing Works | 7 | 7 | 2027-01-18 | 2027-01-25 | 0% | 0% | 12
HO.PS.0GN.ADS.1010 | IPS l As-built drawings Submission for Masonry Works | 7 | 7 | 2027-01-20 | 2027-01-27 | 0% | 0% | 3
HO.PS.0GN.ADS.1030 | IPS l As-built drawings Submission for Doors and Windows | 7 | 7 | 2027-01-20 | 2027-01-27 | 0% | 0% | 3
HO.PS.0GN.ADS.1070 | IPS l As-built drawings Submission for Process scada system | 7 | 7 | 2027-01-27 | 2027-02-03 | 0% | 0% | 4
HO.PS.0GN.ADS.1015 | IPS l As-built drawings Submission for Metal Works | 7 | 7 | 2027-01-28 | 2027-02-04 | 0% | 0% | 3
HO.PS.0GN.ADS.1020 | IPS l As-built drawings Submission for Wood and Plastics | 7 | 7 | 2027-01-28 | 2027-02-04 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.7.2.1.2Pump Station As-Built Drawings Approval |  | 54 | 54 | 2026-12-13 | 2027-02-25 | 0% | 0% | 2
HO.PS.0GN.ADA.1045 | IPS l As-built drawings Approval for HVAC System | 14 | 14 | 2026-12-13 | 2026-12-30 | 0% | 0% | 42
HO.PS.0GN.ADA.1035 | IPS l As-built drawings Approval for Fire Fighting | 14 | 14 | 2026-12-15 | 2027-01-03 | 0% | 0% | 40
HO.PS.0GN.ADA.1055 | IPS l As-built drawings Approval for Electronic Safety and Security | 14 | 14 | 2026-12-22 | 2027-01-10 | 0% | 0% | 35
HO.PS.0GN.ADA.1050 | IPS l As-built drawings Approval for Communication System | 14 | 14 | 2026-12-28 | 2027-01-14 | 0% | 0% | 31
HO.PS.0GN.ADA.1060 | IPS l As-built drawings Approval for Electronic Earth Work | 14 | 14 | 2027-01-12 | 2027-01-31 | 0% | 0% | 20
HO.PS.0GN.ADA.1000 | IPS l As-built drawings Approval for Existing Condition | 14 | 14 | 2027-01-12 | 2027-01-31 | 0% | 0% | 20
HO.PS.0GN.ADA.1025 | IPS l As-built drawings Approval for Thermal and Moisture Protection | 14 | 14 | 2027-01-20 | 2027-02-08 | 0% | 0% | 14
HO.PS.0GN.ADA.1005 | IPS l As-built drawings Approval for Concrete Works | 14 | 14 | 2027-01-20 | 2027-02-08 | 0% | 0% | 14
HO.PS.0GN.ADA.1065 | IPS l As-built drawings Approval for Exterior Improvement | 14 | 14 | 2027-01-25 | 2027-02-11 | 0% | 0% | 11
HO.PS.0GN.ADA.1040 | IPS l As-built drawings Approval for Plumbing Works | 14 | 14 | 2027-01-26 | 2027-02-14 | 0% | 0% | 10
HO.PS.0GN.ADA.1010 | IPS l As-built drawings Approval for Masonry Works | 14 | 14 | 2027-01-28 | 2027-02-16 | 0% | 0% | 8
HO.PS.0GN.ADA.1030 | IPS l As-built drawings Approval for Doors and Windows | 14 | 14 | 2027-01-28 | 2027-02-16 | 0% | 0% | 8
HO.PS.0GN.ADA.1070 | IPS l As-built drawings Approval for Process scada system | 14 | 14 | 2027-02-04 | 2027-02-24 | 0% | 0% | 3
HO.PS.0GN.ADA.1015 | IPS l As-built drawings Approval for Metal Works | 14 | 14 | 2027-02-07 | 2027-02-25 | 0% | 0% | 2
HO.PS.0GN.ADA.1020 | IPS l As-built drawings Approval for Wood and Plastics | 14 | 14 | 2027-02-07 | 2027-02-25 | 0% | 0% | 2
KAFD00330-636-SBC-UP-261029.7.2.2Pump Station Snagging& Desnagging |  | 36 | 36 | 2026-11-23 | 2027-01-03 | 0% | 0% | 41
HO.PS.0GN.SNG.1075 | IPS l Snagging & desnagging for Finishing Works | 14 | 14 | 2026-11-23 | 2026-12-08 | 0% | 0% | 63
HO.PS.0GN.SNG.1080 | IPS l Snagging & desnagging for Specialtes Work | 14 | 14 | 2026-11-26 | 2026-12-12 | 0% | 0% | 60
HO.PS.0GN.SNG.1085 | IPS l Snagging & desnagging for Aluminium Control booths | 14 | 14 | 2026-12-19 | 2027-01-03 | 0% | 0% | 41
KAFD00330-636-SBC-UP-261029.7.2.3Pump Station Manual and Maintenance |  | 7 | 7 | 2027-02-27 | 2027-03-06 | 0% | 0% | 3
HO.PS.0GN.0OM.1090 | IPS l Operation and Maintenance Manuals | 7 | 7 | 2027-02-27 | 2027-03-06 | 0% | 0% | 3
KAFD00330-636-SBC-UP-261029.7.2.4Pump-Station Demobilization |  | 14 | 14 | 2027-01-04 | 2027-01-19 | 0% | 0% | 41
HO.PS.0GN.0DM.1095 | IPS l Demobilization works | 14 | 14 | 2027-01-04 | 2027-01-19 | 0% | 0% | 41
KAFD00330-636-SBC-UP-261029.7.2.5Pump-Station TOC |  | 14 | 14 | 2027-03-15 | 2027-04-01 | 0% | 0% | -1
HO.PS.0GN.TOC.1100 | IPS l Completion of TOC (Take Over Certificate) | 14 | 14 | 2027-03-15 | 2027-04-01 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.7.2.6Pump-Station CDC and CDA |  | 21 | 21 | 2027-02-08 | 2027-03-14 | 0% | 0% | -1
HO.PS.0GN.CDC.1130 | IPS l Civil Defense Certificate | 7 | 7 | 2027-02-08 | 2027-02-16 | 0% | 0% | -1
HO.PS.0GN.CDA.1140 | IPS l Civil Defense Approval | 14 | 14 | 2027-02-17 | 2027-03-14 | 0% | 0% | -1
KAFD00330-636-SBC-UP-261029.7.3Collection System |  | 137 | 137 | 2027-02-08 | 2027-06-24 | 0% | 0% | -85
KAFD00330-636-SBC-UP-261029.7.3.1Collection System As-Built Drawing |  | 28 | 28 | 2027-04-15 | 2027-05-12 | 0% | 0% | -86
KAFD00330-636-SBC-UP-261029.7.3.1.1Collection System As-Built Drawing Submittal |  | 8 | 8 | 2027-04-15 | 2027-04-24 | 0% | 0% | -71
HO.CL.0GN.ADS.1005 | CLS l As-built drawings Submission for Pipes and Valves Work | 8 | 8 | 2027-04-15 | 2027-04-24 | 0% | 0% | -71
HO.CL.0GN.ADS.1000 | CLS l As-built drawings Submission for Plumbing Works | 8 | 8 | 2027-04-15 | 2027-04-24 | 0% | 0% | -71
KAFD00330-636-SBC-UP-261029.7.3.1.2Collection System As-Built Drawing Approval |  | 14 | 14 | 2027-04-25 | 2027-05-12 | 0% | 0% | -58
HO.CL.0GN.ADA.1005 | CLS l As-built drawings Approval for Pipes and Valves Work | 14 | 14 | 2027-04-25 | 2027-05-12 | 0% | 0% | -58
HO.CL.0GN.ADA.1000 | CLS l As-built drawings Approval for Plumbing Works | 14 | 14 | 2027-04-25 | 2027-05-12 | 0% | 0% | -58
KAFD00330-636-SBC-UP-261029.7.3.2Collection System Snagging& Desnagging |  | 14 | 14 | 2027-04-15 | 2027-05-01 | 0% | 0% | -34
HO.CL.0GN.SNG.1010 | CLS l Snagging & desnagging | 14 | 14 | 2027-04-15 | 2027-05-01 | 0% | 0% | -34
KAFD00330-636-SBC-UP-261029.7.3.3Collection System Manual and Maintenance |  | 14 | 14 | 2027-04-27 | 2027-05-12 | 0% | 0% | -44
HO.CL.0GN.0OM.1015 | CLS l Operation and Maintenance Manuals | 14 | 14 | 2027-04-27 | 2027-05-12 | 0% | 0% | -44
KAFD00330-636-SBC-UP-261029.7.3.4Collection System Demobilization |  | 14 | 14 | 2027-02-08 | 2027-02-24 | 0% | 0% | 27
HO.CL.0GN.0DM.1020 | CLS l Demobilization works | 14 | 14 | 2027-02-08 | 2027-02-24 | 0% | 0% | 27
KAFD00330-636-SBC-UP-261029.7.3.5Collection System TOC |  | 7 | 7 | 2027-06-16 | 2027-06-24 | 0% | 0% | -58
HO.CL.0GN.TOC.1025 | CLS l Completion of TOC (Take Over Certificate) | 7 | 7 | 2027-06-16 | 2027-06-24 | 0% | 0% | -58
KAFD00330-636-SBC-UP-261029.7.3.6Collection System CDC and CDA |  | 21 | 21 | 2027-05-13 | 2027-06-15 | 0% | 0% | -58
HO.CL.0GN.CDC.1140 | CLS l Civil Defense Certificate | 7 | 7 | 2027-05-13 | 2027-05-26 | 0% | 0% | -58
HO.CL.0GN.CDA.1150 | CLS l Civil Defense Approval | 14 | 14 | 2027-05-27 | 2027-06-15 | 0% | 0% | -58